## Sheet1
Mid-Year Assessment
|  | Community Services | MID - YEAR | REPORT | 2016/17
Mr S.Cele
Ref | Strategic Objective | Target | Target Date | Actual Date | Target no | Actual no | Comments | Blockages | Corrective Measures | Dir | MM | Cons | Panel
KPA 1.Basic Service Delivery and Infrastructure Development
[10 empty] | 4 | 4 | 4 | 4
Com 2 |  | Construction and Supervision | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.Construction has started.
(eDumbe Regional Stadium )
Com 3 |  | Construction and Supervision | Mid -Year | N/A | 1 | 0 | Not Achieved. | SCM Delays | The project was | 2 | 2 | 2 | 2
|  | ( Bhadeni Stadium ) | [6 empty] | advertised on 10/8/2016
Com 4 |  | Construction and Supervision | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.Construction has started. |  |  | 4 | 4 | 4 | 4
(Nhlakanipho Hall )
Com 5 |  | Construction and Supervision | Mid -Year | N/A | 1 | 0 | Not Achieved. | SCM Delays | The project was | 3 | 3 | 3 | 3
|  | ( Bhadeni Hall ) | [6 empty] | advertised on 10/8/2016
KPA 2. Local Economic Development
Com 6 |  | 40 Workers in the Programme | Mid -Year | 31/12/2016 | 40 | 24 | Not Achieved.Only 24 workers were |  |  | 2 | 2 | 2 | 2
in the programme
Com 7 |  | 20 created job opportunities | Mid -Year | 31/12/2016 | 20 | 20 | Achieved.20 Job opportunities were |  |  | 4 | 4 | 4 | 4
|  | through each Mig Project |  |  |  |  | created through Bhadeni Hall &
Nhlakanipho Hall.
Com 8 |  | 2 Provincial CWP Meetings | Mid -Year | 31/12/2016 | 2 | 2 | Achieved.Two meetings were attended. |  |  | 4 | 4 | 4 | 4
attended
Com 9 |  | 6 CWP Meetings attended | Mid -Year | 21/07/2016 | 6 | 3 | Partially Achieved.3 CWP Meetings were |  |  | 3 | 3 | 3 | 3
|  |  |  | 19/10/2016 |  |  | convened on the following dates:
|  |  |  | 24/11/2016 |  |  | 21/07/2016,19/10/2016 & 24/11/2016.
Com 10 |  | Participated at Umkhosi | Mid -Year | 9-11/09/2016 | 1 | 1 | Achieved |  |  | 4 | 4 | 4 | 4
woMhlanga
Com 11 |  | 10 Arts & Culture Programme | Mid -Year | 31/12/2016 | 10 | 13 | Over-Achieved.The following programmes |  |  | 5 | 5 | 5 | 5
|  | implememnted |  |  |  |  | were implemented:
Umbele Wethu ( 06/07/2016 )
Story Telling & Games ( 17/07/2016 )
Story Telling & Painting ( 16/08/2016 )
Story Telling & Painting ( 23/08/2016 )
Woman's Celebration ( 01/08/2016 )
Umkhosi Womhlanga ( 9-11/9/2016 )
Azibuye emasisweni Dance ( 19/9/2016 )
Umkhosi WeLembe ( 24/9/2016 )
Arts & Culture,Games & Painting (3/10/16 )
Ingoma Competition ( 26/12/2016 &
28/12/2016 )
Cothoza Competition ( 27/12/2016 )
Oswenka Competition ( 27/12/2016 0
Com 13 |  | 4 Functional Forums established | Mid -Year | N/A | 4 | 0 | Not Achieved | The Council has not yet approved | Moved to Q3 | 2 | 2 | 2 | 2
the dates for election
Com 14 |  | 3 Local Federation Structures | Mid -Year | 31/12/2016 | 7 | 2 | Partially Achieved.Only two Federation | Transport to Wards. |  | 3 | 3 | 3 | 3
|  | established |  |  |  |  | structures have been established.
Com 15 |  | 3 Sports structures established | Mid -Year | N/A | 3 | 0 | Not Achieved. |  |  | 2 | 2 | 2 | 2
Com 17 |  | 2 Meetings held to | Mid -Year | N/A | 2 | 0 | Not Achieved. |  |  | 2 | 2 | 2 | 2
facilitate intergration
Com 18 |  | 1Leagues established | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.Football league has been |  |  | 4 | 4 | 4 | 4
established.
Com 19 |  | 12 Sports Programme | Mid -Year | 23/07/2016 | 12 | 7 | Partially Achieved . Mayoral Cup Games was | Financial Constraint. |  | 3 | 3 | 3 | 3
|  |  |  | 21/07/2061 |  |  | organised on 23/07/2016.Local Senior
|  |  |  | 27/07/2016 |  |  | Golden Games on 21/07/2016 ,
|  |  |  | 26-28/08/16 |  |  | District Golden Games on 27/07/2016
|  |  |  | 8-12/12/16 |  |  | and Provincial Indigenous Games on
|  |  |  | 16-18/12/16 |  |  | 26-28/08/2016,Salga Games 8-12 Dec 2016,
|  |  |  | 2016-07-01 |  |  | Mayor's Dec Tournament 16-18 Dec 2016 &
Dundee Horse Race July 2016.
Com 20 |  | 2 LAC and ACC Meetings held | Mid -Year | N/A | 2 | 0 | Not Achieved | The responsible official was | The Municipality has | 2 | 2 | 2 | 2
[8 empty] | acting as an assistant manager | deployed Mr D.P.
[8 empty] | in the office of the Mayor.He | Mpungose to perform
[8 empty] | did not have enough time to | duties of the previous
[8 empty] | perform other duties | incumbent,however
there is no improvement
sincecurrent incumbent
is still waiting for the
election of ward
committee members.
Com 23 |  | 3 Youth Programmes | Mid -Year | N/A | 3 | 0 | Not Achieved. | Financial Constraints |  | 2 | 2 | 2 | 2
KPA 3.Good Governance,Community Participation and Ward Committee Systems
Com 25 |  | 48 War-rooms meetings | Mid -Year | N/A | 48 | 0 | Not Achieved | The responsible official was | The Municipality has | 2 | 2 | 2 | 2
[8 empty] | acting as an assistant manager | deployed Mr D.P.
[8 empty] | in the office of the Mayor.He | Mpungose to perform
[8 empty] | did not have enough time to | duties of the previous
[8 empty] | perform other duties | incumbent,however
there is no improvement
sincecurrent incumbent
is still waiting for the
election of ward
committee members.
Com 26 |  | 2 Meetings for Local Task | Mid -Year | N/A | 2 | 0 | Not Achieved | Not Achieved in Q1 |  | 2 | 2 | 2 | 2
Team held
KPA 4. Cross Cutting Interventions
Com 27 |  | Inception ( Waste Management Plan ) | Mid -Year | N/A | 1 | 0 | Not Achieved | The problem is with the | The target is included in | 2 | 2 | 2 | 2
[8 empty] | National Department of | the Landfill site project.
Environmental affairs.
Com 28 |  | Inception (Environmental Assessment ) | Mid -Year | N/A | 1 | 0 | Not Achieved | The Municipality does not have a |  | 2 | 2 | 2 | 2
project that requires assessment.
Com 29 |  | First Stage of Fencing ( Dumpsite ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Financial Constraints. | SDBIP to be reviewed | 2 | 2 | 2 | 2
|  | ......................................... |  | .......................................
|  | Signed by Manager Strategic |  | Signed by Municipal Manager
|  | M A Sukazi |  | T V Mkhize
|  | Date................................ |  | Date...............................