## Sheet1
Mid-Year Assessment
|  | Corporate Services | MID - YEAR | REPORT | 2016/17
Mr S.R.Ntuli
Ref | Strategic Objective | Target | Target Date | Actual Date | Target no | Actual no | Comments | Blockages | Corrective Measures | Dir | MM | Conse | Panel
KPA 1.Municipal Transformation and Organisational Development
Cor 1 |  | 2nd Draft of 4 Municipal Policies | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Cor 2 |  | Procurement and 1st draft of By-Laws | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Cor 3 |  | Final draft of reviewed policies | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Cor 4 |  | Report on policy implementation | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Cor 6 |  | Report on by-laws implementation | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Cor 7 |  | Report on critical posts to be filled | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.Report on critical |  |  | 4 | 4 | 4 | 4
posts were submitted
Cor 8 |  | Appointment and Placement of | Mid -Year | 31/12/2016 | 1 | 3 | Over-Achieved.3 New appointments were |  |  | 5 | 5 | 5 | 5
|  | relevant incumbent |  |  |  |  | done by November 2016.
Cor 9 |  | 1 Conducted Municipal Skill Audit | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
( 5 Employees )
Cor 12 |  | 1st Draft ( Skill Dev | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Plan )
Cor 13 |  | 1 st Draft ( HR Strategy) | Mid -Year | N/A | 1 | 0 | Not Achieved. | Budget Constraint. | SDBIP to be reviewed | 2 | 2 | 2 | 2
Cor 14 |  | Reviewed EEP | Mid -Year | N/A | 1 | 0 | Not Achieved. |  | Moved to Q3 | 2 | 2 | 2 | 2
Cor 16 |  | Implementation of ICT Strategy | Mid -Year | 31/12/2016 | 1 | 1 | Partially Achieved.The strategy has not yet |  |  | 3 | 3 | 3 | 3
implemented however it has been submitted
to council for approval.
Cor 17 |  | Implementation of ICT Policies | Mid -Year | 31/12/2016 | 1 | 1 | Partially Achieved.ICT Policies have not been |  |  | 3 | 3 | 3 | 3
implemented ,however they have been
submitted to council for approval.
Cor 18 |  | Implementation of DBR and BCP Policies | Mid -Year | N/A | 1 | 0 | Not Achieved. | Pending the approval by | Waiting for the approval | 2 | 2 | 2 | 2
[8 empty] | Council. | by Council
Cor 20 |  | 2 ICT Steering Committee Meetings | Mid -Year | 16/09/2016 | 2 | 2 | Achieved.The meetings were convened on |  |  | 4 | 4 | 4 | 4
|  |  |  | 12/12/2016 |  |  | the following dates 16/09/2016 & 12/12/16.
Cor 21 |  | Implementation ( ICT Risk Register ) | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.ICT Register is being implemented |  |  | 4 | 4 | 4 | 4
and it is an ongoing process.
KPA 2.Good Governance,Community Participation and Ward Committee Systems
Cor 22 |  | 1 Prepared Schedule of Council and | Mid -Year | 30/09/2016 | 1 | 1 | Achieved.The schedule has |  |  | 4 | 4 | 4 | 4
|  | Council Committee Meetings |  |  |  |  | been prepared.
Cor 23 |  | 2 Council Meetings | Mid -Year | 22/08/2016 | 2 | 4 | Over-Achieved.Council Meetings |  |  | 5 | 5 | 5 | 5
|  |  |  | 08/09/2016 |  |  | were held on the following dated:
|  |  |  | 30/09/2016 |  |  | 22/08/2016,08/09/2016 ,
|  |  |  | 15/12/2016 |  |  | 30/09/2016 &15/12/2016
Cor 24 |  | 6 Council Committee Meetings | Mid -Year | 31/12/2016 | 6 | 6 | Achieved.6 Meetings were convened on the |  |  | 4 | 4 | 4 | 4
following dates:13/10/2016 ( Corporate&
Community ),18/10/2016( Infrastrucure )
21/10/2016( Finance & Planning )
16/11/2016 ( Corporate & Community )
23/11/2016 ( Finance & Planning ) &
23/11/2016( Infrastructure )
Cor 27 |  | 48 Ward Committee Meetings | Mid -Year | N/A | 48 | 0 | Not Achieved.No meeting has been convened, |  |  | 2 | 2 | 2 | 2
however ward committee members have
elected.
KPA 3. Cross Cutting Interventions
Cor 30 |  | 4 Established Disaster Structures | Mid -Year | N/A | 4 | 0 | Not Achieved |  |  | 2 | 2 | 2 | 2
Cor 31 |  | 6 Reports on Disaster Relief Programe | Mid -Year | 31/12/2016 | 6 | 3 | Partially Achieved.3 Reports were |  |  | 3 | 3 | 3 | 3
submitted in Quarter1.
|  | ......................................... |  | .......................................
|  | Signed by Manager Strategic |  | Signed by Municipal Manager
|  | M A Sukazi |  | T V Mkhize
|  | Date................................ |  | Date...............................