## Sheet1
Mid-Year Assessment
|  | Technical Services | MID - YEAR | REPORT | 2016/17
Mr S.Cele
Ref | Strategic Objective | Target | Target Date | Actual Date | Target no | Actual no | Comments | Blockages | Corrective Measures | Dir | MM | Conse | Panel
KPA 2.Basic Service Delivery and Infrastructure Development
Tech 1 |  | TORs and Procurement ( Comprehensive | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
Infrastructure Plan )
Tech 2 |  | TORs and Procurement ( Operations and | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
Mantainance Plan )
Tech 3 |  | TORs and Procurement ( Electricity | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
Master Plan )
Tech 4 |  | Construction and supervision | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | The Municipality is busy | 2 | 2 | 2 | 2
|  | (Luneburg Crech ) | [6 empty] | prioritising the projects.
Tech 5 |  | Construction and supervision | Mid -Year | 30/09/2016 | 1 | 1 | Achieved .Practical Complete |  |  | 4 | 4 | 4 | 4
(Kerk Street )
Tech 6 |  | 250 New Electricity connections | Mid -Year | 31/12/2016 | 250 | 250 | Achieved.
Tech 7 |  | Project Starts | Mid -Year | 30/09/2016 | 1 | 1 | Achieved.Service Provider has |  |  | 4 | 4 | 4 | 4
|  | ( Electrification of Mncelwini) |  |  |  |  | been appointed and has
started working.
Tech 8 |  | Project Starts | Mid -Year | 31/12/2016 | 1 | 1 | Partially Achieved. Service Provider has been |  |  | 3 | 3 | 3 | 3
|  | ( Electrification of Ntungwini) |  |  |  |  | appointed and the project is set to start on
14/01/2017.
Tech 9 |  | Project Starts | Mid -Year | N/A | 1 | 0 | Not Achieved. | Resolving Land issues with |  | 2 | 2 | 2 | 2
|  | ( Electrification of Zungwini) | [5 empty] | farmers regarding project
cadastral.
Tech 10 |  | Project Starts | Mid -Year | 30/09/2016 | 1 | 1 | Achieved.Service Provider has |  |  | 4 | 4 | 4 | 4
|  | ( Electrification of eNkembeni ) |  |  |  |  | been appointed and has
started working.
Tech 11 |  | Project Starts | Mid -Year | 31/12/2016 | 4 | 4 | Achieved. |  |  | 4 | 4 | 4 | 4
( 4 Bilanyoni High Masts )
Tech 12 |  | 1 Report on refuse removal | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.The report was submitted. |  |  | 4 | 4 | 4 | 4
Tech 13 |  | Inception ( Housing Sector Plan ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
|  | ......................................... |  | .......................................
|  | Signed by Manager Strategic |  | Signed by Municipal Manager
|  | M A Sukazi |  | T V Mkhize
|  | Date................................ |  | Date...............................