## Sheet1
Mid-Year Assessment
|  | Organisationa | MID - YEAR | REPORT | 2016/17
Mr S.R.Ntuli
Ref | Strategic Objective | Target | Target Date | Actual Date | Target no | Actual no | Comments | Blockages | Corrective Measures | Dir | MM | Cons | Panel
KPA 1.Basic Service Delivery and Infrastructure Development
PLD 1 |  | 6 Facilitated Housing Forums | Mid -Year | 12/07/2016 | 6 | 4 | Partially Achieved.Housing Forum meetings |  |  | 3 | 3 | 3 | 3
|  |  |  | 23/08/2016 |  |  | were facilitated on the following
|  |  |  | 13/09/2016 |  |  | dates: 12/07/2016,23/08/2016 &
|  |  |  | 16/11/2016 |  |  | 13/09/2016 & 16/11/2016
PLD 2 |  | 1 Housing Consumer Education Workshop | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 3 |  | 24 Reports on Housing Projects | Mid -Year | 31/12/2016 | 24 | 24 | Achieved .The reports were |  |  | 4 | 4 | 4 | 4
submitted.
PLD 4 |  | Project Plannind and Progress Report on | Mid -Year | N/A | 1 | 0 | Not Achieved |  |  | 2 | 2 | 2 | 2
Middle Income Houses
KPA 2. Local Economic Development
PLD 5 |  | Inception (LED Strategy ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 6 |  | 2 Meetings (LED Forum ) | Mid -Year | N/A | 1 | 0 | Not Achieved |  |  | 2 | 2 | 2 | 2
PLD 7 |  | 2 Meeting (CTO ) | Mid -Year | 31/12/2016 | 2 | 1 | Partially Achieved.1 Meeting was held on |  |  | 3 | 3 | 3 | 3
19/10/2016.
PLD 8 |  | 1 LED Summit held | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 10 |  | 1 Signed agreement with investors | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 11 |  | Development Approval (Shopping Centre) | Mid -Year | N/A | 1 | 0 | Not Achieved |  |  | 2 | 2 | 2 | 2
PLD 11 |  | Project Inception ( Business Plan ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 12 |  | 1 Heritage Festival by 30/09/2016 | Mid -Year | 31/12/2016 | 1 | 1 | Achieved.Heritage Festival was organised on
01/10/2016.
PLD 13 |  | Exhibition in December 2016 ( Bundu | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
Market )
PLD 14 |  | 1 Training for art | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 15 |  | Renovation of Museum | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 16 |  | Project Inception ( Obivane Dam ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 18 |  | 1 Tourism awareness campaign | Mid -Year | 30/08/2016 | 1 | 1 | Achieved.Tourism Campaign |  |  | 4 | 4 | 4 | 4
workshop was held on 30/8/2016
PLD 19 |  | Draft Programme ( Agricultural Plan ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 20 |  | TORs & Appointment of SP ( Investment | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
Portfolio )
PLD 22 |  | 12 Participants ( Formalizing the informal | Mid -Year | N/A | 12 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
economy )
PLD 23 |  | 2 Trainings Facilitated | Mid -Year | 5-7/7/2016 | 2 | 1 | Partially Achieved.1 Meeting was convened. |  |  | 3 | 3 | 3 | 3
PLD 24 |  | 6 Businesses registered | Mid -Year | N/A | 6 | 0 | Not Achieved | The municipality has not signed |  | 2 | 2 | 2 | 2
MOU with agents.
PLD 25 |  | 24 Cooperatives Supported | Mid -Year | 05/07/2016 | 24 | 23 | Partially Achieved.23 Coorperatives were |  |  | 3 | 3 | 3 | 3
|  |  |  | to 07/07/2016 |  |  | supported through training
PLD 26 |  | 2 Meetings with informal traders | Mid -Year |  | 2
PLD 27 |  | Construction and Supervision | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
( SMMEs Development Park )
KPA 3.Good Governance,Community Participation and Ward Committee Systems
PLD 28 |  | 8 IDP Roadshows by 30/11/2016 | Mid -Year | 31/12/2016 | 8 | 8 | IDP Roadshows were conducted as planned. |  |  | 4 | 4 | 4 | 4
PLD 29 |  | 2 IDP Representative Forums | Mid -Year | 31/12/2016 | 2 | 1 | Partially Achieved.IDP Rep Forum was only |  |  | 3 | 3 | 3 | 3
convened 30/11/2016.
PLD 30 |  | 4 Ward Based Plans | Mid -Year | N/A | 4 | 0 | Not Achieved |  |  | 2 | 2 | 2 | 2
KPA 4. Cross Cutting Interventions
PLD 31 |  | 1 IDP Process Plan | Mid -Year | 14/11/2016 | 1 | 1 | Achieved.IDP Process Plan was |  |  | 4 | 4 | 4 | 4
approved by Council on 14/11/2016
PLD 32 |  | Conduct situational | Mid -Year | 30/09/2016 | 1 | 1 | Achieved.Situational analysis has been |  |  | 4 | 4 | 4 | 4
|  | analysis ( Credible IDP ) |  |  |  |  | conducted
PLD 32 ( A ) |  | Strategic Planning 31/12/2016 | Mid -Year | N/A | 1 | 1 | Not Achieved. |  | Planned for Q3 | 2 | 2 | 2 | 2
PLD 33 |  | Inception ( Capital Investment Plan ) | Mid -Year | N/A | 1 | 0 | Not Achieved | Budget Constraints | SDBIP to be reviewed | 2 | 2 | 2 | 2
PLD 34 |  | 1 Municipal Planning | Mid -Year | 31/12/2016 | 1 | 0 | Not Achieved. | The meeting between our MM | Planned for Q2 | 2 | 2 | 2 | 2
|  | Tribunal | [5 empty] | and other Municipalities in
Zululand did not materialize.
PLD 35 |  | Progress Report on ( Wall to Wall ) | Mid -Year | 30/09/2016 | 1 | 1 | Partially Achieved.The project has been |  |  | 3 | 3 | 3 | 3
advertised.
PLD 36 |  | 2 Reports on Land Use | Mid -Year | N/A | 1 | 1 | Not Achieved. |  |  | 2 | 2 | 2 | 2
Scheme
|  | ......................................... |  | .......................................
|  | Signed by Manager Strategic |  | Signed by Municipal Manager
|  | M A Sukazi |  | T V Mkhize
|  | Date................................ |  | Date...............................