## Sheet1
|  |  | EDUMBE ORGANIZATIONAL SDBIP 2017/2018 | [7 empty] | Year 2017/2018 |  |  | Q 1 |  | Q 2 |  | 1/2 Year |  | Q3 |  | Q4
|  | Strategic Objective | Strategy | Strategic Action/ Project | Key Performance Indicator (KPI) | Unit of Measure | Annual Target (Baseline) | Funding Source | Budget | Items | DEMAND | BASELINE | BACKLOG | Projected Target | Budget | Projected Target | Budget | Projected Target | Budget | Projected Target | Budget | Projected Target | Budget | Responsible Department | POE
KPA 1: MUNICIPAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
KPI 1 | Cor 1 | To improve institutional capacity through policy development and enforcement | Development, review and implemention of policies | Implement approved HR policies | Reviewed 13 HR Policies by 30 June 2018 | Number of HR Policies reviewed. | Reviewed 13 HR Policies by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Reviewed 13 HR Policies by 30 June 2018 | 0 | Corporate | 13 Policies & Council Resolution
KPI 2 | Cor 2 |  | Development, review and implemention of by-laws | Gazetting By-laws | 4 Gazetted Municipal By-laws | Number of Gazetted by-laws. | 4 Gazetted Municipal By-laws by 31 Dec 2017 | Rates- SOP | 55000 | Advertisement= R 10 000 Gazetting= R 45 000.00 | Some by-laws are not gazetted | Some by-laws are not gazetted | Some by-laws are not gazetted | 1 st Draft | 25000 | Final Drft | 30000 | Final Drft | 55000 | X | X | X | X | Corporate | By-laws & Council Resolution
KPI 3 | Cor 3 |  | Review and implementation of organogram | Implement organogram | Implemented approved organogram | Date of Adoption | Implemented organogram by 30 June 2018 | None | 0 | None | None | None | None | Implement Organogram | 0 | Implement Organogram | 0 | Implement Organogram | 0 | Implement Organogram | 0 | Implement Organogram | 0 | Corporate | Council Resolution
KPI 4 | Cor 4 |  | Review and implementation of WSP | Implement WSP | Implemented WSP | Date of Adoption | Implemented WSP by 31 April 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | Implemented WSP by 31 April 2018 | 0 | X | X | Corporate | Council Resolution
KPI 5 | Cor 5 |  | Review and implementation of WSP | Implement WSP | Implemented WSP | % of Implementation | 100% Implementation of WSP Budget by April 2018 | None | 0 | None | None | None | None | Implement | 0 | Implement | 0 | Implement | 0 | 100% Implementation of WSP Budget by April 2018 | 0 | Implement | 0 | Corporate | Council Resolution
KPI 6 | Cor 6 |  | Review and implementation of Employment Equity Plan (EEP) | Implement EEP | Submitted EEP to DoL | Date of submission | Submitted EEP to DoL by 31 January 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | Submitted EEP to DoL by 31 January 2018 | 0 | X | X | Corporate | Acknowledgement
KPI 7 | Cor 7 |  | OHS implementation | Purchase protective clothing | Implemented OHS Strategy | Date of Adoption | Protective clothing delivered by 31 September 2017 | Rates - BUS | 300000 | Protective Clothing = R2 90 000.00,Advertsement = R 10 000.00 | None | None | None | Protective clothing delivered by 31 September 2017 | 300000 | X | X | Protective clothing delivered by 31 September 2017 | 300000 | X | X | X | X | Corporate | Council Resolution
KPI 8 | Cor 8 |  |  | Servicing OHS equipment | Seviced OHS Equipments | Date of Adoption | Serviced OHS Equipments by 31 December 2017 | EQS | 60000 | Maintenance of fire extinguishers = R 50 000.00 & Sign boards = R 10 000.00 | Inadequate OHS Equipments | Inadequate OHS Equipments | Inadequate OHS Equipments | X | X | Appointment letter issued by 31 Dec 2017 | 60000 | Appointment letter issued by 31 Dec 2017 | 60000 | X | X | X | X | Corporate | Invoices
KIP 9 | Cor 9 |  |  | Medical screening | Conducted Medical Screening | Date of Adoption | Conducted Medical Screening by 31 March 2018 | Building & Structures Fees | 20000 | Medical Expenses | None | None | None | X | X | X | X | X | X | Appointment letter issued by 31 March 2018 | 20000 | X | X | Corporate | Invoices
KPI 10 | Cor 10 |  | Review and implemention of ICT Government Framework | Implement approved ICT policies | Impemented approved ICT policies | Date of Adoption | Implemented ICT policies by 30 June 2018 | None | 0 | None | None | None | None | X | X | Implement | 0 | Implement | 0 | Implement | 0 | Implement | 0 | Corporate | Council Resolution
KPI 11 | Cor 11 |  |  | Perform information backups | 12 Backups and Registers performed | Number of Backups and Register performed | 12 Backups and Registers performed by 30 June 2018 | None | 0 | None | None | None | None | 3 Backups and Registers performed | 0 | 3 Backups and Registers performed | 0 | 6 Backups and Registers performed | 0 | 3 Backups and Registers performed | 0 | 3 Backups and Registers performed | 0 | Corporate | Invoices
KPI 12 | Cor 12 |  |  | Perform information restores | 4 Restores and registers performed | Number of Restores and Register performed | 4 Restores and Register performed by 30 June 2018 | None | 0 | None | None | None | None | 1 Restore and Register performed | 0 | 1 Restore and Register performed | 0 | 2 Restores and Register performed | 0 | 1 Restore and Register performed | 0 | 1 Restore and Register performed | 0 | Corporate | Invoices
KPI 13 | Cor 13 |  |  | Review Logs | 12 Logs Reviews | Number of Reviews of Logs | 12 Logs Reviews by 30 June 2018 | None | 0 | None | None | None | None | 3 Logs Reviewed | 0 | 3 Logs Reviewed | 0 | 6 Logs Reviewed | 0 | 3 Logs Reviewed | 0 | 3 Logs Reviewed | 0 | Corporate | Council Resolution
KPI 14 | Cor 14 |  | Improving the ICT infrastructure | Implement Disaster Recovery Plan and Business Continuity Plan | Implemented DRP & BCP test | Date of Adoption | Implemented DRP & BCP test by 31 December 2017 | None | 0 | None | None | None | None | X | X | Implemented DRP & BCP test by 31 December 2017 | 0 | Implement | 0 | Implement | 0 | Implement | 0 | Corporate | Council Resolution
KPI 15 | Cor 15 |  |  | Appoint Service Provider to provide ICT Equipment | Purchased Hardware equipment s | Number of ICT Equipment | Purchased Hardware equipment 30 September 2017 | None | 150000 | Computers Purchases = R 150 000.00 | None | None | None | Purchased Hardware equipment 30 September 2017 | 150000 | X | X | Purchased Hardware equipment 30 September 2017 | 150000 | X | X | X | X | Corporate | Invoices
KPI 16 | Cor 16 |  |  |  | Purchased Software licenses | Number of Software licenses. | Purchased Software licenses by 31 December 2017 | None | 150000 | Software licenses = R 150 000.00 | None | None | None | X | X | Purchased Software licenses by 31 December 2017 | 150000 | Purchased Software licenses by 31 December 2017 | 150000 | X | X | X | X | Corporate | Invoices
KPI 17 | Cor 17 |  |  |  | Installed Antivirus software | Date of Agreement | Installed Antivirus software by 31 December 2017 | None | 25000 | Purchase Anti-virus. | None | None | None | X | X | Installed Antivirus software by 31 December 2017 | 25000 | Installed Antivirus software by 31 December 2017 | 25000 | X | X | X | X | Corporate | Invoices
KPI 18 | Mun 1 |  | Review and implementation of PMS | Review PMS Framework | Reviewed PMS framework | Date of Adoption | Reviewed PMS framework by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | Reviewed PMS framework | 0 | X | X | Executive | PMS Framework Document & Council Resolution
KPI 19 | Mun 2 |  |  | Review PMS Policy | Reviewed PMS Policy | Date of Adoption | Reviewed PMS policy by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | Reviewed PMS policy | 0 | X | X | Executive | PMS Policy Document & Council Resolution
KPI 20 | Mun 3 |  |  | Developed SDBIP & Organizational Scorecard | Developed SDBIP & Organizational Scorecard | Date of Adoption | Developed SDBIP & Organizational Scorecard by 30 June 2018 | Internal Funding | 5000 | Advetisemenet = R 5000.00 | None | None | None | X | X | X | X | X | X | X | X | Developed SDBIP & Organizational Scorecard by 30 June 2018 | 5000 | All Departments | Council Resolution
KPI 21 | Mun 4 |  |  | Performance agreement | Signed performance agreements of S56 | Number of signed performance agreement. | 4 Signed performance agreements by 31 August 2017 | Internal Funding | 5000 | Advetisemenet = R 5000.00 | None | None | None | 4 Signed performance agreements by 31 August 2017 | 8710 | X | X | 4 Signed performance agreements by 31 August 2017 | 5000 | X | X | X | X | Executive | 4 Signed performance agreements
KPI 22 | Mun 5 |  |  | Annual report | Completed Annual report | Date of Completion | Completed Annual report by 31 January 2018 | Internal Funding | 20848 | Advetisemenet = R 5000.00,Printing = R 15 000.00 & Courier =R 848 | None | None | None | X | X | X | X | X | X | Completed Annual report by 31 January 2018 | 20848 | X | X | Executive | Council Resolution
KPI 23 | Mun 6 |  |  | Annual performance report | Completed Annual performance report | Date of Completion | Completed Annual performance report by 31 August 2017 | Internal Funding | 5000 | Advertsement = R 5000.00 | None | None | None | Completed Annual performance report by 31 August 2017 | 7000 | X | X | Completed Annual performance report by 31 August 2017 | 5000 | X | X | X | X | Executive | Council Resolution
KPI 24 | Mun 7 |  |  | Mid-year Assessment report | Conducted mid-year assessment | Date of Completion | Conducted mid-year assessment by 31 January 2018 | Internal Funding | 5424 | Advetisement =R 5000.00 & Courier =R 424.00 | None | None | None | X | X | X | X | X | X | Conducted mid-year assessment by 31 January 2018 | 5424 | X | X | Executive | Council Resolution
KPI 25 | Mun 8 |  |  | B2B | 16 Compiled B2B reports | Number of reports compiled. | 16 Compiled B2B reports by 30 June 2018 | None | 0 | None | None | None | None | 4 B2B Reports | 0 | 4 B2B Reports | 0 | 8 B2B Reports | 0 | 4 B2B Reports | 0 | 4 B2B Reports | 0 | Executive | Reports
KPI 26 | Mun 9 |  |  | Oversight Report | Completed Oversight Report | Date of Adoption | Completed Oversight Report by 31 March 2018 | Internal Funding | 5636 | Advetisement =R 5000.00 & Courier = R 636.00 | None | None | None | X | X | X | X | X | X | Completed Oversight Report by 31 March 2018 | 5636 | X | X | Executive | Council Resolution
KPI 27 | Mun 10 | To improve municipal corporate image | Review and Implementation of Communication Strategy | Provide a reviewed communication strategy | Reviewed Communication Strategy | Date of Adoption | Reviewed Communication Strategy by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Reviewed Communication Strategy by 30 June 2018 | 0 | Executive | Council Resolution
KPI 28 | Mun 11 |  |  | Establish a communications policy | Approved Communications policy | Date of Adoption | Approved Communication policy by 30 June 2017 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Approved Communication policy by 30 June 2017 | 0 | Executive | Council Resolution
KPI 29 | Cor 18 |  |  | Maintenance of website | Maintained and updated municipal website | Date of mantanance | Maintained and updated municipal website by 30 June 2018 | Internal Funding | 140000 | Advertisement = R 5000.00 & Service Provider R 135 000.00 | None | None | None | 1 Report by 30 September 2017 | 30000 | 1 Report by 31 December 2017 | 30000 | 1 Report by 31 December 2017 | 60000 | 1 Report by 31 March 2018 | 50000 | 1 Report by 30 June 2018 | 30000 | Corporate | Quarterly Reports
KPI 30 | Mun 12 | To ensure effective and efficient Municipal Administration and Communication. | Development of Municipal branding | Newsletter | 4 Sets of Supplied & Delivered Newsletter | Number of newspaper publications | 4 Sets of Supplied & Delivered Newsletter by 30 June 2018 | EQS | 50000 | None | None | None | None | 1 Set of Supplied and Delivered Newsletter | 25000 | X | X | 1 Set of Supplied and Delivered Newsletter | 25000 | 1 Set of Supplied and Delivered Newsletter | 25000 | X | X | Executive | News Paper & Delivery note
KPA 2: BASIC SERVICE DELIVERY & INFRASTRUCTURE DEVELOPMENT
KPI 31 | Tech 1 | To ensure provision of basic services in a fair, equitable and sustainable manner | Provision of Free Basic Services | To provide free basic services to all indigent households with available resources | 2% of households provided with free basic services | % of households provided with free basi services. | 2% of households provided with free basic services by 30 June 2017 | Equitable Share | 1471680 | Eskom Payment = R 1 471 680 | None | None | None | X | X | X | X | X | X | X | X | 2% of households provided with free basic services by 30 June 2017 | 1471680 | Infrastructure | Reports
KPI 32 | Tech 2 |  | Improvement of Access to Roads | Regravelling of Tholakele Access Road | Completed Tholakele Access Road | Date of Completion | Completed Tholakele Access Road ( Gravel Road )(Kwavova access from D 1875 ) By 30 June 2018 | MIG | 2000000 | Contractor = R 1 720 000.00 & Professional fees = R280 000.00 | None | None | None | Site Establishment | 50000 | Commencement of work | 50000 | Commencement of work | 100000 | 50 % of Completed work | 700000 | Projecte Completion | 1200000 | Infrastructure | Completion Certificate
KPI 33 | Tech 3 |  |  | Izingudeli Pedistrian Bridge | Completed Izingudeni Pedestrian Bridge | Date of Completion | Completed Izingudeni Pedestrian Bridge By 30 June 2018 | MIG | 3500000 | Contractor = R 3 010 000.00 & Professional fees = R 490 000.00 | None | None | None | Site Establishment | 500000 | Commencement of work | 500000 | Commencement of work | 1000000 | 50 % of Completed work | 200000 | Projecte Completion | 2300000 | Infrastructure | Completion Certificate
KPI 34 | Tech 4 |  |  | Patching of Potholes | 15 000 sq/m of potholes patched | Number of sm/m patched | 15 000 sq/m of potholes patched By 30 June 2018 | EQS | 1000000 | Advertisement = R10 000.00 & Purchase of Patching material = R 990 000.00 | None | None | None | 3750 sq/m of potholes patched | 250000 | 3750 sq/m of potholes patched | 250000 | 7500 sq/m of potholes patched | 500000 | 3750 sq/m of potholes patched | 250000 | 3750 sq/m of potholes patched | 250000 | Infrastructure | Reports
KPI 35 | Tech 5 |  | Improvement of Access to Electricity | Obivane/Nkonkotho Electrification | Completed Obivane/Nkonkotho Electrification | Date of Completion | Completed Obivane/Nkonkotho Electrification By 30 June 2018 | INEP | 7000000 | Contractor = R 7 000 000.00 | None | None | None | Site Establishment | 500000 | Commencement of work | 2500000 | Commencement of work | 3000000 | 50% of work completed | 3000000 | Project Completion | 1000000 | Infrastructure | Completion Certificate
KPI 36 | Tech 6 |  |  | Bulk Infrastructure Upgrade | CompletedBulk infrastructure Upgrade | Date of Completion | Completed Bulk infrastructure Upgrade By 30 June 2018 | INEP | 6000000 | Contractor = R 6 000 000.00 | Old Infrastructure | Old Infrastructure | Old Infrastructure | Site Establishment | 500000 | Commencement of work | 2500000 | Commencement of work | 3000000 | 50% of work completed | 2000000 | Project Completion | 1000000 | Infrastructure | Completion Certificate
KPI 37 | Tech 7 |  |  | Enkembeni Electrification Phase 4 | Completed Enkembeni Electrification Phase 4 | Date of Completion | Completed Enkembeni Electrification Phase 4 By 30 June 2018 | INEP | 7000000 | Contractor = R 7 000 000.00 | None | None | None | Site Establishment | 500000 | Commencement of work | 2500000 | Commencement of work | 3000000 | 50% of work completed | 3000000 | Project Completion | 1000000 | Infrastructure | Completion Certificate
KPI 38 | Tech 8 |  |  | Ward 1 Electrification | Completed Ward 1 Electrification | Date of Completion | Completed( Mahloni ) Ward 1 Electrification By 30 June 2018 | INEP | 4000000 | Contractor = R 4 000 000.00 | None | None | None | Site Establishment | 1000000 | Commencement of work | 1000000 | Commencement of work | 2000000 | 50% of work completed | 1000000 | Project Completion | 1000000 | Infrastructure | Completion Certificate
KPI 39 | Tech 9 |  |  | Ensuring Continuous Maintenance of Electrical Infrastructure | Fully maintained Electrical Infrastructure | Level of maintanance | Fully maintained Electrical Infrastructure By 30 June 2018 | EQS | 1000000 | Purchasing material = R 1 000 000.00 | None | None | None | Site Establishment | 50000 | Commencement of work | 50000 | Commencement of work | 100000 | 50 % of Completed work | 700000 | Projecte Completion | 200000 | Infrastructure | Reports
KPI 40 | Tech 10 |  | Provision of Refuse Removal | residential and commercial waste collection | number of households & businesses with access to waste removal | % of households & Businesses with access to waste removal. | 5% of households & businesses with access to waste removal by 30 June 2018 | Internal Funding | 250000 | Fencing of Dump site = R 100 000.00, Purchase of plastic bags & Tools = R 50 000.00 | None | None | None | X | X | X | X | X | X | X | X | 5% of households & businesses with access to awste removal by 30 June 2018 | 250000 | Infrastructure | Reports
KPI 41 | PLD 2 |  | Improvement of access to sustainable human settlement | Facilitate Housing Forums | Housing Forums held | Number of housing forums | 10 Housing Forums held by 30 June 2018 | None | 0 | None | None | None | None | 3 Housing Forums | 0 | 3 Housing Forums | 0 | 6 Housing Forums | 0 | 2 Housing Forums | 0 | 2 Housing Forums | 0 | Planning | Attendance Register
KPI 42 | PLD 3 |  |  | Conducting housing consumer education workshops | 4 Consumer Education Workshops conducted | Number of Consumer Education Conducted. | 4 Consumer Education Workshops conducted by 30 June 2018 | None | 0 | None | None | None | None | 1 Consumer Education Workshop | 0 | 1 Consumer Education Workshop | 0 | 2 Consumer Education Workshops | 0 | 1 Consumer Education Workshop | 0 | 1 Consumer Education Workshop | 0 | Planning | Attendance Register
KPI 43 | Tech 11 |  | Improvement of Access to public facilities and amenities | Fencing of eDumbe Cemetry | Fully fenced eDumbe Cemetery | Date of Completion | Fully fenced eDumbe Cemetery by 30 June 2018 | MIG | 2000000 | Contractor = R 1 720 000.00 & Professional fees = R280 000.00 | None | None | None | Site Establishment | R100 000,00 | Commencement of work | 500000 | Commencement of work | 600000 | 50% of work completed | 1000000 | Project Completion | 400000 | Infrastructure | Completion Certificate
KPI 44 | Tech 12 |  |  | Construction of Kanyekanye Hall | Completed Kanyekanye Hall | Date of Completion | Completed Kanyekanye Hall by 30 June 2018 | MIG | 3000000 | Contractor = R 2 580 000.00 & Professional fees = R 420 000 00 | None | None | None | Site Establishment | 500000 | Commencement of work | 500000 | Commencement of work | 1000000 | 50% of work completed | 1000000 | Project Completion | 1000000 | Infrastructure | Completion Certificate
KPI 45 | Tech 13 |  | Provision of Access to Sportfacilities | Construction of Mangosuthu Combi Court | Completed Mangosuthu Combi Court | Date of Completion | Completed Mangosuthu Combi Court by 30 June 2018 | MIG | 2000000 | Contractor = R 1 720 000.00 & Professional fees = R280 000.00 | None | None | None | Site Establishment | R100 000,00 | Commencement of work | 500000 | Commencement of work | 600000 | 50% of work completed | 1000000 | Project Completion | 400000 | Infrastructure | Completion Certificate
KPI 46 | Tech 14 |  |  | Upgrading of Impucuko Sportfield | Completed Impucuko Sportfield | Date of Completion | Completed Impucuko Sportfield by 30 June 2018 | MIG | 2964800 | Contractor = R 2 549 780.00 & Professional fees = R 415 072.00 | None | None | None | Site Establishment | 164800 | Commencement of work | 800000 | Commencement of work | 964800 | 50% of work completed | 1000000 | Project Completion | 1000000 | Infrastructure | Completion Certificate
KPI 47 | Tech 15 |  |  | Construction of Ophuzane Combi Court | Completed Ophuzane Combi Court | Date of Completion | Completed Ophuzane Combi Court by 30 June 2018 | MIG | 2000000 | Contractor = R 1 720 000.00 & Professional fees = R280 000.00 | None | None | None | Site Establishment | R100 000,00 | Commencement of work | 500000 | Commencement of work | 600000 | 50% of work completed | 1000000 | Project Completion | 400000 | Infrastructure | Completion Certificate
KPI 48 | Tech 16 |  | Ensuring Provision and Maintenance of Municipal Buildings | Maintenance of Municipal Buildings | Fully maintained municipal buildings | Date of Completion | Fully maintained municipal buildings by 30 June 2018 | EQS | 200000 | Purchase of material = R 2 000 000.00 | None | None | None | Fully maintained Municipal Buildings | R100 000,00 | Fully maintained Municipal Buildings | 500000 | Fully maintained Municipal Buildings | 600000 | Fully maintained Municipal Buildings | 1000000 | Fully maintained Municipal Buildings | 400000 | Infrastructure | Completion Certificate
KPA 3: LOCAL ECONOMIC DEVELOPMENT AND SOCIAL DEVELOPMENT
KPI 49 | Tech 17 | To create conducive environment for sustainable economic growth and development | Job creation and promotion of employment opportunities | Implement EPWP Programme | 120 Work Opportunities created through EPWP Programme | Number of job opportunities created | 120 Work Opportunities created through EPWP Programme by 30 June 2018 | EPWP Grant | 1389000 | Stiepend for workers =R 960 000.00 & Purchase of material = R 429 000.00 | None | None | None | 30 Work Opportunities | 347250 | 30 Work Opportunities | 347250 | 60 Work Opportunities | 964500 | 30 Work Opportunities | 347250 | 30 Work Opportunities | 347250 | Infrastructure | Appointment letters
KPI 50 | Tech 18 |  |  | Create job opportunities through Capital projects | 30 Job opportunities created through each MIG Project | Number of job opportunities created | 30 Job opportunities created through each MIG Project by 30 June 2018 | MIG | 0 | None | None | None | None | 8 Job Opportunities Created | 0 | 8 Job Opportunities Created | 0 | 16 Job Opportunities Created | 0 | 8 Job Opportunities Created | 0 | 6 Job Opportunities Created | 0 | Infrastructure | Appointment letters
KPI 51 | Com 1 |  |  | Coordinate the Implementation of CWP Programme | 4 Provincial CWP meetings attended | Number of CWP meetings attended | 4 Provincial CWP meetings attended by 30 June 2018 | None | 0 | None | None | None | None | 1 Meeting Attended | 0 | 1 Meeting Attended | 0 | 2 Meetings Attended | 0 | 1 Meeting Attended | 0 | 1 Meeting Attended | 0 | Community | Attendance Register
KPI 52 | Com 2 |  |  |  | 6 CWP Local Reference Committee Meetings held | Number of CWP Local Reference Committee Meetings held | 6 CWP Local Reference Committee Meetings held by 30 June 2018 | None | 0 | None | None | None | None | 2 CWP Local Reference Meeting | 0 | X | X | 2 CWP Local Reference Meeting | 0 | 2 CWP Local Reference Meeting | 0 | 2 CWP Local Reference Meeting | 0 | Community | Attendance Register
KPI 53 | PLD 1 |  |  | Create job opportunities through LED Projects | 10 Jobs created through LED Projects | Number of job opportunities created | 10 Jobs created through LED Projects by 30 June 2018 | None | 0 | None | None | None | None | 2 Jobs created | 0 | 4 Jobs created | 0 | 6 Jobs created | 0 | 2 Jobs created | 0 | 2 Jobs created | 0 | Planning | Appointment letters/Attendance register
KPI 54 | PLD 2 |  | Development and Implementation of LED Strategy | Formulate LED Strategy | Approved LED Strategy | Date of approval | Reviewed LED Strategy by 30 June 2018 | None | 0 | None | None | None | None | 1st Draft of the Document | 0 | 2 nd Draft of the Document | 0 | 2 nd Draft of the Document | 0 | Final Document | 0 | Reviewed LED Strategy | 0 | Planning | LED Strategy & Council Resolution
KPI 55 | PLD 3 |  | Development of Strategic Alliance and Partnership for economic growth and Development | Revive and support LED Forum | Revived LED Forum | Number of Forums | 4 LED Forum by 30 June 2018 | None | 0 | None | None | None | None | 1 LED forum | 0 | 1 LED forum | 0 | 2 LED forums | 0 | 1 LED forum | 0 | 1 LED forum | 0 | Planning | Attendance Register
KPI 56 | PLD 4 |  |  | Establish and support CTO | Established CTO | Date of Adoption | Established CTO by 30 September 2017 | None | 0 | None | None | None | None | Established CTO by 30 September 2017 | 0 | X | X | X | X | X | X | X | X | Planning | Council Resolution
KPI 57 | PLD 5 |  |  | Hosting of the LED summit | One summit held | Number of summits | One summit held by 30 June 2018 | None | 0 | None | None | None | None | X |  | X |  | X |  | X |  | One summit held by 30 June 2018 | 0 | Planning | Attendance Register
KPI 58 | PLD 6 |  |  | Signing of agreements with development Agencies | Signed agreements with development Agencies | Date of Agreement | 1 Signed agreement with development Agencies by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | 1 Signed agreement with development Agencies by 30 June 2018 | 0 | Planning | Agreement & Council Resolution
KPI 59 | PLD 7 |  | Facilitation and Implementation of LED Anchor Projects | Facilitate the development of a Shopping Centre | Signed agreements with investors | Date of Agreement | 2 Signed agreements with investors by 31 December 2017 | None | 0 | None | None | None | None | X | X | 2 Signed agreements with investors by 31 December 2017 | 0 | Signed agreements with investors by 31 December 2017 | 0 | X | X | X | X | Planning | Council Resolution
KPI 60 | PLD 8 |  |  |  | Approved documents for the development of a Shopping Centre | Date of approval | Approved documents for the development of a Shopping Centre by 31 Dec 2017 | None | 0 | None | None | None | None | X | X | Approved documents for the development of a Shopping Centre by 31 Dec 2017 | 0 | Approved documents for the development of a Shopping Centre by 31 Dec 2017 | 0 | X | X | X | X | Planning | Council Resolution
KPI 61 | PLD 9 |  | Marketing and showcasing of economic and tourism development | Formulate Tourim Strategy | approved Tourism Strategy | Date of Adoption | Approved Tourism strategy by 30 June 2018 | None | 0 | None | None | None | None | 1st Draft of the Document | 0 | 2 nd Draft of the Document | 0 | 2 nd Draft of the Document | 0 | Final Document | 0 | Approved Tourism Strategy | 0 | Planning | Tourism Strategy & Council Resolution
KPI 62 | PLD 10 |  | Formalizing the Informal Economy | Create Business incubation programme | Number of Trainings Facilitated | Number of Trainings Facilitated | 4 Facilitated Trainings on busines incubation programme by 30 June 2018 | None | 0 | None | None | None | None | 1 Training Facilitated | 0 | 1 Training Facilitated | 0 | 2 Trainings Facilitated | 0 | 1 Training Facilitated | 0 | 1 Training Facilitated | 0 | Planning | Attendance Register
KPI 63 | PLD 11 |  |  | Informal Traders | 4 meetings held with Informal Traders Association | Number of Meetings held | 4 meetings held with Informal Traders Association by 30 June 2018 | None | 0 | None | None | None | None | 1 Meeting | 0 | 1 Meeting | 0 | 2 Meetings | 0 | 1 Meeting | 0 | 1 Meeting | 0 | Planning | Attendance Register
KPA 4: GOOD GOVERNANCE, COMMUNITY PARTICIPATION & WARD COMMITTEE SYSTEM
KPI 64 | Com 3 | To promote effective community participation | Strengthening the functionality of Ward Committees | Conducting and attending ward committee meetings | 12 Sittings of Ward Committees | Number of sittings of Committee Meetings | 96 Sitting of Ward Committees Meetings by 30 June 2018 | EQS | 576000 | Out-of-Pocket Expense for Ward Committee = R 576 000.00 | None | None | None | 24 Sittings of Ward Committees | 144000 | 24 Sittings of Ward Committees | 144000 | 48 Sittings of Ward Committees | 288000 | 24 Sittings of Ward Committees | 144000 | 24 Sittings of Ward Committees | 144000 | Community | Attendance Register
KPI 65 | Mun 13 |  | Review and Implemention of Community Participation Framework | Review and implement Community Participation Framework | Reviewed and implemented Community Participation Framework | Date of Adoption | Reviewed and implemented Community Participation Framework 30 June 2018 | None | R 0 00 | None | No Community Participation Framework | No Community Participation Framework | No Community Participation Framework | 1st Draft of the Document | R 0 00 | Second Draft Of the Document | R 0 00 | Second Draft Of the Document | R 0 00 | Final Document | R 0 00 | X | R 0 00 | Executive | Community Participation Framework & Council Resolution
KPI 66 | PLD 12 |  |  | Facilitate IDP Consultative Meeting | 16 IDP Road-shows held | Number of IDP consultatives | 16 IDP Road-shows held by 30 June 2018 | EQS | 50000 | Advertisement = R 5000.00 & Refreshment = R 25 000.00 | None | None | None | X | 0 | 16 IDP Road-Shows | 50000 | 16 IDP Road-Shows | 50000 | X | X | X | X | Planning | Attendance Register
KPI 67 | PLD 13 |  |  | Facilitate IDP Representative Forums | 2 IDP Representative Forums held | Number of IDP Representative Forums held | 2 IDP Representative Forums held by 30 June 2018 | EQS | 25000 | Refreshment = R 25 000.00 | None | None | None | X |  | 1 IDP Rep Forum | 15000 | 1 IDP Rep Forum | 25000 | 1 IDP Rep Forum | 10000 | X | X | Planning | Attendance Register
KPI 68 | Com 4 |  | Implemention of Operation Sukuma Sakhe | Functionality of war rooms | 12 sittings of war rooms | Number of sittings of War Rooms | 12 sittings of war rooms by 30 June 2018 | None | 0 | None | None | None | None | 1 Sitting of war room | 0 | 1 Sitting of war room | 0 | 2 Sittings of war rooms | 0 | 1 Sitting of war room | 0 | 1 Sitting of war room | 0 | Community | Attendance Register
KPI 69 | PLD 14 |  | Development and Implemention of Ward Based Plans | Facilitate Ward based plans | 8 Wards Based Plan Facilitated by 30 June 2018 | Number of Ward Based Plan | 8 Wards Based Plan Facilitated by 30 June 2018 | None | R 0 00 | None | None | None | None | 2 Ward Based Plans | R 0 00 | 2 Ward Based Plans | R 0 00 | 4 Ward Based Plans | R 0 00 | 2 Ward Based Plans | R 0 00 | 2 Ward Based Plans | R 0 00 | Planning | Attendance Register
KPI 70 | Com 5 | To promote cohesive social development | Implementation of Special Programmes | Implementation of Special Programmes | 4 Implemented Special Programmes | Number of Implemented Special Programmes | 4 Implemented Special Programmes by 30 June 2018 | Internal Funding | 100000 | Sound System = R 6000.00 & Transport = R 94 000.00 | None | None | None | 2 Implemented Special Programmes | 25000 | 2 Implemented Special Programmes | 25000 | 4 Implemented Special Programmes | 50000 | 2 Implemented Special Programmes | 25000 | 2 Implemented Special Programmes | 25000 | Community | Attendance Register
KPI 71 | Com 6 |  | Establishment of Functional Forums | Establishment of Youth Council | 1 Youth Council elected | Number of Youth Councils elected | 1 Youth Council elected by 30 September 2017 | EQS | R 0 00 | None | None | None | None | 1 Youth Council elected | R 0 00 | X | X | 1 Youth Council elected | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 72 | Com 7 |  |  | Establishment of Sport Council | 1 Sport Council elected | Number of Sport Councils elected | 1 Sport Council elected by 30 September 2017 | EQS | R 0 00 | None | None | None | None | 1 Sport Council elected | R 0 00 | X | X | 1 Sport Council elected | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 73 | Com 8 |  |  | Establishment of Women's Forum | 1 Women's Forum established | Number of established Forums | 1 Women's Forum established by 30 September 2017 | EQS | R 0 00 | None | None | None | None | 1 Women's Forum established | R 0 00 | X | X | 1 Women's Forum established | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 74 | Com 9 |  |  | Establishment of Men's Forum | 1 Men's Forum established | Number of established Forums | 1 Men's Forum established by 30 September 2017 | EQS | R 0 00 | None | None | None | None | 1 Men's Forum established | R 0 00 | X | X | 1 Men's Forum established | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 75 | Com 10 |  |  | Establishment of Eldery Forum | 1 Eldery Forum established | Number of established Forums | 1 Eldery Forum established by 30 June 2018 | EQS | R 0 00 | None | None | None | None | 1 Eldery Forum established | R 0 00 | X | X | 1 Eldery Forum established | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 76 | Com 11 |  |  | Establishment of Disability Forum | 1 Disability Forum established | Number of established Forums | 1 Disability Forum established by 30 September 2017 | EQS | R 0 00 | None | None | None | None | 1 Disability Forum established | R 0 00 | X | X | 1 Disability Forum established | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 77 | Com 12 |  |  | Establishment of HIV/Aids Forum | 1 HIV/Aids Forum established | Date of Adoption | 1 HIV/Aids Forum established by 30 September 2017 | None | 0 | None | None | None | None | 1 HIV/Aids Forum established | 0 | X | X | 1 HIV/Aids Forum established | R 0 00 | X | X | X | X | Community | Council Resolution
KPI 78 | Com 13 |  | Sports Development | Hosting of indigenous games | Hosted indigenous games | Number of Games | 3 Hosted indigenous games by 30 June 2018 | public facilities | R 20 000, 00 | Transport = R 5000.00 & Sound system = R 15 000.00 | None | None | None | X | X | 1 Indigenous game | 6666.7 | 1 Indigenous game | 6666.7 | 1 Indigenous game | 6666.7 | 1 Indigenous game | 6666.7 | Community | Attendance Register
KPI 79 | Com 14 |  |  | Hosting of Mayoral Games | Hosted Mayoral Games | Number of Games | 2Hosted Mayoral Games by 30 June 2018 | public facilities | R 300 000, 00 | Transport = R 100 000.00 & Awards = R 200 000.00 | None | None | None | X | X | 1 Mayoral Game | 150000 | 1 Mayoral Game | 150000 | 1 Mayoral Game | 150000 | X | X | Community | Attendance Register
KPI 80 | Com 15 |  |  | Hosting of Golden games | Hosted Golden games | Number of Games | 3 Hosted Golden games by 30 June 2018 | public facilities | R 14 400, 00 | Transport = R 5 400.00 & Awards = R 9000.00 | None | None | None | 1 Golden Game | 4800 | 1 Golden Game | 4800 | 2 Golden Games | 9600 | 1 Golden Game | 4800 | X | X | Community | Attendance Register
KPI 81 | Com 16 |  | HIV-Aids Intervention | Conducting HIV/AIDS Awareness Campaign | 4 Conducted HIV/AIDS Awareness Campaign | Number of HIV/AIDS Awareness Campaigns Conducted. | 4 Conducted HIV/AIDS Awareness Campaign by 30 June 2018 | EQS | R 50 000, 00 | Transport = R 46 000.00 & Sound System = R 4000.00 | None | None | None | 1 HIV/AID Awareness Campagn | 12500 | 1 HIV/AID Awareness Campagn | 12500 | 2 HIV/AID Awareness Campagns | 25000 | 1 HIV/AID Awareness Campagn | 12500 | 1 HIV/AID Awareness Campagn | 12500 | Community | Attendance Register
KPI 82 | Cor 19 |  | Facilitating the functioning of Council and Council Committees | Facilitating Sittings of Council Meeting | 04 Council Meeting Sittings facilitated | Number of Council Meetings | 04 Council Meeting Sittings facilitated by 30 June 2018 | None | 0 | None | None | None | None | 1 Council Meeting | 0 | 1 Council Meeting | 0 | 2 Council Meetings | 0 | 1 Council Meeting | 0 | 1 Council Meeting | 0 | Corporate | Attendance Register
KPI 83 | Cor 20 |  |  | Facilitating Sittings of Executive Committee | 12 Executive Committees Sittings facilitated | Number of Executive Committees Sittings facilitated | 12 Executive Committees Sittings facilitated by 30 June 2018 | None | 0 | None | None | None | None | 3 Executive Committee Meetings | 0 | 3 Executive Committee Meetings | 0 | 6 Executive Committee Meetings | 0 | 3 Executive Committee Meetings | 0 | 3 Executive Committee Meetings | 0 | Corporate | Attendance Register
KPI 84 | Cor 21 |  |  | Facilitating Sittings of Finance and Planning and Development portfolio committee meetings | 12 Finance and Planning and Development portfolio committee meetings facilitated | Number of Finance & Planning Portfolio Meetings | 12 Finance and Planning and Development portfolio committee meetings facilitated by 30 June 2018 | None | 0 | None | None | None | None | 3 Finance & Planning Portfolio Meetings | 0 | 3 Finance & Planning Portfolio Meetings | 0 | 6 Finance & Planning Portfolio Meetings | 0 | 3 Finance & Planning Portfolio Meetings | 0 | 3 Finance & Planning Portfolio Meetings | 0 | Corporate | Attendance Register
KPI 85 | Cor 22 |  |  | Facilitating Sittings of Technical Services Portfolio Committee meetings | 12 Technical Services Portfolio Committee meetings facilitated | Number of Technical Portfolio Meetings | 12 Technical Services Portfolio Committee meetings facilitated by 30 June 2018 | None | 0 | None | None | None | None | 3 Technical Portfolio Meetings | 0 | 3 Technical Portfolio Meetings | 0 | 6 Technical Portfolio Meetings | 0 | 3 Technical Portfolio Meetings | 0 | 3 Technical Portfolio Meetings | 0 | Corporate | Attendance Register
KPI 86 | Cor 23 |  |  | Facilitating Sittings of Community and Corporate Services Portfolio Committees | 12 Community and Corporate Services Portfolio Committees facilitate | Number of Community & Corporate Portfolio Committee Meetings | 12 Community and Corporate Services Portfolio Committees facilitate by 30 June 2018 | None | 0 | None | None | None | None | 3 Community & Corporate Services Portfolio Meetings | 0 | 3 Community & Corporate Services Portfolio Meetings | 0 | 6 Community & Corporate Services Portfolio Meetings | 0 | 3 Community & Corporate Services Portfolio Meetings | 0 | 3 Community & Corporate Services Portfolio Meetings | 0 | Corporate | Attendance Register
KPI 87 | Mun 14 |  |  | Facilitating Sittings of Municipal Public Accounts Committee (MPAC) | 04 Municipal Public Accounts Committee (MPAC)Meetings facilitated | Number of MPAC Facilitated Meetings | 04 Municipal Public Accounts Committee (MPAC)Meetings facilitated by 30 June 2018 | None | 0 | None | None | None | None | 1 MPAC Meeting | 0 | 1 MPAC Meeting | 0 | 2 MPAC Meetings | 0 | 1 MPAC Meeting | 0 | 1 MPAC Meeting | 0 | Corporate | Attendance Register
KPI 88 | Cor 24 |  |  | Facilitating Sittings of Audit Committee | 04 Audit Committee Meetings facilitated | Number of Audit Committee Meetings | 04 Audit Committee Meetings facilitated by 30 June 2018 | EQS | R 210 000, 00 | Advertisements = R 10 000.00, Audi sittings = R 194 750.00 & Courier Charges = R 5 250 | None | None | None | 1 Audit Committee Meeting | 52500 | 1 Audit Committee Meeting | 52500 | 2 Audit Committee Meetings | R 1 05 000 .00 | 1 Audit Committee Meeting | 52500 | 1 Audit Committee Meeting | 52500 | Executive | Attendance Register
KPI 89 | PLD 15 |  | Batho-Pele Principles | Batho-Pele Principles | Engangements with sector departments to do customer care survey | Conducted Costomer survey | Conducted Costomer survey by 30 June 2018 | None | 0 | None | None | None | None | 1 Report by 30 September 2017 | 0 | 1 Report by 31 December 2017 | 0 | 1 Report by 31 December 2017 | 0 | 1 Report by 31 March 2018 | 0 | 1 Report by 30 June 2018 | 0 | Corporate | Reports
KPI 90 | Com 17 |  | Promotion of arts, culture and heritage | Co-ordination of Umkhosi Womhlanga | 1 Umkhosi Womhlanga Coordinated | Number of Festivals hosted | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | EQS | 100000 | Transport = R R70 000.00 , Promotional Items = R 25 000.00 & Accommodation = R 5000.00 | None | None | None | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | 160000 | X | X | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | 160000 | X | X | X | X | Community | Attendance
KPA 5: MUNICIPAL FINANCIAL VIABILITY & MANAGEMENT
KPI 91 | Mun 15 | To improve municipal financial viability and sound financial management | To improve municipal audit opinion,council oversight and accountability | Establish Risk-based Internal audit plan | Approved Risk-based internal audit plan | Date of Adoption | Approved Risk-based internal audit plan by 30 September 2017 | Internal Funding | 1490470 | Internal Auditors = R 1 490 470.00 | None | None | None | Approved Risk-based internal audit plan by 30 September 2017 | 1490470 | X | X | Approved Risk-based internal audit plan by 30 September 2017 | 1490470 | X | X | X | X | Executive | Risk Based Assessment Plan & Council Resolution
KPI 92 | Mun 16 |  |  | Review of AC and IA Charters | Reviewed AC and IA Charters | Date of Adoption | Reviewed AC & IA Charters by 30 September 2017 | None | 0 | None | None | None | None | Reviewed AC & IA Charters by 30 September 2017 | 0 | X | X | Reviewed AC & IA Charters by 30 September 2017 | 0 | X | X | X | X | Executive | Council Resolution
KPI 93 | Mun 17 |  |  | Establish Internal Audit Methodology | Approved Internal Audit Methodology | Date of Adoption | Approved Internal Audit Methodology by 30 September 2017 | None | 0 | None | None | None | None | Approved Internal Audit Methodology by 30 September 2017 | 0 | X | X | Approved Internal Audit Methodology by 30 September 2017 | 0 | X | X | X | X | Executive | Council Resolution
KPI 94 | Mun 18 |  |  | Conduct Audit Committee Assessments | Conducted Audit Committee Assessments | Date of Assessment | Conduct Audit Committee Assessments by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Conduct Audit Committee Assessments by 30 June 2018 | 0 | Executive | Council Resolution
KPI 95 | Mun 19 |  |  | Review Risk Management Framework | Reviewed Risk Management Framework | Date of Adoption | Reviewed Risk Management Framework by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Reviewed Risk Management Framework by 30 June 2018 | 0 | Executive | Council Resolution
KPI 96 | Mun 20 |  |  | Review Risk Management Policy | Reviewed Risk Management Policy | Date of Adoption | Reviewed Risk Management Policy by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Reviewed Risk Management Policy by 30 June 2018 | 0 | Executive | Council Resolution
KPI 97 | Mun 21 |  |  | Conducted Risk Assessment | Conducted Risk Assessment | Date of Assessment | Conducted Risk Assessment by 31 August 2017 | None | 0 | None | None | None | None | Conducted Risk Assessment by 31 August 2017 | 0 | X | X | Conducted Risk Assessment by 31 August 2017 | 0 | X | X | X | X | Executive | Council Resolution
KPI 98 | Mun 22 |  |  | Functional Risk Managment Committee | 4 Risk Management Committee Meetings | Number of Meetings | 4 Conducted Risk Committee Meetings by 30 June 2018 | Internal Funding | 0 | None | None | None | None | 1 Risk Committee Meeting | 21367.5 | 1 Risk Committee Meeting | 21367.5 | 2 Risk Committee Meetings | 42735 | 1 Risk Committee Meeting | 21367.5 | 1 Risk Committee Meeting | 21367.5 | Executive | Attendance Register
KPI 99 | Mun 23 |  | Fraud and Corruption Prevention | Reviewed Fraud Prevention Plan | Reviewed Fraud Prevention Plan | Date of Adoption | Reviewed Fraud Prevention Plan by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Reviewed Fraud Prevention Plan by 30 June 2018 | 0 | Executive | Council Resolution
KPI 100 | Mun 24 |  | Development and implemention of Audit Action Plan | Developed and 100% Implementation of Audit Action Plan | Developed Audit Action Plan | Date of Adoption | Developed Audit Action Plan by 31 January 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | Developed Audit Action Plan by 31 January 2018 | 0 | X | X | Executive | Council Resolution
KPI 101 | Mun 25 |  |  | 100% Implementation of Audit Action Plan | 100% Implemented Audit Action Plan | Date of Adoption | 100% Implemented Audit Action Plan by 30 June 2018 | None | 0 | None | None | None | None | 1 Report by 30 September 2017 | 0 | 1 Report by 31 December 2017 | 0 | 2 Reports by 31 December 2017 | 0 | 1 Report by 31 March 2018 | 0 | 1 Report by 30 June 2018 | 0 | Executive | Reports
KPI 102 | Mun 26 |  | Enhancement of Auditor-General engagement | Functional IDP/Budget Steering Committeee | 4 Dashboard Committee Meetings held | Number of Dashboard Committee Meetings | 4 Dashboard Committee Meetings held by 30 June 2018 | Property Rates | 0 | None | None | None | None | 1 Dashboard Committee Meeting | 400 | 1 Dashboard Committee Meeting | 400 | 2 Dashboard Committee Meetings | 800 | 1 Dashboard Committee Meeting | 400 | 1 Dashboard Committee Meeting | 400 | Executive | Attendance Register
KPI 103 | Fin 1 |  | Payment to creditors to be made within 30 days in terms of section 65 of MFMA | 100% payment to creditors to be made within 30 days | 100% payment to creditors within 30 | Number of monthly reports | 12 Reports submitted by 30 June 2018 | None | 0 | None | None | None | None | 3 Reports Submitted | 0 | 3 Reports Submitted | 0 | 6 Reports Submitted | 0 | 3 Reports Submitted | 0 | 3 Reports Submitted | 0 | Finance | Monthly Reports
KPI 104 | Fin 2 | To improve municipal financial viability and sound financial management | Ensuring financial reporting and compliance | Submitted in-year Financial Reports in line with legislation | 17 Reports submitted by 30 June 2018 | Number of reports submitted. | 17 Reports submitted by 30 June 2018 | None | 0 | None | None | None | None | 6 Reports Submitted | 0 | 6 Reports Submitted | 0 | 12 Reports Submitted | 0 | 3 Reports Submitted | 0 | 2 Reports Submitted | 0 | Finance | Reports
KPI 105 | Fin 3 |  | Implementing revenue enhancement strategy | Implemented Revenue Enhancement Strategy | 100% Implemented Revenue Enhancement Strategy | % of Implementation | 100% Implemented Revenue Enhancement Strategy by 30 June 2018 | None | 0 | None | None | None | None | 1 Report by 30 September 2017 | 0 | 1 Report by 31 December 2017 | 0 | 2 Reports by 31 December 2017 | 0 | 1 Report by 31 March 2018 | 0 | 1 Report by 30 June 2018 | 0 | Finance | Reports
KPI 106 | Fin 4 |  | Revenue Management |  | 12 Reports submitted | Number of reports submitted. | 12 Reports submitted by 30 June 2018 | None | 0 | None | None | None | None | 3 Reports Submitted | 0 | 3 Reports Submitted | 0 | 6 Reports Submitted | 0 | 3 Reports Submitted | 0 | 3 Reports Submitted | 0 | Finance | Reports
KPI 107 | Fin 5 |  |  | Enhance revenue collection | 90% revenue collection rate | % of revenue collection | 90% revenue collection rate by 30 June 2018 | Property Rates | 186000 | Printing of billing statements = R 186 000.00 | Revenue Collection is sitting at 30% | Revenue Collection is sitting at 30% | Revenue Collection is sitting at 30% | 3 Reports on Revenue collection | 46500 | 3 Reports on Revenue collection | 46500 | 6 Reports on Revenue collection | 93000 | 3 Reports on Revenue collection | 46500 | 3 Reports on Revenue collection | 46500 | Finance | Reports
KPI 108 | Fin 6 |  | Expenditure Management | Formulated Plan for a Capital Budget | 100% Implemented the Capital Budget Plan | % of Implementation | 100% Implemented Capital Budget Plan by 30 June 2018 | None | 0 | None | None | None | None | 1 Report by 30 September 2017 | 0 | 1 Report by 31 December 2017 | 0 | 2 Reports by 31 December 2017 | 0 | 1 Report by 31 March 2018 | 0 | 1 Report by 30 June 2018 | 0 | Finance | Reports
KPI 109 | Fin 7 |  |  | Formulated Plan for Operational Budget | 100% Implemented Operational Budget plan | % of Implementation | 100% Implemented Operational Budget plan by 30 June 2018 | None | 0 | None | None | None | None | 1 Report by 30 September 2017 | 0 | 1 Report by 31 December 2017 | 0 | 2 Reports by 31 December 2017 | 0 | 1 Report by 31 March 2018 | 0 | 1 Report by 30 June 2018 | 0 | Finance | Reports
KPI 110 | Fin 8 |  |  | Monitored Expenditure against approved Budget | 12 Comparison reports prepared | Number of Reports | 12 Comparison reports prepared by 30 June 2018 | None | 0 | None | None | None | None | 3 Comparison Reportrs | 0 | 3 Comparison Reportrs | 0 | 6 Comparison Reportrs | 0 | 3 Comparison Reportrs | 0 | 3 Comparison Reportrs | 0 | Finance | Reports
KPI 111 | Fin 9 |  | Improving Budget Process and Implementation | Functional IDP/Budget Steering Committeee | 7 Steering Committee Meetings | Number of Steering Committee Meeting | 7 Steering Committee Meetings by 30 June 2018 | None | 0 | None | None | None | None | 2 Steering Committee Meetings | 0 | 2 Steering Committee Meetings | 0 | 4 Steering Committee Meetings | 0 | 2 Steering Committee Meetings | 0 | 1 Steering Committee Meeting | 0 | Finance | Attendance Register
KPI 112 | Fin 10 |  |  | An approved IDP/Budget Time Table (Process Plan) | An approved IDP/Budget Process Plan | Date of approval | An approved IDP/Budget Process Plan by 31 August 2017 | None | 0 | None | None | None | None | An approved IDP/Budget Process Plan by 31 August 2017 | 0 | X | 0 | An approved IDP/Budget Process Plan by 31 August 2017 | 0 | X | 0 | X | 0 | Finance | Council Resolution
KPI 113 | Fin 11 |  | Enhancing Actual service charges and property rates revenue | Reviewed Tariffs | Reviewed Tariffs | Date of approval | Reviewed Tariffs by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | Review Tariffs | 0 | Review Tariffs | 0 | Finance | Council Resolution
KPI 114 | Fin 12 |  |  | Implemented tariffs | Implemented tariffs | Level of implementation | Implemented tariffs by 30 June 2018 | None | 0 | None | None | None | None | 1 Report by 30 September 2017 | 0 | 1 Report by 31 December 2017 | 0 | 2 Reports by 31 December 2017 | 0 | 1 Report by 31 March 2018 | 0 | 1 Report by 30 June 2018 | 0 | Finance | Reports
KPI 115 | Fin 13 |  |  | Implemented General Valuation and SV Roll | Implemented Valuation Roll | Level of implementation | Implemented Valuation Roll by 01 August 2017 | Property Rates | 250000 | Municipal Valuer ( SV ) = R 250 000.00 | Current Valuation roll is not updated | Current Valuation roll is not updated | Current Valuation roll is not updated | Implemented Valuation Roll by 01 August 2017 | 250000 | X | X | Implemented Valuation Roll by 01 August 2017 | 250000 | X | X | X | X | Finance | Council Resolution
KPI 116 | Fin 14 |  |  | Preparation of the New General Valuation roll | Prepared New General Valuation Roll | Date of Adoption | Prepared New General Valuation Roll by 30 June 2018 | Property Rates | 1400000 | Municipal Valuer ( new ) = R 1 400 000.00 | Current Valuation roll is not updated | Current Valuation roll is not updated | Current Valuation roll is not updated | X | X | X | X | X | X | X | X | Prepared New General Valuation Roll by 30 June 2018 | 1400000 | Finance | Council Resolution
KPI 117 | Fin 15 |  | Ensuring compliance with SCM Regulations | Reviewed SCM Policy | Reviewed SCM Policy | Date of Adoption | Reviewed SCM Policy per 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Reviewed SCM Policy per 30 June 2018 | 0 | Finance | Council Resolution
KPI 118 | Fin 16 |  |  | Appointed New Bid Committees | 3 Bid Committees appointed | Number of Bid Committees appointed | 3 Bid Committees appointed by 31 July 2017 | None | 0 | None | None | None | None | 3 Bid Committees appointed by 31 July 2017 | 0 | X | X | 3 Bid Committees appointed by 31 July 2018 | 0 | X | X | X | X | Finance | Appointment letters
KPI 119 | Fin 17 |  |  | Trained Bid Committees | 1 Training conducted | Number of Trainings conducted | 1 Training conducted by 30 September 2017 | None | 0 | None | None | None | None | 1 Training Conducted | 0 | X | X | 1 Training Conducted | 0 | X | X | X | X | Finance | Attendance Register
KPI 120 | Fin 18 |  |  | SCM Quarterly Reports | 4 SCM Reports | Number of SCM Reports | 4 SCM Reports by 30 June 2018 | None | 0 | None | None | None | None | 1 SCM Report | 0 | 1 SCM Report | 0 | 2 SCM Reports | 0 | 1 SCM Report | 0 | 1 SCM Report | 0 | Finance | Reports
KPI 121 | Fin 19 |  |  | Developed schedule of Bid Committee Meetings | Developed schedule of Bid Committee Meetings | Date of Adoption | Developed schedule of Bid Committee Meetings 30 September 2017 | None | 0 | None | None | None | None | Developed schedule of Bid Committee Meetings | 0 | X | X | Developed schedule of Bid Committee Meetings | 0 | X | X | X | X | Finance | Bid Committee Schedule
KPI 122 | Fin 20 |  | Effective Management of Assets | Reviewed Fixed Asset Register | Reviewed Fixed Asset Register | Date of approval | Reviewed Fixed Asset Register by 30 June 2018 | Equitable Share | 600000 | Service Provider = R 600 000.00 | None | None | None | Review Asset Register | 600000 | X | X | Review Asset Register | 600000 | X | X | X | X | Finance | Council Resolution
KPI 123 | Fin 21 |  | Facilitating the appointment of Financial Interns | Appointed over a multi-year period | Five appointed interns | Number of Interns appointed | Five appointed interns by 30 June 2018 | FMG Grant | 575000 | Salaries for five interns = R 575 000.00 | None | None | None | X | X | X | X | X | X | X | X | Five appointed interns by 30 June 2018 | 575000 | Finance | Appointment letters
KPI 124 | Fin 22 |  | Implementation of mSCOA | Implemented Municipal Standard Chart of Account | 4 reports on Municipal Standard Chart Account submitted | Number of reports submitted. | 4 reports on Municipal Standard Chart Account submitted by 30 June 2018 | FMG Grant | 1325000 | MSCOA Implementation = R 1 325 000.00 | None | None | None | 1Report Submitted | 331250 | 1Report Submitted | 331250 | 2 Reports Submitted | 662500 | 1Report Submitted | 331250 | 1Report Submitted | 331250 | Finance | Reports
KPI 125 | Fin 23 |  |  |  | 4 reports on Municipal Standard Chart Account submitted | Number of reports submitted. | 4 reports on Municipal Standard Chart Account submitted by 30 June 2018 | Property Rates | 280000 | Software licenses = R 280 000.00 | None | None | None | 1Report Submitted | 70000 | 1Report Submitted | 70000 | 2 Reports Submitted | 140000 | 1Report Submitted | 70000 | 1Report Submitted | 70000 | Finance | Reports
KPA 6 : CROSS CUTTING INTERVENTIONS (SPATIAL DEVELOMENT, ENVIRONMENT PLANNING & DISASTER MANAGEMENT)
KPI 126 | PLD 16 | To ensure efficient and sound Strategic and Spatial municipal planning | Facilitate the formulation of the Credible IDP | Formulate IDP Process plan | 1 IDP process plan produced | Date of approval | 1 IDP process plan produced by 31 August 2017 | None | 0 | None | None | None | None | 1 IDP process plan produced by 31 August 2017 | 0 | X | X | 1 IDP process plan produced by 31 August 2017 | 0 | X | X | X | X | Planning | IDP Process Plan & Council Resolution
KPI 127 | PLD 17 |  |  | Formulate a credible IDP | Approved IDP | Date of approval | Approved IDP by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Approved IDP by 30 June 2018 | 0 | Planning | IDP Document & Council Resolution
KPI 128 | PLD 18 |  | Enhancing Municipal Spatial Planning | Develop Spatial Development Framework | Completed SDF | Date of approval | Completed SDF by 30 June 2018 | EQS | 400000 | Service Provider = R 400 000.00 | None | None | None | X | X | X | X | X | X | X | X | Completed SDF by 30 June 2018 | 400000 | Planning | SDF Document & Council Resolution
KPI 129 | PLD 19 |  |  | Develop Municipal Sector Plans | Completed Sector Plans | Date of Completion | x3 Completed Sector Plans by 30 June 2018 | EQS | 1100000 | Advertisement = R 10 000.00 & Service Provider = R 1 090 000.00 | None | None | None | X | X | X | X | X | X | X | X | x3 Completed Sector Plans by 30 June 2018 | 1100000 | Planning | Council Resolution
KPI 130 | PLD 20 |  | Enhancing Land Use Management Systems | Establish Municipal Planning Tribunal (SPLUMA Implementation) | Established Municipal Tribunal by August 2018 | Date of Adoption | Established Municipal Tribunal by August 2018 | None | 0 | None | None | None | None | Established Municipal Tribunal by August 2017 | 0 | X | X | Established Municipal Tribunal by August 2017 | 0 | X | X | X | X | Planning | Council Resolution
KPI 131 | PLD 21 |  |  | Develop Wall to Wall Land Use Scheme | CompletedPhase one of wall to wall scheme | Date of Completion | Completed Phase one of wall to wall scheme by June 2018 | Rates - SOP | 1000000 | Service Provider = R 1 000 000.00 | None | None | None | X | X | X | X | X | X | X | X | Completed Phase one of wall to wall scheme by June 2018 | 1000000 | Planning | Council Resolution
KPI 132 | PLD 22 |  |  | Enforce Land Use Scheme | 100 % enforced Land Use Schemes | % Of enforcement | 100 % enforced Land Use Schemes by 30 June 2018 | None | 0 | None | None | None | None | Enforce | 0 | Enforce | 0 | Enforce | 0 | Enforce | 0 | Enforce | 0 | Planning | Reports
KPI 133 | Com 18 | To promote and preserve a safe and healthy environment | Enhancing Environmental Quality in Compliance with relevant legislation | Planting of greens and continous cleaning of parks and gardens | Completed Schedule of cleaning intervals | Date of Completion | Completed Schedule of cleaning intervals by 30 June 2018 | None | 0 | None | None | None | None | X | X | X | X | X | X | X | X | Completed Schedule of cleaning intervals by 30 June 2018 | 0 | Community | Reports
KPI 134 | Com 19 |  |  |  | 10 Trees Planted | Date of Completion | 10 Trees Planted by 30 June 2018 | None | 0 | None | None | None | None | X | X | 10 Trees Planted | 0 | 10 Trees Planted | 0 | X | X | X | X | Community | Reports
KPI 135 | Com 20 |  |  | Facilitate process of legalising Waste Disposal | Legalized Waste Disposal by 30 June 2018 | Date of approval | Legalized Waste Disposal by 30 June 2018 | None | 0 | None | None | None | None | X | X | Appointment of consultant | 0 | Appointment of consultant | 0 | X | X | Legalized Waste Disposal by 30 June 2018 | 0 | Community | Council Resolution
KPI 136 | Cor 25 |  | Improving Municipal Response towards Disaster Occurences | Conduct public safety awareness campaign | 8 Conducted Public Safety Awareness Campaigns | Number of campaigns conducted | 8 Conducted Public Safety Awareness Campaigns by 30 June 2018 | None | 0 | None | None | None | None | 2 Campaigns | 0 | 2 Campaigns | 0 | 4 Campaigns | 0 | 2 Campaigns | 0 | 2 Campaigns | 0 | Corporate | Attendance Register
|  | ........................................... | ..............................................
|  | Signed By Municipal Manager | Signed by Mayor
|  | Date.............................. | Date......................................