## 2016-2017
Audit Action Plan - èDumbe Municipality
AG Audit Reports 2016/2017
Matters to be included in the auditor's report: these matters should be addressed as a matter of urgency
Annexure A: Matters affecting the auditor's report.
# = Finding was reported in the 2015/2016 management report but was not resolved.
Item | Source Document/ Reference | Finding Description | AG Recommendation | Implementation plan to address finding / Action required | Date Action to be completed | Responsible Department & Official | Progress Report from Management | Comments from Internal Audit
#1 | AG Management Report 2016/2017 - Detailed Finding 5 | Creditors not paid within 30 days. | Management should implement controls over the monitoring and tracking of invoices thereby ensuring payment within 30 days, furthermore, reasons for not processing payments on time should be documented on the payment voucher. | > Complete and review creditor reconciliations monthly; > Monthly creditors register will be developed, implemented and monitored by Manco to facilitate payments of invoices within 30 days of receipt; > Age analysis will be monitored monthly. | 2018-02-28 | Finance - CFO and Manager Finance
As per section 65(2)(e) of the MFMA, money owed by the municipality must be paid within 30 days. The municipality does not always pay creditors within 30 days as required by section 65(2)(e) of the MFMA. This results in non-compliance with section 65 of the MFMA and consequently led to the incurrence of fruitless and wasteful expenditure.
#2 | AG Management Report 2016/2017 - Detailed Finding 13 | AOPO - Targets are not measurable. | Management should ensure that quarterly reports and the annual performance report are compiled based on the format and information could be measured in SDBIP and Annual performance report. SDBIP and Annual performance report should be reviewed to ensure all targets are measurable. | > Setting goals, indicators & targets using SMART principle. > Review 2017/18 SDBIP to ensure that targets are set based on a SMART principle. | 2018-02-28 | Executive - Acting PMS & Risk Manager
Section 41(1)(b) of the MSA states that a municipality must, in terms of its performance management system and in accordance with any regulations and guidelines that may be prescribed, set measurable performance targets with regard to each of those development priorities and objectives. During the audit of predetermined objectives a number of indicators were identified as not being measurable.
#3 | AG Management Report 2016/2017 - Detailed Finding 14 | AOPO - Inconsistency between planned targets and reported achievements. | The annual performance report should be reviewed to the planned documents to ensure that indicators and targets that are planned are reported on. Indicators should be clear, specific and well defined across all performance management and monitoring documents. This will ensure that there is consistency applied and no ambiguity in measuring the targets. Furthermore management should ensure that quarterly reports and the annual performance report are compiled based on formats and information consistent with the IDP and SDBIP. | > Management will review quarterly SDBIP. | 2018-02-28 | Executive - Acting PMS & Risk Manager
Section 41(1)(b) of the MSA states that a municipality must, in terms of its performance management system and in accordance with any regulations and guidelines that may be prescribed, set measurable performance targets with regard to each of those development priorities and objectives. As a result of the significance of the finding, it is concluded that the targets reported in the annual performance report are not consistent with those reported actual achieved. This has resulted in non-compliance with the MSA.
#4 | AG Management Report 2016/2017 - Detailed Finding 15 | Verifiability of key performance indicators. | Key performance indicators must be verifiable. The process that is used to calculate the target must be present, and have the ability to be validated. Some of the electricity projects listed, i.e. Ntungwini, Enkembeni, completion certificates were provided though it could not satisfy the Auditors as they requested the list of households which is obtained from the Department of Energy. | > Management will ensure that a complete POE file exists | 2018-02-28 | Executive - Acting PMS & Risk Manager
Paragraph 3.2 of the Framework for Managing Programme Performance Information (FMPPI) states that a good performance indicator should be: Reliable, Well-defined, Verifiable, Cost-effective, Appropriate and Relevant.
Other important matters: these matters should be addressed to prevent them from leading to material misstatements of the financial statements or material findings on the performance report and compliance with legislation in future.
Annexure B: Other important matters.
Item | Source Document/ Reference | Finding Description | AG Recommendation | Implementation plan to address finding / Action required | Date Action to be completed | Responsible Department & Official | Progress Report from Management | Comments from Internal Audit
5 | AG Management Report 2016/2017 - Detailed Finding 16 | Policies not updated. | The accounting officer should improve his oversight to annually review policies to confirm that the policies are aligned to the current legislation and accounting standards to enable and support the understanding and execution of sound internal control objectives, processes, and responsibilities. All changes to the policies should be communicated thereafter to all staff and training provided, if deemed necessary. | > All municipal policies will be reviewed. | 2018-02-28 | All departments of the Municipality - Accounting Officer, CFO, Director Corporate & Community Services and Director Planning & Infrastructure.
|  | In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control. The policies of the municipality were not reviewed annually and were last updated 5 years ago. |  | > All reviewed policies will be submitted to Council for approval. | 2018-04-30
6 | AG Management Report 2016/2017 - Detailed Finding 17 | Audit Committee Meetings. | The accounting officer must implement controls to ensure that the audit committee meets a minimum of 4 times a year. | > Ensure appointment of audit committee members. > Ensure that a minimum of four meetings sit during the 2017/18 FY. | 2018-02-28 | Executive - Accounting Officer
|  | In terms of section 166(4)(b) of the MFMA the audit committee must meet as often as is required to perform its functions, but at least four times a year. It was noted that the audit committee only held 3 meetings during the 2016/2017 FY, resulting in non-compliance with MFMA section 166. |  |  | 2018-06-30
7 | AG Management Report 2016/2017 - Detailed Finding 18 | No terms of reference in place. | The accounting officer must ensure that terms of reference are in place for each committee which has been established. | > Develop terms of references for the stated committees. > Submit developed terms of references to Council for approval. | 2018-02-28 | > Executive - Accounting Officer; > Corporate & Community Services - Director Corporate & Community; > Finance - CFO
|  | In Terms of Circular 65 of the MFMA, all committees should have terms of reference in place. It was noted that the following committees do not have terms of references: (i) Finance Portfolio Committee, (ii) Audit committee and (iii) EXCO. |  |  | 2018-04-30
8 | AG Management Report 2016/2017 - Detailed Finding 19 | SCM - Approved procurement plan was not submitted to National Treasury by 31 March 2016. | The CFO must implement control to ensure that the procurement plan is submitted to National Treasury within the legislated deadline. | > Develop procurement plan for 2018/2019 FY; > Submit the 2018/19 procurement plan to National Treasury by 31 March 2018. | 2018-02-28 | Finance - CFO and Manager SCM
|  | In terms of National Treasury Instruction 2 of 2016/17, the municipality must submit to treasury its procurement plan by the 31 March. During the audit of procurement management it was noted that the procurement plan was submitted in September 2016, this resulted in non-compliance with NT instruction 2 of 2016/2017. |  |  | 2018-03-31
Item | Source Document/ Reference | Finding Description | AG Recommendation | Implementation plan to address finding / Action required | Date Action to be completed | Responsible Department & Official | Progress Report from Management | Comments from Internal Audit
#9 | AG Management Report 2016/2017 - Detailed Finding 20 | IT Control Environment Deficiencies. |  |  |  | Corporate & Community Services - Manager ICT
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control.
|  | The following deficiencies in the general IT internal control environment were identified: >Segregation of duties: the function of both IT Security Officer and IT Governance Champion position is being carried out by the IT Technician. | >Management must create a new position for an IT Security officer and nominate an IT Governance Champion or delegate these duties to someone other than IT Technician. | >Provide budget provision for IT Security Officer; >Nominate the ICT Manager to perform IT Governance Champion functions; | >2018/19 FY; > 28 Feb 2018;
|  | > The Job description of the IT Technician does not cover all the responsibilities and duties carried out by the technician. > The IT steering committee met four times during the year, contravening the requirement as per the ICT charter i.e. 6 meetings per year. | > Management should amend the IT Technicians job description to correlate with his current responsibilities. >IT Steering committee must schedule meetings every 2 months in order to comply with the ICT Charter. | >Amend job description of IT Technician; > Develop an annual meetings plan for the IT steering committee; > Review ICT Charter on the IT Steering Committee meetings; | >28 Feb 2018; > 28 Feb 2018; >30 June 2018;
|  | >The SLA relating to Syntel expired in 2012. >Notebooks do not have the latest critical and security network updates installed. >The user accounts for the Camelsa agents are stored on the system in a perpetually disabled state and are reactivated upon each visit. These accounts are not removed despite being dormant for periods longer than 90 days. | >The Syntel SLA must be renewed to a fixed term contract. > Notebooks must be booked in to the IT Technician to facilitate him manually updating the devices with the latest critical and security updates. In addition the IT Technician must schedule update booking availability times for staff who do not work onsite on a daily basis. Large automatic updates must be conducted overnight by locking the relevant devices in the IT Technician's office or another secure room. | > Appoint a new service provider for electric sales; > Develop monthly schedules of conducting updates; >Install updates on Notebooks with the latest critical and security networks; >Monitor compliance with installed updates; | > 31 Mar 2018; > 28 Feb 2018
|  | > IT Technician does not delete the accounts as the same agents return for evaluation and application support at varying time intervals throughout the year. >The Disaster recovery plan test is not being conducted each year. >Management did not schedule a disaster recovery test to be conducted during the year under review. >The Network Controller post is vacant. | >The IT Technician must adhere to the User account Management policy and remove dormant Camelsa user accounts, new accounts may be created when new Camelsa technicians visit the Municipality for evaluation. >Management must adhere to the disaster recovery plan and schedule disaster recovery test to be conducted on an annual basis. | > Ensure adherence with the user account management policy by removing dormant user accounts; >Make budget provision to acquire resources to implement disaster recovery plan; | > 28 Feb 2018; > 2018/19 FY;
#10 | AG Management Report 2016/2017 - Detailed Finding 21 | Periodic reviews of User access not performed and inadequate user access controls. | The IT Technician must test and confirm that transactions linked to user accounts remain on the system after being removed to avoid the need to maintain accounts of former employees thereby ensuring all dormant accounts from the system are timeously removed upon departure of the employee. Management must implement controls to ensure that reviews of user accounts are performed on a monthly basis to identify unauthorised access privileges. | > Ensure that monthly and quarterly reviews on user access will be performed and signed as proof of being reviewed. | 2018-02-28 | Corporate & Community Services - Manager ICT
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control.
The following deficiencies were identified relating to user access controls: >The user account for PZ Ntanzi was disabled upon resignation in December 2016 however the user account has yet to be removed from the system due to important transactions history which still exists on the account profile. >The user access reports are not reviewed on a monthly basis. >User accounts which are not removed can be reactivated and used to produce fictitious transactions. By not conducting regular reviews on user access privileges, the early detection of incorrect privileges will not be possible which could result in abuse of user account rights and subsequent misstatements in the financial statements.
11 | AG Management Report 2016/2017 - Detailed Finding 22 | Review of access reports not performed. | The monitoring responsibility of the Director of Corporate Services should be delegated to another independent Director temporarily until the position is filled. Furthermore the vacant post must be advertised and filled as soon as possible. | > Ensure that monthly independent reviews of the access reports are done, monitored and signed as proof of being reviewed. | 2018-02-28 | Corporate & Community Services - Director Corporate & Community
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control. It was noted that the Director of Corporate Services does not perform independent reviews on reviewed user access reports. This is due to the Director of Corporate Services position being vacant and the responsibilities of this post have not yet been delegated to an acting person.
It was noted that the Director of Corporate Services does not perform independent reviews on reviewed user access reports. This is due to the Director of Corporate Services position being vacant and the responsibilities of this post have not yet been delegated to an acting person.
12 | AG Management Report 2016/2017 - Detailed Finding 23 | No backups performed. | A new cloud/online storage service provider must be appointed immediately to ensure a media facility is available to conduct daily backups. Manual weekly backups of the file server should be conducted on physical storage media in the interim until a new cloud/online storage service provider has been appointed. | > Make budget provision to appoint cloud/online storage service provider in the 2018/2019 FY. > Ensure that weekly and monthly backups are being performed. | >31 May 2018; > 28 Feb 2018 | Corporate & Community Services - Director Corporate & Community and Manager ICT
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control.
It was noted that the file server is not being backed up on a daily basis furthermore no service provider has been appointed for the online backup facility. The previous service provider Vox telecoms cancelled their services to the Municipality due to non-payment of their account in April 2016. In the event of a disaster or any other method of loss/damage to critical data, the Municipality will not be able to restore information to their file system and network which will impact the ability to continue.
13 | AG Management Report 2016/2017 - Detailed Finding 24 | Action plan inadequate. | The CFO must improve the Municipality's action plan by including details of the necessary actions of commitments intended by management to rectify the findings and ensure that the implementation of the action plan is adequately monitored and reviewed, thereby increasing its effectiveness. | >Review the 2015/2016 external audit action plan and include details of the necessary actions or commitments intended by management to rectify the findings; > Develop an external audit action plan for both 2016/2017 and 2015/2016 financial years; > Monitor and update the action plan on a monthly basis. > Submit the action plan to Manco, EXCO, Audit Committee and Council for monitoring and reporting purposes. | 2018-02-28 | Executive - Accounting Officer and Internal Auditor
In terms of section 62(1) of the MFMA, the accounting officer of a municipality is responsible for managing the financial administration of the entity, and must for this purpose take all reasonable steps to ensure: a) That the resources of the entity are used effectively, efficiently, economically and transparently; b) That full and proper records of the financial affairs of the entity are kept; c) That the entity has and maintains effective, efficient and transparent systems of financial and risk management and internal control;
An audit action plan was developed and implemented for addressing prior period findings raised in the external audit management report. However the action plan does not detail the necessary actions or commitments by management intended to rectify the findings. In addition, there is no evidence to indicate that the action plan is monitored, thus compromising its effectiveness.
14 | AG Management Report 2016/2017 - Detailed Finding 25 | Asset register reconciliation not performed. | CFO should ensure that asset register reconciliations are performed and reviewed on a monthly basis. | > Develop a quarterly plan for performing monthly assets physical checks; > Monthly physical checks done will be monitored and signed as proof of review; >Develop, perform, review and sign monthly assets register reconciliations. | >2018/01/31; >Ongoing; > 2018/02/28 and Ongoing. | Finance - CFO and Manager SCM
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control.
It was noted that no fixed asset register reconciliations were performed during the year consequently errors and omissions are not timeously detected and corrected which could possibly lead to a misstatement in fixed assets on the annual financial statements.
15 | AG Management Report 2016/2017 - Detailed Finding 26 | Council resolution not signed for disposal of Assets. | Management must ensure that the process and procedures in place for the disposal of assets are adhered to thereby ensuring that disposals are adequately approved by Council. | > Submit an item to Council to be tabled for condoning. | 2018-04-30 | >Executive - Accounting Officer; > Finance - CFO & Manager SCM
Section 14(1) &(2) of the MFMA states: 1. A municipality may not transfer ownership as a result of a sale or other transaction or otherwise permanently dispose of a capital asset needed to provide the minimum level of basic municipal services. 2. A municipality may transfer ownership or otherwise dispose of a capital asset other than one contemplated in subsection(1), but only after the municipal council, in a meeting open to the public :- a. has decided on reasonable grounds that the asset is not needed to provide the minimum level of basic municipal services; and b. has considered the fair market value of the asset and the economic and community value to be received in exchange for the asset.
It was noted that there was no council resolution for the disposal of any disposals during the period under review. Resulting in non-compliance with section 14 of the MFMA, consequently fixed assets may be misstated in the annual financial statement.
#16 | AG Management Report 2016/2017 - Detailed Finding 27 | Equitable share misstated. | Management must ensure that all AFS supporting information is accurate and reliable. | > Perform cross checks on the financial system and allocation as per DoRA of equitable share received to confirm that they are accurate. > Investigate the difference of R388 000 for 2016/17. > Investigate the difference of R458 000 for 2015/16. > Amend AFS figures for equitable share. | 2018-04-30 | Finance - CFO and Manager Finance
In terms of Section 64 of the MFMA the accounting officer must for the purposes of subsection(1) take all reasonable steps to ensure that the municipality has and maintains a management, accounting and information system which:- i. recognises revenue when it is earned; ii. accounts for debtors; and iii. accounts for receipts of revenue.
During the audit of equitable share it was noted that bank receipts for equitable share amounted to R57 512 000 and allocation as per DoRA is R59 000 000 with the difference of R388 000 not agreeing to the amount withheld as per letter of correspondence from treasury which states that R493 000 was withheld. Consequently equitable share may be misstated.
17 | AG Management Report 2016/2017 - Detailed Finding 33 | No background checks performed on new appointments. | The Municipality should comply with the HR policy by insisting that the results of the vetting are received and have been evaluated prior to making appointments. This information should then be securely filed. | > Management should review the recruitment policy and include a paragraph dealing with vetting of employees which include background checks prior to an interview being conducted; >Management should review the employee files for inclusion of the MIE background screening report prior to submitting the appointment letter to the MM for signing. When the MIE background screening is not included, necessary measures should be undertaken prior to approving the appointment. | 2018-04-30 | Corporate & Community Services - Director Corporate & Community and Acting Manager HR
In terms of section 67(1) of the MFMA, a municipality, in accordance with applicable law and subject to any applicable collective agreement, must develop and adopt appropriate systems and procedures, consistent with any uniform standards prescribed in terms of section 72(1)(c), to ensure fair, efficient, effective and transparent personnel administration, including:- a) the recruitment, selection and appointment of personnel as staff members.
In performing the audit of human resource management it was noted that the vetting of qualifications is not performed as results from the SAQA were not on file. As a result of this the municipality is at risk of hiring people with inappropriate qualifications or which do not meet the qualifying criteria which could result in duties not being performed at the expected level.
18 | AG Management Report 2016/2017 - Detailed Finding 34 | Senior management position vacant. | Council should ensure that all vacant positions, especially management positions, are filled with permanent resources. | > Ensure that Director Corporate & Community resumes duties as per appointment on Council meeting that sat on 13 December 2017; > Ensure that Director Corporate & Community signs work contract, job description and performance agreement as per MSA. | 2018-02-28 | Executive - Accounting Officer
In terms of s56(1)(a)(i) of the MFMA a municipal council (2) a person appointed as municipal manager in terms of subsection(1) must at leased have the skills, expertise, competencies and qualifications as prescribed. Furthermore a person appointed in terms of subsection(1)(b) may not be appointed to act for a period that exceeds three months.
During the HR management audit it was noted that the position for Senior Manager Community Services was vacant for the entire 2016/2017 financial year.
#19 | AG Management Report 2016/2017 - Detailed Finding 35 | No performance management systems for other employees. | The Municipality should implement a performance system for other employees in order to detect the performance of each employee other than the seniors. | > Management will review and amend the performance management system policy to cascade down to other levels. | 2018-02-28 | > Executive - Accounting Officer >Corporate & Community Services - Director Corporate & Community
In terms of section 62(1) of the MFMA, the accounting officer of a municipality is responsible for managing the financial administration of the entity, and must for this purpose take all reasonable steps to ensure: a) That the resources of the entity are used effectively, efficiently, economically and transparently; b) That full and proper records of the financial affairs of the entity are kept; c) That the entity has and maintains effective, efficient and transparent systems of financial and risk management and internal control;
During the HR management audit it was noted that no performance management system was in place for other employees other than senior managers. As a result under performance of employees may not be detected.
#20 | AG Management Report 2016/2017 - Detailed Finding 36 | No approved roads infrastructure policy and maintenance plan. |  | > Develop Roads infrastructure policy; > Submit the roads infrastructure policy to Council for approval; > Develop maintenance plan | > 28 Feb 2018; > 30 Apr 2018; | > Executive - Accounting Officer; > Planning & Infrastructure Services - Director Planning & Infrastructure
|  | The functions and powers over "municipal roads" vest with the local municipality in terms of Section 156(1) of the Constitution read together with Part B of Schedule 4 and Part B of Schedule 5. Furthermore, in terms of Section 83 of the Municipal Structures Act, a municipality has the functions and powers assigned to it in terms of Section 156 and 229 of the Constitution. | The accounting officer together with the infrastructure manager must develop, approve and implement roads infrastructure policies and procedures.
|  | The Municipality did not develop and implement a policy for the planning, management and reporting of road infrastructure this will impact on proper planning and decision making to achieve desired outcomes in respect of the management of road infrastructure. | The policy should clearly set out the following: >strategic planning (long and medium - term plans/operational plans); > life cycle of road infrastructure; > maintenance planning (preventative, routine and repairs); > funding of new road infrastructure and maintenance of existing road infrastructure; > management information system; > roles and responsibilities of staff involved in road infrastructure.
|  | In addition, the municipality did not have an approved road infrastructure maintenance plan and an approved plan for backlogs which clearly indicates: > allowance for the rectification of existing defects, >description of the work to be carried out, > forecast of the necessary maintenance, > maintenance expenditure for the planning period and > eradication of existing backlog. | The maintenance plan which must address the following key issues: > allowance for the rectification of existing defects; > description of the work to be carried out; and > forecast of the necessary maintenance (preventative, routine and repairs); > addressing backlogs; > maintenance expenditure for the planning period; and > a plan to eradicate existing backlogs.
#21 | AG Management Report 2016/2017 - Detailed Finding 37 | No road asset management system. | The accounting officer must develop and approve a roads asset management system which must address the following: > road network; > condition of the road network; >life cycles of the roads; > maintenance planning; > maintenance history; and > backlogs. | > Develop road asset register, which will be monitored on quarterly basis and signed as proof of review. | 2018-03-31 | Planning & Infrastructure Services - Director Planning & Infrastructure and Manager PMU
The functions and powers over "municipal roads" vest with the local municipality in terms of Section 156(1) of the Constitution read together with Part B of Schedule 4 and Part B of Schedule 5. Furthermore, in terms of Section 83 of the Municipal Structures Act, a municipality has the functions and powers assigned to it in terms of Section 156 and 229 of the Constitution.
The municipality does not have a roads assets management system in place which records: > description of the road; > condition of the road; > life cycle of the road; > maintenance planning; and > maintenance history and backlogs.
#22 | AG Management Report 2016/2017 - Detailed Finding 38 | Internal control deficiency in managing existing consultants. | Management is to develop and implement a policy governing the appointment, and monitoring of consultants which provides for skill transfer. Furthermore, management is to develop and implement internal controls over consultants in order to facilitate compliance with the provisions of section 116 of the MFMA. | > Management will develop and implement a policy governing the appointment, and monitoring of consultants | 2018-03-31 | Executive - Accounting Officer
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control.
During the audit of consultants, the following internal control deficiencies were identified: 1) no formal policy in place governing consultants. While paragraph 35 of the supply chain management concerns consultants, the provisions relate primarily to procurement processes. 2) the municipality's action plan does not include prior year findings relating to consultants. 3) management did not conduct an annual review on the performance of consultants. 4) management did not conduct an analysis regarding the extent of their use of consultants. 5) no gap analysis performed prior to contracting consultants (needs assessment). 6) the bids terms of reference did not include the following: (i) requirements on experience and qualification; (ii) the task directive, objectives, goals and scope of the assignment; and (iii) the objectives, goals and scope of the assignment. 7) both consultants Delta Blue and Ducharme are appointed to address needs which are continuous, i.e. preparation of VAT returns, and asset register respectively, confirmed through enquiry with CFO, no posts for these functions exist. It was noted that no attempt was made on the part of management to create these posts. 8) the terms of reference of the SLA for both consultants, does not include an objective for transfer of skills, including the nature, scope and goals of the training program and no evidence was kept of skills transferred from the respective consultants to the municipal staff members. 9) there are no controls in place for monitoring and evaluating the performance of consultants. Non-compliance with standing legislation relating to and governing the hire of consultants.
#23 | AG Management Report 2016/2017 - Detailed Finding 39 | Consequence Management. | The municipality must develop a policy that governs the investigation of all unauthorised irregular as well as fruitless and wasteful expenditure. Going forward, Council should ensure that all matters are investigated to determine and assess if there are any individual that are liable and were reckless in their duties, prior to writing off the expenditure. | > Develop Consequence Management policy; > Submit policy to Council for approval. | > 2018/02/28; > 2018/04/30. | Executive - Accounting Officer
MFMA section 32 (2) stipulates that, a municipality must recover unauthorised, irregular or fruitless and wasteful expenditure from the person liable for that expenditure unless the expenditure in the case of unauthorised expenditure, is - authorised in an adjustments budget; or certified by the municipal council, after investigation by a council committee, as irrecoverable and written off by the council; and in the case of irregular or fruitless and wasteful expenditure is, after investigation by a council committee, certified by the council as irrecoverable and written off by the council.
In terms of section 67 of the Municipal Systems Act, a municipality, in accordance with applicable law and subject to any applicable collective agreement, must develop and adopt appropriate systems and procedures, consistent with any uniform standards prescribed in terms of section 72(1)(c), to ensure fair, efficient, effective and transparent personnel administration, including disciplinary procedures and the investigation of allegations of misconduct and complaints again staff.
During the audit of consequence management it was noted that no formal policy and procedures exist for consequence management. It was further noted that no investigations have taken place regarding any unauthorised, irregular and fruitless and wasteful expenditure identified in previous years resulting non-compliance section 32 of the MFMA.
24 | AG Management Report 2016/2017 - Detailed Finding 40 | Predetermined objectives - IDP non compliance. | Management should implement adequate controls and exercise oversight responsibility to ensure that legislative deadlines are adhered to. A performance reporting checklist should be maintained and adhered to. All supporting documentation should be filed and easily retrievable to support compliance with performance planning regulations. | > Management must review the IDP document to ensure that all documents which are recorded as being attached are indeed part of the IDP document; >Develop a performance reporting checklist that will be maintained and adhered to; > Create a supporting document file that will be retrievable (soft and hard copies); > Make budget provision to publicise summary IDP | 2018-06-30 | Planning & Infrastructure Services - Director Planning & Infrastructure and Manager Planning
In terms of the MSA section 25(4)(b), within 14 days of the adoption of its IDP the municipality must publicise a summary of the plan.
Section 29(3)(b) of the MSA, states that a local municipality must draft its IDP, taking into account the integrated development processes of, and proposals submitted to it by the district municipality.
Section 26 of the MSA states that an IDP plan must reflect:- b) an assessment of the existing level of development in the municipality, which must include an identification of communities which do not have access to basic municipal services; g) applicable disaster management plans.
In performing the audit of predetermined objectives the following issues have been identified: > no supporting evidence was provided that the municipality had consulted the district municipality proposals in drafting the IDP; > while the adoption of the IDP was advertised, a summary of the plan was not publicised; > it was noted that while IDP makes reference to annexure 15 as containing the disaster recovery plan, annexure 15 is missing. Furthermore, it was noted that the IDP does not contain an assessment of the existing level of development in the municipality as well as an indication of communities which do not have access to basic municipal services. This results in non-compliance with the MSA and municipal planning and reporting regulations.
25 | AG Management Report 2016/2017 - Detailed Finding 42 | No documented standard operating procedures. | Management should document and implement a standard operating procedure for the collection, recording, processing, monitoring and reporting of performance information. This would set in place controls that departments and managers can be measured against in an effort to improve the reporting process and the quality of the information provided in support of the information reported in the annual performance report. | > Develop Standard Operating procedures; | 2018-03-31 | All head of departments.
In terms of Section 62(c)(i) of the MFMA the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose ensure that the municipality has and maintains effective, efficient and transparent systems of > financial and risk management and internal control, and > internal audit operating in accordance with any prescribed norms and standards.
Paragraph 5.2 page 13 of the FMPPI states that performance information systems should be integrated within existing management processes and systems. The accounting officer or head official of an institution is responsible for ensuring that the institution has documentation addressing the following: > integration of performance information structures and systems within existing management processes and systems; > definitions and technical standards of all the information collected by the institution; > processes for identifying, collecting, collating, verifying and storing information.
The municipality does not have documented standard operating procedures in place to ensure that an effective, efficient and transparent system is kept. In addition there were no definitions and technical standards of all information collected. Subsequent walkthrough of systems also revealed that municipal officials are not fully aware of the input, process systems and output documents generated and require collaboration from other individuals to confirm the process. This underlines that, the performance management system is not fully understood across departments involved in the process.
In the absence of documented standard operating procedures this could result in the information reported in the annual performance report may contain material misstatements and inconsistencies due to a lack of understanding.
26 | AG Management Report 2016/2017 - Detailed Finding 43 | Non-compliance: MFMA section 72. | Management should implement adequate controls and exercise oversight responsibility to ensure that legislative deadlines are adhered to. A performance reporting checklist should be maintained and adhered to. | > Management will develop a performance reporting checklist that will be maintained and adhered to; > Management will ensure that the mid-year assessment will be tabled to Council on time as per the MFMA. | 2018-01-31 | Executive - Accounting Officer and Acting Manager PMS & Risk
In terms of section 72(1) of the MFMA. The accounting officer of a municipality must by 25 January of each year assess the performance of the municipality during the first half of the financial year, and submit the report on such assessment to the mayor of the municipality.
It was noted through inspection of council minutes, that the tabling on the mid-year assessment took place on the 31 January 2016, 6 days after the legislated deadline.
27 | AG Management Report 2016/2017 - Detailed Finding 44 | No indigent register developed and implemented. | The accounting officer should improve his oversight and ensure that the indigent register is developed, implemented and maintained by the municipality. Indigent register should be communicated thereafter to all staff. | > Develop, implement and maintain an indigent register. | 2018-03-31 | > Finance - CFO and Manager Finance; > Corporate & Community Services - Director Corporate & Community and Manager Community
In terms of Municipal systems act S97 - Contents of the policy - a credit control and debt collection policy must provide for: c) provision for indigent debtors that is consistent with its rates and tariffs policies and policy national policy on indigents.
In terms of Municipal systems act S104 - regulations and guidelines - (1) the minister may for the purposes of this chapter make regulations or issues guidelines with section 120 to provide for or regulate the following matters: > development and implementation of an indigent policy.
During the audit of debtors it was noted that the municipality did not develop and implement an indigent register.
AG Audit Reports 2015/2016
Matters to be included in the auditor's report: these matters should be addressed as a matter of urgency
Annexure A: Matters affecting the auditor's report.
Item | Source Document/ Reference | Finding Description | AG Recommendation | Implementation plan to address finding / Action required | Date Action to be completed | Responsible Department & Official | Progress Report from Management | Comments from Internal Audit
28 | AG Management Report 2015/2016 - Detailed Finding 3 | Hexing BravoPlex - Irregular expenditure. | Management is to provide audit with reasons as to why the above occurred, furthermore management must seek legal advice as to whether or not to cancel the contract taking into account all financial ramifications. | > Management will ensure compliance with PPPFA in all bids. | 2018-03-31 | >Executive - Accounting Officer; > Finance - CFO and Manager SCM |  | During our follow up review we noted per discussion with Mr. S Mngwengwe (CFO) that the Municipality will not use the service provider until the matter is completely resolved. He further indicated that the matter has been submitted to the MPAC for investigation. As soon as the outcome of the investigation is determined, legal advice would be sort out.
During the audit of bid 8/2014/2015, in respect of Smart metering solutions, awarded to Hexing Bravoplex it was noted that despite the bid advertisement specifically stating that the 90/10 principal of the Preferential procurement framework act would apply, the bids were not evaluated using said principal. Paragraph 8 of the bid evaluation minutes also states that the 90/10 principal was applied and refers to an annexure for record of the evaluation, however no such annexure was attached as the evaluation was not done. Enquiry with SCM Manager revealed that this was due to the nature of the bid, as bids did not have a specific price attached but were structured on a commission basis. Inspection of bid register however revealed that of the 6 bids recorded 3 quoted fixed amounts. Furthermore as per the PPFA in the event of there being no price, bids should still be evaluated using BBBE and functionality. In addition to the above the advertisement for the above did not include the tendering condition relating to locally produced goods. This results in non-compliance with Supply Chain Management Regulation 28 and PPR 9 with all arising expenditure being irregular.
29 | AG Management Report 2015/2016 - Detailed Finding 13 | AOPO - Non-compliance MSA sec 41(1)(a). | Municipality must set appropriate key performance indicators as a yardstick for measuring performance including outcomes and impact, with reared to the municipality's development priorities and objectives set out in its IDP. This should be considered when planning the 2016/17 IDP. | > Management will revise priorities and objectives and align them with KPIs in the Strategic Planning for 2018/19 IDP session. | 2018-06-30 | Planning & Infrastructure Services - Director Planning & Infrastructure and Manager Planning |  | During our performance management system detailed testing the recommendation has not been implemented.
As per inspection of the IDP it was noted that KPIs including the input indicators were not set out in the IDP for each development priority for three years. This was only set in the 2015/16 organizational scorecard which is the SDBIP. This results in non-compliance with MSA sec 41(1)(a).
30 | AG Management Report 2015/2016 - Detailed Finding 14 | AOPO - KPI's - Non-compliance MSA sec.43. | KPIs should be set on the percentage of households with access to basic level of sanitation, electricity and waste removal. | > Management will revise Section C of the IDP and illustrate percentages of people with access to basic services as required by Section 43(1)(a) of the MSA. | 2018-06-30 | Planning & Infrastructure Services - Director Planning & Infrastructure and Manager Planning |  | During our performance management system detailed testing the recommendation has not been implemented.
During the cause of the audit it was noted that the KPIs were not set on the percentage of households with access to basic level of water/sanitation/electricity/solid waste removal. This results in non-compliance with MSA sec43(1)(a) and Local Government: Municipal Planning and Performance Management Regulations (GNR. 796 of 24 August 2001) Reg 10(a).
31 | AG Management Report 2015/2016 - Detailed Finding 15 | AOPO - IDP - Performance targets. | The Municipality should set performance targets with regards to each development priority and objective and KPIs for the year and should be commensurate with available resources and the municipality's capacity. | > Ensure that development priorities and objectives as well as the annual KPIs will be aligned to the realistic budget. | 2018-06-30 | Planning & Infrastructure Services - Director Planning & Infrastructure and Manager Planning
|  | During the course of the audit it was noted that the municipality did not, in terms of its PMS and in accordance with any regulations and guidelines that may be prescribed, set measurable performance targets with regard to each of the development priorities and objectives and KPIs for the financial year. Furthermore, as per inspection of the IDP Performance targets set are not commensurate with available resources and the municipality's capacity. | [5 empty] | We noted per inspection of the PMS quarter 1 report that the recommendation has not been implemented. We confirmed by discussion with Mr Sukazi (Manager Strategic and Political Support) that the scorecards have been updated. We were provided with the updated scorecard on the 08 June 2017 and noted that the recommendation has not been implemented.
32 | AG Management Report 2015/2016 - Detailed Finding 16 | Long outstanding debtors not disconnected & Notice of default of payment not sent monthly to debtors. | The accounting officer should implement controls to monitor the collection of long outstanding debtors' balances owing and to ensure the implementation of the credit control policy. Every effort must be made to ensure that accurate accounts are sent to every debtor on a monthly basis and that the provisions of the debt control policy are implemented in order to collect outstanding debt. Failure to do so will impact the cash flow of the municipality and impact the ability to achieve the targets set in the SDBIP. | > Management will compile a list of top 100 debtors every month; > Management will conduct disconnections immediately; > Management will ensure compliance with the debt control policy | 2018-02-28 | Finance - CFO and Manager Finance |  | During our follow up review we noted through discussion with Mr. S Mngwengwe (CFO) that control implemented is an action plan which has been compiled and indicates the finding, the resolution or action, date of implementation and responsible officials. However the action plan is ongoing and still to be updated. Furthermore, he indicated that a debt impairment policy was drafted. We confirmed by inspection of the debt impairment policy has been drafted. The policy is subject to approval by the municipal council.
|  | During the audit of revenue and receivables it was identified that the services of debtors whose balances have been outstanding for 90 days or longer have not been disconnected. It has also been identified that monthly debtors' statements were not always sent, result incompliance with the credit control policy. | [5 empty] | We also noted through discussion with Mr. S Mngwengwe (CFO) that the finance officials are currently in the process of performing a clean up on the debtors age analysis. Once the age analysis is completed and the correct amounts calculated, thereafter the monthly statements would be forwarded to the relevant debtors.
Other important matters: these matters should be addressed to prevent them from leading to material misstatements of the financial statements or material findings on the performance report and compliance with legislation in future.
Annexure B: Other important matters.
33 | AG Management Report 2015/2016 - Detailed Finding 17 | Fixed asset register control weakness. | Management should amend the asset register accordingly ensuring compliance with the local government capital asset management guideline. | > Asset register will be amended as per recommendation and ensure that compliance with local government capital asset management guideline. | 2018-02-28 | Finance - CFO and Manager SCM |  | During our follow up review we noted by discussion with Mr. S Mngwengwe (CFO) on the 30/05/2017 that the finding is not resolved.
During the assessment performed on the asset register the following deficiencies were noted: > no purchases dates reflected for Land or assets under constructions, there is no title deed number; > the site descriptions for land is not adequate enough to identify the land; > the land on which the landfill site is situated cannot be determined; > residual values have not been indicated for all assets; > the depreciation method and rate used for the assets is not reflected on the asset register for certain categories of assets; > not all assets have barcodes or unique numbers. Assets may be incorrectly valued, resulting in depreciation being incorrectly calculated.
34 | AG Management Report 2015/2016 - Detailed Finding 18 | Non-compliance MFMA section 32 | Management is to amend the report submitted to the MEC of local government to include provisions b and c of section 32(4) of the MFMA. Furthermore these reports must also be submitted to the Auditor General. | > Review reports submitted to MEC of local government and AG, then amend the reports to be submitted in 2018/19. |  | Executive - Accounting Officer |  | During our follow up review we noted by discussion with Mr. S Mngwengwe (CFO) that the recommendation has not been resolved.
During the audit of unauthorised, irregular and fruitless and wasteful expenditure it was noted that section 32(4) reports were not submitted to the Auditor General, furthermore it was noted that the reports did not include the following > whether any person is responsible or under investigation for such unauthorised, irregular or fruitless and wasteful expenditure; > the steps that have been taken to recover or rectify such expenditure and to prevent a recurrence of such expenditure; and > in addition to the above no unauthorised expenditure was disclosed. This results in non-compliance with section 32(4) of the MFMA
35 | AG Management Report 2015/2016 - Detailed Finding 24 | SCM Internal Control deficiencies | Management is to provide reasons as to why the above occurred. Furthermore management must design and implement processes in order to address all strengthen the control environment. |  |  | Finance - Accounting Officer and Manager SCM |  | During our follow up review we noted by discussion with Mr. S Mngwengwe (CFO) that the reason for the exception is due to the SCM Manager post being vacant and poor supervision of staff.
|  | During the audit of procurement the following internal control deficiencies were identified. > Supply Chain Manager post vacant for the entire year; > The SCM policy does not state that no award above R15 000 may be made in terms of this policy to a person whose tax matters have not been declared by the South African Revenue Service to be in order; > The municipality does not have an adequate action plan to address both internal and external findings related to Supply Chain; > Master file amendment forms not maintained. |  | > Submit amended SCM policy to Council for approval. | > 30 Apr 2018; |  |  | During our follow up review we noted through discussion with Mr. S Mngwengwe (CFO) that the control implemented is the SCM policy which has currently been reviewed. We further confirmed that the reviewed policy included the necessary changes required. The policy however is still to be approved. We further confirmed through discussion with the CFO that the action plan will be compiled which is indicated on the auditor's conclusion.
36 | AG Management Report 2015/2016 - Detailed Finding 20 | VAT registration number not on invoice and discrepancies in VAT numbers. | Management is to provide audit with reasons as to why the above occurred. Furthermore management must implement controls to ensure that only invoices with the correct details are accepted. | > Management will perform a population test to check all the invoices received as of July 2017 that they are in line with the SARS requirements of an valid tax invoice. > Management will ensure that all invoices received will be checked and only accepted if they comply with the SARS requirements. | 2018-03-31 | Finance - CFO and Manager Finance |  | During our review of procurement and payments we noted that the finding still remains. Furthermore we noted through discussion with Mr. S Mngwengwe (CFO) that the finding remains unresolved.
During the audit of expenditure discrepancies relating to the VAT were identified, furthermore the municipality's VAT registration number did not appear on some of the invoices. Input VAT may have been incorrectly claimed resulting in SARS interest and penalties being incurred. Furthermore VAT may be misstated owing to submissions.
37 | AG Management Report 2015/2016 - Detailed Finding 21 | Suppliers in the service of the state. | Management is to investigate and report back on the matter. | > Investigate all new suppliers in the database as of July 2018 to date to confirm reliability of declarations. | 2018-02-28 | Finance - CFO and Manager SCM |  | During our follow up review we noted that the recommendation was implemented as the management comment indicates the results of the investigation. With reference to the management comment, we noted that an investigation will be conducted on all new suppliers, however we confirmed through discussion with Mr. S Mngwengwe (CFO) that the investigations has not been done.
During the audit of procurement it was noted that the following were made to suppliers who are in the service of the state who have submitted false declarations: > Isulami Trading and Projects; > Sanzelwe; > Shobane Civil and Cleaning Services; > Barloworld; > Aon South Africa.
38 | AG Management Report 2015/2016 - Detailed Finding 22 | Adequate records not maintained. | Management must provide reasons as to why the abocce mentioned listings are not maintained. Furthermore management should implement controls thereby ensuring proper records are kept for accounting purposes. The Accounting officer should endeavour to ensure that all information requested by the Auditor General is provided timeously. | > Management will ensure that the listed listings as per finding will be developed and maintained. | 2018-02-28 | Finance - CFO and Manager Finance |  | During our follow up review we noted per discussion with Mr. S Mngwengwe (CFO) that there has been no interactions with AG since the report. Therefore we were unable to perform further testing.
During the audit of revenue it was noted that the municipality did not maintain the following listings: > Consumer deposits held at year end as requested; > Listing of disconnections / reconnections as well as new connections for electricity; > Cancelled traffic fines. Non-compliance with section 62 of the MFMA.
39 | AG Management Report 2015/2016 - Detailed Finding 24 | No interest on overdue accounts. | Management must provide reasons for the finding. In addition management is to implement the provisions of section 64(2) and ensure interest is levied on all outstanding accounts. | > Management will finalise the clean up process on the debtors age analysis; > Management will effect the charging of interest on outstanding accounts. | 2018-02-28 | Finance - CFO and Manager Finance |  | During our follow up review we noted through discussion with Mr. S Mngwengwe (CFO) on that the recommendation has not been resolved. Furthermore, the CFO indicated that the finance officials are currently in the process of performing a clean up on the debtors age analysis. Once the age analysis is completed and the correct amounts calculated, thereafter the monthly statements would be forwarded to the relevant debtors. In addition, once the clean up process is performed, the interest would be calculated on overdue accounts.
In terms of section 64(2)(g) of the MFMA, the accounting officer must take all reasonable steps to ensure that the municipality charges interest on arrears, except where the council has granted exemptions in accordance with its budget related policies and within a prescribed framework. Contrary to the requirements of the MFMA the municipality does not charge interest on arrear accounts.
40 | AG Management Report 2015/2016 - Detailed Finding 25 | Vat payments not made timeously. | Management should implement controls in order to ensure that VAT payments are made timeously. | >Management will ensure that controls will be implemented to pay VAT payments on time; |  |  |  | During our follow up review, we noted through discussion with Mr. S Mngwengwe (CFO) that the VAT payments cannot be made timeously as the Municipality is currently facing financial constraints. The recommendation has not been implemented.
During the audit of VAT it was identified that the payments were not made timeously for the months of October 2015, April, May and June 2016.
41 | AG Management Report 2015/2016 - Detailed Finding 26 | Budget - Non-compliance. | Management is to provide audit with reasons as to why the above occurred, in addition management is to implement stringent internal controls thereby ensuring compliance with all related legislation. | > Management will develop a quarterly reporting checklist that will be adhered to and monitored on a monthly basis; > Management will ensure that all reports as required by section 22 of the MFMA will be submitted. | > 28 Feb 2018; > Ongoing | Finance - CFO and Manager Finance |  | During our follow up review, we noted through discussion with Mr. S Mngwengwe (CFO) that the recommendations and finding has not been implemented.
During the audit of budget compliance it was noted that the municipality did not submit the following reports to Provincial Treasury: > age creditors audited - 2014/15; > age debtors audited - 2014/15; > financial position - 2014/15; > capital acquisition - 2014/15; > asset management audited - 2014/15; > cash flow audited - 2014/15; > financial performance audited - 2014/15; > asset management budgeted - 2015/16; > cash flow budgeted - 2015/16. Non-compliance with section 22(b) of the MFMA.
42 | AG Management Report 2015/2016 - Detailed Finding 27 | Quarterly Returns - Non-compliance. | Management is to provide audit with reasons as to why the above occurred, in addition management is to implement stringent internal controls thereby ensuring compliance with all related legislation. | > Management will develop a quarterly reporting checklist that will be adhered to and monitored on a monthly basis; > Management will ensure that all reports as required by section 74 of the MFMA will be submitted. | > Ongoing | Finance - CFO and Manager Finance |  | During our follow up review, we noted through discussion with Mr. S Mngwengwe (CFO) that the recommendations and finding has not been implemented.
During the audit of compliance it was noted that the municipality did not submit the quarter 3 and quarter 4 Investment monitoring reports. Non-compliance with Section 74(1) of the MFMA.
43 | AG Management Report 2015/2016 - Detailed Finding 28 | Conditional Grants Return Forms - Non-compliance. | Management is to provide audit with reasons as to why the above occurred, in addition management is to implement stringent internal controls thereby ensuring compliance with all related legislation. | > Management will develop a quarterly reporting checklist that will be adhered to and monitored on a monthly basis; > Management will ensure that all reports as required by section 71 of the MFMA will be submitted. | > Ongoing | Finance - CFO and Manager Finance |  | During our follow up review, we noted through discussion with Mr. S Mngwengwe (CFO) that the recommendations and finding has not been implemented.
During the audit of budget compliance it was noted that the municipality did not submit the following reports to Provincial Treasury: > Finance Management Grant - June 2016; > Integrated National Electricification Programme - June 2016; > Municipal Infrastructure Grant - June 2016; > Municipal Systems Improvement Programme Grant - June 2016; > Expanded Public Works Programme Grant - June 2016. Non-compliance with section 71 of the MFMA.
44 | AG Management Report 2015/2016 - Detailed Finding 29 | Service level agreements not in place for electricity connections. | Management should ensure that all new connections are supported by valid service contracts in compliance with the credit control policy. | > Management will ensure that all new electricity connections will be supported by valid service contracts. | 2018-06-30 | Finance - CFO and Manager Finance |  | During our follow up review we noted by discussion with Mr. S Mngwengwe (CFO) that new connections have signed service level agreements. We confirmed per inspection of the listing of new connections for the period under review that there was only one new connection i.e. Shoprite Checkers. We were therefore unable to select a sample of 5 for our testing.
|  | During the audit of revenue and receivables it was noted that the municipality does not ensure that valid agreements are in place for all electricity connections. Upon request valid contracts for the following consumer debtors could not be provided by the municipality: > PEP Stores, Anesco CC, AFGRI Operations Pty Ltd, Paulpietersburg Spar, ABSA Bank Limited, Vodacom Pty Ltd, Erlo Construction CC, Mondi Ltd, Edumbe Community Health Centre, Colefax Trading (Pty) Ltd (KFC), Dumbe Nursery, Provisiale Administrasie, Paulpietersburg Country, Housewives Market, Paulpietersburg Timbers Pty Ltd, First Rand Bank, Dumbe Funerals, Van Rooyen, The Regional Manager, SA Post Office, Shoprite Checkers (Pty) Ltd, Dumbe Municipality, Builders City, Ntshangase. | [5 empty] | We further confirmed that the agreement for municipal services for Shoprite Checkers state the following information: 1. Effective date: 01/03/2017; 2. Account number: 7703201; 3. Further states the terms and conditions and that "the applicant agrees that all payments on the consumer account will be allocated in the order specified in the Councils Control Policy, a copy of which is available for scrutiny at the cashiers office.
45 | AG Management Report 2015/2016 - Detailed Finding 30 | Uploading of the 2015/16 Mid-Year Budget and Performance Assessment Reports onto municipal websites. | Management is to provide audit with reasons as to why the above occurred, in addition management is to implement stringent internal controls thereby ensuring compliance with all related legislation. | > Management will ensure that compliance with section 75 of the MFMA is adhered to. | Ongoing | > Finance - CFO; > Corporate & Community Services - Director Corporate & Community |  | During our follow up review we noted by inspection of the Municipal website that the following file was uploaded: KZN261 Annual Budget A1 Schedule - version 2016-2017. Upon inspection of the actual file which was uploaded we noted that it was the 2015/2016 budget. We confirmed through discussion with Mr Mathabela (IT Manager) the incorrect budget was uploaded.
|  | In terms of section 75(2) of the MFMA a municipality must place their Midyear Budget and Performance Assessment reports within 5 days after its tabling in the council or on the date on which it must be made public, whichever occurs first. It was noted during the audit that the municipality did not upload their 2015/16 Mid-Year Budget and Performance Assessments Reports on their municipal website within the legislated time frame. Non-compliance with Regulation 34(1) of the MBRR as well as Section 75(2) of the MFMA. | [5 empty] | Furthermore, we noted by inspection of Council resolution dated 18 January 2017 that the mid-year budget and performance assessments were noted by Council. We confirmed by inspection of the website that the upload reference date for the performance assessments was the 3 February 2017. Therefore, we confirm the information was not uploaded within 5 days after being tabled at Council as per section 75(2) on the MFMA.
46 | AG Management Report 2015/2016 - Detailed Finding 31 | 2015/16 Adjustment Budget Process. | Management is to provide audit with reasons as to why the above occurred, in addition management is to implement stringent internal controls thereby ensuring compliance with all related legislation. | > Management will ensure compliance with Regulation 23 of the MBRR. | 2018-03-15 | > Executive - Accounting Officer; > Finance - CFO |  | During our follow up review, we noted by discussion with Mr. S Mngwengwe (CFO) that the adjustment budget was concluded late for the current financial year as well.
When the annual budget has been adjusted, the municipality should take table their Adjustments Budget to Council at any time after the Mid-Year Budget and Performance Assessment Report has been tabled in Council but not later than 28 February of the current year as required by Regulation 23(1) of the MBRR. During the audit of budget compliance it was noted that the municipality did not submit the adjustment budget within the legislated time frame. This results in non-compliance with Regulation 23(1) of the MBRR.
47 | AG Management Report 2015/2016 - Detailed Finding 32 | 2015/16 MFMA Competency Level Return (S1 and S2) | Management is to provide audit with reasons as to why the above occurred, in addition management is to implement stringent internal controls thereby ensuring compliance with all related legislation. |  | 2018-02-28 | Finance - CFO and Manager Finance |  | We noted that the recommendation has not been implemented.
Section 14(1) of the Municipal Regulations on Minimum Competency Levels states that the municipal manager of the municipality and chief executive officer of a municipal entity must monitor the compliance with the prescribed minimum competency levels of financial and supply chain management officials. Section 14(2) states further that such information must be reported to National Treasury and relevant Provincial Treasury by 30 January and 30 July of each year.
It was noted during the audit that the municipality did not submit the minimum competency levels report for the first half of the 2015/16 financial year which was due on the 30th January 2016. This results in non-compliance with Section 14(1) of the MFMA.
48 | AG Management Report 2015/2016 - Detailed Finding 40 | Risk Register. | Management is to ensure that cognisance is taken of the above listed risks in its next risk assessment. | > Management will ensure that the risks listed as per the finding will be added to the risk register. > Management will perform review on the risk register | 2018-02-28 | Executive - Acting Manager PMS and Risk
|  | Section 62(1)(c)(i) of the MFMA states that the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps to ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control. | [5 empty] | During our review of internal audit we noted per discussion with Mrs L Masondo (Senior Risk Officer)
During the assessment of the municipality's risk register it was noted that the following risks were not considered: 1. Risk associated with major suppliers and contractors; 2. Risks resulting from its interactions with various other government entities and parties outside the government; 3. Risks resulting from downsizing of entity operations and personnel considered; 4. Risks posed by disruption of information systems processing and the extent to which backup systems are available and can be implemented. 5. Risks resulting from the lack of qualifications of personnel hired or the extent to which they have been trained or not trained. 6. Risks resulting from heavy reliance on contractors or other related parties to perform critical entity operations identified. 7. Risks resulting from unusual employee access to vulnerable assets. 8. Human capital-related risks, such as the inability to provide succession planning and retain key personnel who can affect the ability of the entity or programme activity to function effectively, and the inadequacy of compensation and benefit programmes to keep the entity competitive with the private sector for labour. 9. Risks indicated by a history of unauthorised, irregular and fruitless and wasteful expenditure, or other statutory non-compliance. 10. Risks inherent to the nature of its mission or to the significance and complexity of any specific programmes or activities it undertakes. Non-compliance with section 62 of the MFMA.