ÉDUMBE Municipality

MID-TERM PERFORMANCE REPORT

2017/2018 Financial Year

TABLE OF CONTENTS

| NO. | CONTENT |
| --- | --- |
| 1. | Massage from the Municipal Manager |
| 2. | Background to Municipal Performance Reporting |
| 3. | The Municipal Reporting process |
| 4. | Limitations in Municipal Reporting |
| 5. | Summary of Municipal Performance |
| 6. | Performance of External Service Providers |
| 7. | Municipal Grant Finding 2017/2018 Financial year |
| 8. | Expenditure Patterns on Capital Projects |
| 9. | Performance Management Processes |
| 10. | Performance Assessment |
|  | 10.1. Quarter 1 Assessment |
| 11. | Steps on Managing Performance at Organisational level |
| 12. | Background to Municipal Scorecard / SDBIP ANNEXURE 1. MUNICIPAL MID-TERM REPORT ON SERVICE DELIVERY TARGETS (TARGETS VS ACTUAL ACHIEVEMENTS) |
| 13. | Performance Highlights on each Key Performance Area (KPA) |
|  | 13.1. Municipal Transformation and Institutional Development 13.2. Basic Service Delivery and Infrastructure Development 13.3. Local Economic Development 13.4. Good Governance, Public Participation and Ward Committee Systems 13.5. Financial Viability and Finance Management 13.6. Cross Cutting Interventions |
| 14. | State of Readiness on National Disaster Implementation by the Municipality |
| 15. | Conclusion |
| 16. | Recommendations |
| 17. | Acronyms |

2. MESSAGE FROM THE MUNICIPAL MANAGER

As the Accounting Officer of eDumbe Municipality, I am taking this opportunity to express my sincere gratitude thanks to Honourable Mayor S.J. Mavuso,  Executive Committee Members and the whole Council for trusting me and my Management team with the responsibility of being the agency of change in this municipality. Since we started with our responsibilities as Municipal management team, we have committed ourselves in working as one team with one vision and mission.

Section 72 of the Municipal Finance Management Act, No 56 of 2003, stipulates that the Accounting Officer of the Municipality must assess performance of the Municipality during the first half of the financial year, taking into account

(ii) the Municipality’s service delivery performance during the first half of the financial year, and the service delivery targets and performance indicators set in the SDBIP

I hereby present the report as legislated and have taken into account all the required areas to indicate the whole picture in terms of the Municipal performance.  I commit to continously monitor, evaluate and review the performance of the Municipality on regular basis to ensure the Municipal objectives are met.

I thank you

___________________________

MR MP KHATHIDE

MUNICIPAL MANAGER

2.  BACKGROUND TO MUNICIPAL PERFORMANCE REPORTING

The Mid-Term Performance Report is compiled in terms of the legislative requirements, Chapter 6 of the Municipal Systems Act, 32 of 2000 and Chapter 12 of the Municipal Finance Management Act, 56 of 2003.  The Municipal Systems Act prescribes the role of each sphere of government in the municipal performance reporting.

2.1  Purpose of the Report

The main purpose of this report is to account to MEC for Local Government, Provincial legislature, NCOP, Minister of Cooperative Governance and Traditional Affairs, National Treasury, Auditor-General and to the citizens of South Africa on progress being made by municipalities towards achieving the mid-term goals of “a better life for all”. Furthermore, the report is a key performance report to the communities and other stakeholders in keeping with the principles of transparency and accountability of government to the citizens. It subscribes to the South African developmental nature of participatory democracy and cooperative governance and responds to the principles of the Constitution, Batho Pele, White Paper on Local Government, MSA and the MFMA

2.2  The Assessment Process and the Methodology followed in Compiling the Report

According to the provisions of the Municipal Systems Act, 32 of 2000, municipalities must monitor and measure the progress of their performance by preparing quarterly and mid-year performance reports, in terms of Chapter 6 of the MSA, on performance management systems. These quarterly and mid-year reports make up the municipalities’ annual performance reports (Section 46 report), which are submitted to the Auditor-General, together with the financial statements, for auditing. After adoption of the audited performance report by the municipal council, it must then be submitted to the MEC for Local Government.

2.3  Compilation and Structure of the Report

The report should present the status of current progress on mid-term performance which has been conducted.  This is followed by a brief assessment attached as  Annexure 1 showing the outcome on the Performance of each Key Performance Indicator (KPI), POE, Comments and Corrective Measures on KPI’s not Achieved.

3.  THE MUNICIPAL REPORTING PROCESS

3.1.  SECTION 72 OF THE MUNICIPAL FINANCE MANAGEMENT ACT, 56 OF           2003

The Accounting Officer of a Municipality must by 25 January of each year:

- Assess the performance of the Municipality during the first half of the financial year, taking into account:

(ii) the Municipality’s service delivery performance during the first half of the financial year, and the service delivery targets and performance indicators set in the service delivery and budget implementation plan.

3.2 CHAPTER 12 OF THE MUNICIPAL FINANCE MANAGEMENT ACT No. 56 of 2003

The Mid-Term Performance report must form part of the municipality’s annual report

terms of chapter 12 of the Municipal Finance Management Act

3.3. SECTION 121 OF THE MUNICIPAL FINANCE MANAGEMENT ACT (MFMA) 56 OF 2003, REQUIRES THAT:

(1) 	Every municipality and every entity must for each financial year prepare an annual report.  The Council of a municipality must within nine months after the end of a financial year deal with the annual report of the municipality and of any municipal entity under the municipality’s sole or shared control in accordance with section 129.

3.4.  SECTION 129 OF THE MUNICIPAL FINANCE MANAGEMENT ACT (MFMA) 56 OF 2003, REQUIRES THAT:

- The Council of a municipality must consider the annual report of the municipality and of any municipal entity under the municipality’s sole or shared control, and by no later than two months from the date on which the annual report was tabled in the council in terms of section 127, adopt an oversight report containing the council’s comments on the annual report, which must include a statement whether the council:

  - has approved the annual report with or without reservations;

  - has rejected the annual report; or

  - has referred the annual report back for revision of those components that can be revised.

4.  LIMITATIONS IN MUNICIPAL REPORTING

Outline the limitations in compilation of the report.

Municipality’s Demographic Information

5. SUMMARY OF MUNICIPAL PERFORMANCE (2017/2018)

The information provided on the table below indicates the overall mid-term performance review of the Municipality during 2017/2018 financial year. The report is compiled in line with the 6 national KPAs and is the focus of the Municipal Systems Act Section 46

Table 1

| Total number of Targets | 136 |
| --- | --- |
| Total Number of Q2 Targets Achieved | 44 (32%) |
| Total Number of Q2 Targets not Achieved | 62 (46%) |
| Number of Targets not planned for Q2 ( in Progress) | 30 (22.%) |

6.  PERFORMANCE OF EXTERNAL SERVICE PROVIDERS

The monitoring of the service provider performance is ensured through the signing of the Service Level Agreement. It is currently being done by user departments due to the non availability of the legal Service Unit within the Municipality. The end user department provides monthly reports to the SCM unit and Office of the Municipal Manager through PMS Unit of the Service providers about the Performance of the Service Providers.  Necessary Action is taken to those failing to perform, i.e. issuing of letters of intent for termination, imposing penalties.

| Good (G) | The service has been provided at acceptable standards and within the time frames stipulated in the SLA/Contract |
| --- | --- |
| Satisfactory (S) | The service has been provided at acceptable standards and outside of the timeframes stipulated in the SLA/Contract |
| Poor (P) | The service has been provided below acceptable standards |

The following are the service providers engaged in each business unit during the 2015/2016 financial year.

| BID NO. | PROJECT DESCRIPTION | SERVICE PROVIDER AWARDED TO | CONTRACT AMOUNT | FUNDER | DATE OF AWARD | ESTIMATED END DATE | CHALLENGES | ASSESSMENT OF SERVICE PROVIDER’S PERFORMANCE | MEASURES TAKEN FOR POOR PER |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EDUMT01/2017/18 | Construction of Tholakele Access Roads | Ethala Construction | R1 537 768.91 | MIG | 02 Oct 2017 | 02 Feb 2018 | Service Provider’s performance is good. But due to inclement weather terrain and space between household and the road, the road is affected by erosion. | Good | Negotiations are in progress as it will have financial implications |
| EDUMT02/2017/18 | Construction of Ezingudeni Pedestrian Bridge | Khanyisa Civils & General Maintenance cc | R2 697 686.31 | MIG | 19 Sep 2017 | 19 Mar 2018 |  | Good |  |
| EDUMT03/2017/18 | Impucuko Sportsfield | Vezokungcono Yimpie JV | R2 558 787.00 | MIG | 22 Sep 2017 | 22 Mar 2018 | Slow progress by the Contractor | Satisfactory | PMU section is monitoring the project closely |
| EDUMT06/2017/18 | Construction of Mangosuthu Combi Court | Consa Trading Enterprise | R1 683 932.02 | MIG | 26 Sep 2017 | 26 Mar 2018 |  | Good |  |
| EDUMT07/2017/18 | Construction of Ophuzane Combi Court | SMM Trading and Projects (PTY) LTD | R1 728 181.29 | MIG | 23 Oct 2017 | 23 Feb 2018 | Slow progress by the Contractor | Satisfactorily | The Municipality has issued letters of intent to terminate |
| EDUMT04/2017/18 | Fencing of eDumbe Cemetery | Dlabandlondlo Deezlo JV | R1 7364 428.50 | MIG | The project was put on hold due to internal issues | Will advice once an appointment is done | Community unrest | Poor | The Secttion is awaiting final approval to utilise funds for another project. |
| EDUMPRO02/2016/17 | Upgrade of Infrastructure | Contractor: Thando Electrical Consultant: Boston Ink Project Engineers | R6 000 000 | Department of Energy | 15 Nov 2017 | 30 June 2018 |  | Good |  |
| EDUMPRO02/2016/17 | Lenjane Electrification | Contractor: Emagameni Electric Consultant: Siyethemba Consulting Engineers | R4 390 000 | Department of Energy | 01 March 2018 | 30 June 2018 |  | Satisfactory | Notice of underperperformance have been served to the Consultant. |
| EDUMPRO02/2016/17 | Enkembeni Phase 4 | Contractor: Megelec Construction & Prime Construction Consultant: BTMN Consulting Engineers | R7 000 000 | Department of Energy | 19 Jan 2018 | 30 June 2018 | This is due to non performance by Consultant. | Poor | Notice of underperperformance have been served to the Consultant. |
| EDUMPRO02/2016/17 | Obivane/Nkonkotho Electrification | Contractor: Not appointed yet Consultant: Sibgem Consulting Engineers | R7 500 000 | Department of Energy | 01 Mar 2018 | 30 June 2018 | This is due to non performance by Consultant. | Poor | Notice of underperperformance have been served to the Consultant. |
| FWPQ 03/2017/18 | Supply and Delivery of Refuse Bags | Lwandle Lwethu General Dealer | R110 000 | Own Funding | 06 Sep 2017 | Once off service | None | Good |  |
| FWPQ 02/2016/17 | Transport for Umkhosi Wohlanga | KP Multipurpose Dealer | R74 000 | Own Funding | 06 Sep 2017 | Once off service | None | Good |  |
| EDUMPRO 01/2017/18 | Development of Wall to Wall Scheme | Black Cubans Consulting | R977 040 | CoGTA | 19 Sep 2017 | N/A | None | Good |  |

7.  MUNICIPAL GRANT FUNDING 2017/2018 FINANCIAL YEAR

| Grant Name | Date in which the Grant was received | Amount Received | Opening Balance | Conditions of the Grant (Briefly) | Amount Spent as of 31 Dec 2017 | Balance Left as at 31 Dec 2017 | Reason for not Spending/ Over Spending |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Finance Management Grant | 26/07/2017 | R 1 900 000 | R 0.00 | N/A | R 1 119 465.62 | R 780 544.38 | N/A |
| Art and Culture | 09/10/2017 | R 1 118 000 | R 435 042.46 | N/A | R 522 860.38 | R 1 030 182.08 | N/A |
| Energy | 27/10/2017 | R10 000 000 | R28 649.96 | N/A | R12 980 857.90 | R7 019 142.10 | N/A |
|  | 08/12/2017 | R10 000 000 |  |  |  |  |  |
|  | TOTAL RECEIVED | R20 000 000 |  |  |  |  |  |
| Municipal Infrastructure Grant | 17/07/2017 | R 5 000 000 | R494 112.94 |  | R9 337 369.02 | R5 662 630.98 | N/A |
|  | 08/12/2017 | R10 000 000 |  |  |  |  |  |
|  | TOTAL RECEIVED | R15 000 000 |  |  |  |  |  |
| CoGTA Massification Grant | 31/12/2017 | R200 000 | R23 361.11 | N/A | R195 000 | R23 361.11 | N/A |
| E P W P Integrated Grant | 15/08/2017 | R348 000 | R0.00 | N/A | R476 418.73 | R496 581.27 | N/A |
|  | 15/12/2017 | R625 000 |  |  |  |  |  |
|  | TOTAL RECEIVED | R973 000 |  |  |  |  |  |
| TOTAL GRANTS RECEIVED |  | R39 191 000 |  |  |  |  |  |

8.  EXPENDITURE PATTERNS ON EACH CAPITAL PROJECT

| Project Name | Ward in which the project is implemented | Progress on site | Contract Value | Expenditure as of 30 June 2017 | Percentage of work done as of 30 June 2017 | Balance left after 30 June 2017 | Over Spent Amount | Reason for over/under spending |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | R0.00 | R0.00 | % | R0.00 | R0.00 |  |
| Construction of Tholakele Access Roads | Ward 5 | The project is on Practical Completion | R2 447 078.40 | R2 101 191.83 | 95% |  | R 0,00 | N/A |
| Construction of Ezingudeni Pedestrian Bridge | Ward 1 | Foundations are completed, Contractor has ordered and waiting for the steel | R3 582 271.00 | R1 714 989.94 | 95% |  | R 0,00 | N/A |
| Construction of Impucuko Sportfield | Ward 7 | Levelling of sportfield and change rooms is currently in progress | R2 877 400 | R1 930 891.34 | 40% | R 0,00 | R 0,00 | N/A |
| Construction of Mangosuthu Combi Court | Ward 2 | The Contractor is busy with ablution work | R2 000 000 | R938 128.56 | 40% |  | R 0.00 | N/A |
| Construction of Ophuzane Combi Court | Ward 8 | The platform for combi court is complete | R2 000 000 | R440 754.00 | 35% |  | R 0.00 | N/A |
| Fencing of eDumbe Cementery | Ward 3 | The project is on hold due to internal issues | R2 000 000 | R165 956.40 | 0% | R 0,00 | R 0,00 | N/A |

9.  PERFORMANCE MANAGEMENT PROCESSES

In terms of Chapter 6, of the Municipal Systems Act. No 32 of 2000, the 2001 Municipal Planning and Performance Management Regulations (2001) were published, setting out the requirements for a municipal PMS. The Regulations also contain the general indicators prescribed by the Minister responsible for local government and have been attached as Annexure 1in our PMS Framework. A further set of Regulations were published in 2006 and they deal with Performance Management for Municipal Managers and managers that are directly accountable to Municipal Managers.

The performance Management System is located within a legislative and policy framework and is influenced by, but not limited to the following:

- The Constitution of the Republic of South Africa, Act 108 of 1996.

- The White Paper on Local Government,1998

- The Municipal Systems Act 32 of 2000

- The Municipal Planning and Performance Regulations 2001

- The Municipal Finance Management Act 56 of 2003

- Monitoring and Evaluation Policy Framework and Procedure Manual

The major PMS policy instruments is the 1998 White Paper on Local Government supported by the Batho Pele principles, and was given legal stature through the adoption of the Local Government: Municipal Systems Act in 2000 (Act 32 of 2000). The said Act requires all municipalities to:

- Develop a performance management system

- Set targets and monitor and review the performance of the Municipality based on indicators linked to their Integrated Development Plan (IDP)

- Publish an annual performance report on the performance of the Municipality forming part of its annual report as per the Municipal Finance Management Act (MFMA).

- Incorporate and report on a set of general (sometimes also referred to as national) indicators prescribed by the Minister responsible for local government

- Conduct, on a continuous basis, an internal audit of all performance measures

- Have their annual performance report audited by the Auditor-General

- Involve the community in setting indicators and targets and reviewing municipal performance

9.  MONITORING, EVALUATION AND REVIEW

The Municipality has got PMS Framework that is aligned to the legislation and Integrated Development Plan .The Framework is best suited to the circumstances of the municipality and it was approved by the Council. Monthly reports are submitted by senior managers for all activities carried out in that particular month and at the end of every quarter. Senior managers were expected to prepare and submit quarterly performance reports for monitoring and evaluation of actual performance against set targets.

Quarterly reports have been submitted to Council, Internal Auditors, MPAC and Audi Committee for assessment, auditing and evaluation. Assessment of section 54/56 employees has been conducted in quarter 1, and PMS Section is currently busy with processes of conducting Q2 Assessment. The Municipal Manager and the Managers that are directly accountable to the Municipal Managers have signed the performance agreements. Council Committees are fully functional and effective in performing their delegated task

10.  PERFORMANCE ASSESSMENT

It is reported that Quarter 1 assessments for 2017/2018 was performed as legislated. Bonuses for 2016/2017 Assessment were not paid to Senior Managers and Municipal Manager due to financial Constraints.

10.1.  QUARTER 1. ASSESSMENT

The Assessment was conducted only to the following section 54/56 employees

| No | Position held | Period Covered for Q1 |
| --- | --- | --- |
| 1. | Municipal Manager (Acting) | 1 July – 30 September 2017 |
| 2. | Chief Financial Officer | 1 July – 30 September 2017 |
| 3. | Director Infrastructure and Planning | 1 July – 30 September 2017 |
| 4. | Director Corporate and Community Services | Post was still vacant |

11.  STEPS FOR MANAGING PERFORMANCE AT ORGANIZATIONAL LEVEL

2. Performance Monitoring

6. Performance Review

1. Performance Planning

3. Performance Measurement

4. Performance

Analysis

5. Performance

Reporting

Organisational Performance Management

12. BACKGROUND TO MUNICIPAL SCORECARD/SDBIP

In terms of MSA (1) (a) A municipality must set key performance indicators ,including input indicators ,output iand outcome indicators,in respect of each of the developmental priorities and objectives referred to in section 26 (c) of the Act.

(b) A key performance indicator must be measurable,relevant,objective and precise.

(2) In setting key performance indicators ,a municipality must ensure that :

- Communities are involved.

The Municipal Scorecard reflects the 6 National KPAs and local priorities .The Scorecard enables a wider assessment of how the municipality is performing.

The performance report is based on measures included within the Municipal Screcard and incoperates priority measures selected from the IDP

These targets were reviewed and updated by Council at Council meeting

We also have legislative framework which provides for performance management at various levels in a municipality including Organizational (sometimes also referred to as municipal, corporate or strategic level), departmental (also referred to as services, operational or section/team level) and lastly, individual level.

At Organizational level, the five-year IDP forms the basis for performance management, whereas at operational level the annual SDBIP /Scorecard forms basis.  The performance measures associated with the IDP have a long-term focus, whereas those associated with the SDBIP are short-term and focus on reviewing the progress made in implementing the current budget and achieving the annual service delivery targets.

At Departmental level, the measures are captured in the SDBIPs /Scorecards of the various departments that operate within the municipality. Performance management should occur at the various levels and relate to one another, as required by the 2001 Municipal Planning and Performance Regulations through cascading performance measures from organisational to departmental level, both the IDP and the SDBIP/Scorecard eventually link with individual performance management. Regarding performance management at individual level, the MFMA specifically requires that the annual performance agreements of Section 57 Managers must be linked to the SDBIP and the measurable performance objectives approved with the budget.

MUNICIPAL MID-TERM REPORT ON SERVICE DELIVERY TARGETS AND PERFORMANCE

(TARGETS VS ACTUAL ACHIEVEMENTS)

ATTACHED

ANNEXURE 1

|  |  |  | MID YEAR REPORT ON SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q 1 | Q 2 | 1/2 Year |  |  |  |  |
|  |  | Strategic Objective | Strategy | Strategic Action/ Project | Key Performance Indicator (KPI) | Unit of Measure | Annual Target (Baseline) | Budget | Projected Target | Projected Target | Mid year Projected Target | Actual Achieved Performance (Mid year) | Portfolio of evidence | Comments | Corrective measres |
| KPA 1: MUNICIPAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI 1 | Cor 1 | To improve institutional capacity through policy development and enforcement | Development, review and implemention of policies | Implement approved HR policies | Reviewed 13 HR Policies by 30 June 2018 | Number of HR Policies reviewed. | Reviewed 13 HR Policies by 30 June 2018 | R 0.00 | X | X | X | In progress | None | Target planned for Q3 |  |
| KPI 2 | Cor 2 |  | Development, review and implemention of by-laws | Gazetting By-laws | 4 Gazetted Municipal By-laws | Number of Gazetted by-laws. | 4 Gazetted Municipal By-laws by 31 Dec 2017 | R 55 000.00 | 1 st Draft | Final Drft | Final Drft | Not Achieved | None | Target not achieved, due to cash flow issues however one By-law was gazetted for Property Rates | Municipality to source funds for gazetting |
| KPI 3 | Cor 3 |  | Review and implementation of organogram | Implement organogram | Implemented approved organogram | Date of Adoption | Implemented organogram by 30 June 2018 | R 0.00 | Implement Organogram | Implement Organogram | Implement Organogram | In progress |  |  | Revise SDBIP to rephrase the Indicator |
| KPI 4 | Cor 4 |  | Review and implementation of WSP | Implement WSP | Implemented WSP | Date of Adoption | Implemented WSP by 31 April 2018 | R 0.00 | X | X | X | In progress | None | Target planned for Q3 |  |
| KPI 5 | Cor 5 |  | Review and implementation of WSP | Implement WSP | Implemented WSP | % of Implementation | 100% Implementation of WSP Budget by April 2018 | R 0.00 | Implement | Implement | Implement | In progress | None | Target planned for Q3 |  |
| KPI 6 | Cor 6 |  | Review and implementation of Employment Equity Plan (EEP) | Implement EEP | Submitted EEP to DoL | Date of submission | Submitted EEP to DoL by 31 January 2018 | R 0.00 | X | X | X | In progress | None | Target planned for Q3 |  |
| KPI 7 | Cor 7 |  | OHS implementation | Purchase protective clothing | Implemented OHS Strategy | Date of Adoption | Protective clothing delivered by 31 September 2017 | R 300 000.00 | Protective clothing delivered by 31 September 2017 | X | Protective clothing delivered by 31 September 2017 | Not Achieved | None | Process was stopped due to financial issues | Review SDBIP |
| KPI 8 | Cor 8 |  |  | Servicing OHS equipment | Seviced OHS Equipments | Date of Adoption | Serviced OHS Equipments by 31 December 2017 | R 60 000.00 | X | Appointment letter issued by 31 Dec 2017 | Appointment letter issued by 31 Dec 2017 | Not Achieved | None |  | Review SDBIP |
| KIP 9 | Cor 9 |  |  | Medical screening | Conducted Medical Screening | Date of Adoption | Conducted Medical Screening by 31 March 2018 | R 20 000.00 | X | X | X | Target in progress | None | Target planned for Q3 | Target to be reviewed as it is not budgeted for |
| KPI 10 | Cor 10 |  | Review and implemention of ICT Government Framework | Implement approved ICT policies | Impemented approved ICT policies | Date of Adoption | Implemented ICT policies by 30 June 2018 | R 0.00 | X | Implement | Implement | Archieved | Council Resolution |  |  |
| KPI 11 | Cor 11 |  |  | Perform information backups | 12 Backups and Registers performed | Number of Backups and Register performed | 12 Backups and Registers performed by 30 June 2018 | R 0.00 | 3 Backups and Registers performed | 3 Backups and Registers performed | 6 Backups and Registers performed | Achieved | Back-ups Reports |  |  |
| KPI 12 | Cor 12 |  |  | Perform information restores | 4 Restores and registers performed | Number of Restores and Register performed | 4 Restores and Register performed by 30 June 2018 | R 0.00 | 1 Restore and Register performed | 1 Restore and Register performed | 2 Restores and Register performed | Achieved | Restore Database reports |  |  |
| KPI 13 | Cor 13 |  |  | Review Logs | 12 Logs Reviews | Number of Reviews of Logs | 12 Logs Reviews by 30 June 2018 | R 0.00 | 3 Logs Reviewed | 3 Logs Reviewed | 6 Logs Reviewed | Achieved | VIP and Pastel Syestems Access Logs Reports |  |  |
| KPI 14 | Cor 14 |  | Improving the ICT infrastructure | Implement Disaster Recovery Plan and Business Continuity Plan | Implemented DRP & BCP test | Date of Adoption | Implemented DRP & BCP test by 31 December 2017 | R 0.00 | X | Implemented DRP & BCP test by 31 December 2017 | Implement | Not Achieved | None | Computers for Disaster Recovery Plan were purchased due to financial issues | Budget Provision to be prioritised next financial year |
| KPI 15 | Cor 15 |  |  | Appoint Service Provider to provide ICT Equipment | Purchased Hardware equipment s | Number of ICT Equipment | Purchased Hardware equipment 30 September 2017 | R 150 000.00 | Purchased Hardware equipment 30 September 2017 | X | Purchased Hardware equipment 30 September 2017 | Not Achieved | None | SCM processes were discontinued due to non availability of funds | Budget Provision to be prioritised next financial year |
| KPI 16 | Cor 16 |  |  |  | Purchased Software licenses | Number of Software licenses. | Purchased Software licenses by 31 December 2017 | R 150 000.00 | X | Purchased Software licenses by 31 December 2017 | Purchased Software licenses by 31 December 2017 | Not Achieved | None | Due to Financial issues | Make Budget Provision next financial years |
| KPI 17 | Cor 17 |  |  |  | Installed Antivirus software | Date of Agreement | Installed Antivirus software by 31 December 2017 | R 25 000.00 | X | Installed Antivirus software by 31 December 2017 | Installed Antivirus software by 31 December 2017 | Target in progress | Requisition and purchase order | SCM processes are ongoing but not finalised |  |
| KPI 18 | Mun 1 |  | Review and implementation of PMS | Review PMS Framework | Reviewed PMS framework | Date of Adoption | Reviewed PMS framework by 30 June 2018 | R 0.00 | X | X | X | Target in progress | Darft PMS Framework | Draft Framework in place awaiting for Council Approval |  |
| KPI 19 | Mun 2 |  |  | Review PMS Policy | Reviewed PMS Policy | Date of Adoption | Reviewed PMS policy by 30 June 2018 | R 0.00 | X | X | X | Target in progress | Agenda for Dec Counci Meetingl | PMS policy awaiting approval by Council |  |
| KPI 20 | Mun 3 |  |  | Developed SDBIP & Organizational Scorecard | Developed SDBIP & Organizational Scorecard | Date of Adoption | Developed SDBIP & Organizational Scorecard by 30 June 2018 | R 5 000.00 | X | X | X | Achieved | Council Resolution |  |  |
| KPI 21 | Mun 4 |  |  | Performance agreement | Signed performance agreements of S56 | Number of signed performance agreement. | 4 Signed performance agreements by 31 August 2017 | R 5 000.00 | 4 Signed performance agreements by 31 August 2017 | X | 4 Signed performance agreements by 31 August 2017 | Achieved | Signed Agreements |  |  |
| KPI 22 | Mun 5 |  |  | Annual report | Completed Annual report | Date of Completion | Completed Annual report by 31 January 2018 | R 20 848.00 | X | X | X | Target in progress | Draft Annual report | Target planned for Q3, however darft report is in place |  |
| KPI 23 | Mun 6 |  |  | Annual performance report | Completed Annual performance report | Date of Completion | Completed Annual performance report by 31 August 2017 | R 5 000.00 | Completed Annual performance report by 31 August 2017 | X | Completed Annual performance report by 31 August 2017 | Achieved | Approved Annual Performace Report |  |  |
| KPI 24 | Mun 7 |  |  | Mid-year Assessment report | Conducted mid-year assessment | Date of Completion | Conducted mid-year assessment by 31 January 2018 | R 5 424.00 | X | X | X | In progress | Mid year Assessment Report | Target planned for Q3 | Municipality to ensure the Assessment is conducted |
| KPI 25 | Mun 8 |  |  | B2B | 16 Compiled B2B reports | Number of reports compiled. | 16 Compiled B2B reports by 30 June 2018 | R 0.00 | 4 B2B Reports | 4 B2B Reports | 8 B2B Reports | Achieved | Monthly and Quarterly B2B Reports |  |  |
| KPI 26 | Mun 9 |  |  | Oversight Report | Completed Oversight Report | Date of Adoption | Completed Oversight Report by 31 March 2018 | R 5 636.00 | X | X | X | Target in progress |  | Target planned for Q3 |  |
| KPI 27 | Mun 10 | To improve municipal corporate image | Review and Implementation of Communication Strategy | Provide a reviewed communication strategy | Reviewed Communication Strategy | Date of Adoption | Reviewed Communication Strategy by 30 June 2018 | R 0.00 | X | X | X | In progress | Draft Document (Comm Strategy) | Target not planned for Q2 |  |
| KPI 28 | Mun 11 |  |  | Establish a communications policy | Approved Communications policy | Date of Adoption | Approved Communication policy by 30 June 2017 | R 0.00 | X | X | X | In progress |  | Target not planned for Q2 | Municipality to ensure the adoption of this Policy by 30 June 2018 |
| KPI 29 | Cor 18 |  |  | Maintenance of website | Maintained and updated municipal website | Date of mantanance | Maintained and updated municipal website by 30 June 2018 | R 140 000.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 1 Report by 31 December 2017 | Achieved | Updated Website |  |  |
| KPI 30 | Mun 12 | To ensure effective and efficient Municipal Administration and Communication. | Development of Municipal branding | Newsletter | 4 Sets of Supplied & Delivered Newsletter | Number of newspaper publications | 4 Sets of Supplied & Delivered Newsletter by 30 June 2018 | R 50 000.00 | 1 Set of Supplied and Delivered Newsletter | X | 1 Set of Supplied and Delivered Newsletter | Not Achieved | None |  | Make Budget Provision next financial years |
| KPA 2: BASIC SERVICE DELIVERY & INFRASTRUCTURE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI 31 | Tech 1 | To ensure provision of basic services in a fair, equitable and sustainable manner | Provision of Free Basic Services | To provide free basic services to all indigent households with available resources | 2% of households provided with free basic services | % of households provided with free basi services. | 2% of households provided with free basic services by 30 June 2017 | R 1 471 680 | X | X | X | Not Achieved | None |  | Revise SDBIP due to non availability of Budget |
| KPI 32 | Tech 2 |  | Improvement of Access to Roads | Regravelling of Tholakele Access Road | Completed Tholakele Access Road | Date of Completion | Completed Tholakele Access Road ( Gravel Road )(Kwavova access from D 1875 ) By 30 June 2018 | R 2 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos | Pavement layers of gravel material, Gabion protection and Supervision |  |
| KPI 33 | Tech 3 |  |  | Izingudeli Pedistrian Bridge | Completed Izingudeni Pedestrian Bridge | Date of Completion | Completed Izingudeni Pedestrian Bridge By 30 June 2018 | R 3 500 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos | Reinforced concrete foundations, Construction of Structures and Supervision |  |
| KPI 34 | Tech 4 |  |  | Patching of Potholes | 15 000 sq/m of potholes patched | Number of sm/m patched | 15 000 sq/m of potholes patched By 30 June 2018 | R 1 000 000.00 | 3750 sq/m of potholes patched | 3750 sq/m of potholes patched | 7500 sq/m of potholes patched | Not Achieved | None | Department was unable to puchase asohalt due to fianancial issues | Make Budget Provision next financial years |
| KPI 35 | Tech 5 |  | Improvement of Access to Electricity | Obivane/Nkonkotho Electrification | Completed Obivane/Nkonkotho Electrification | Date of Completion | Completed Obivane/Nkonkotho Electrification By 30 June 2018 | R 7 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Q2 Target not Archieved | None | Project is currently on design stage. There were technical delays by the Service Provider during 2016/17 financial year | Infrastructure Department to monitor the project closely and impose penalties in case of such delays |
| KPI 36 | Tech 6 |  |  | Bulk Infrastructure Upgrade | Completed Bulk infrastructure Upgrade | Date of Completion | Completed Bulk infrastructure Upgrade By 30 June 2018 | R 6 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos | Construction and Supervision |  |
| KPI 37 | Tech 7 |  |  | Enkembeni Electrification Phase 4 | Completed Enkembeni Electrification Phase 4 | Date of Completion | Completed Enkembeni Electrification Phase 4 By 30 June 2018 | R 7 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Q2 Target not Archieved | None | Project is currently ongoing though there were technical delays | Infrastructure Department to monitor the project closely and impose penalties in case of such delays |
| KPI 38 | Tech 8 |  |  | Ward 1 Electrification | Completed Ward 1 Electrification | Date of Completion | Completed( Mahloni ) Ward 1 Electrification By 30 June 2018 | R 4 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Q2 Target not Archieved | None | Project on design stage. There were delays with Eskom approval | Infrastructure Department to impose penalties in case of delays |
| KPI 39 | Tech 9 |  |  | Ensuring Continuous Maintenance of Electrical Infrastructure | Fully maintained Electrical Infrastructure | Level of maintanance | Fully maintained Electrical Infrastructure By 30 June 2018 | R 1 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | List of new installations and replacements |  |  |
| KPI 40 | Tech 10 |  | Provision of Refuse Removal | residential and commercial waste collection | number of households & businesses with access to waste removal | % of households & Businesses with access to waste removal. | 5% of households & businesses with access to waste removal by 30 June 2018 | R 250 000.00 | X | X | X | Achieved | Schedule of households with access to waste removal |  |  |
| KPI 41 | PLD 2 |  | Improvement of access to sustainable human settlement | Facilitate Housing Forums | Housing Forums held | Number of housing forums | 10 Housing Forums held by 30 June 2018 | R 0.00 | 3 Housing Forums | 3 Housing Forums | 6 Housing Forums | Achieved | Attendance Registers |  |  |
| KPI 42 | PLD 3 |  |  | Conducting housing consumer education workshops | 4 Consumer Education Workshops conducted | Number of Consumer Education Conducted. | 4 Consumer Education Workshops conducted by 30 June 2018 | R 0.00 | 1 Consumer Education Workshop | 1 Consumer Education Workshop | 2 Consumer Education Workshops | Not Achieved | None | Unavailability of funds | Revise SDBIP |
| KPI 43 | Tech 11 |  | Improvement of Access to public facilities and amenities | Fencing of eDumbe Cemetry | Fully fenced eDumbe Cemetery | Date of Completion | Fully fenced eDumbe Cemetery by 30 June 2018 | R 2 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Not Achieved | None | Project on hold due to dispute by local Community | Council to take Decision and SDBIP be reviewed |
| KPI 44 | Tech 12 |  |  | Construction of Kanyekanye Hall | Completed Kanyekanye Hall | Date of Completion | Completed Kanyekanye Hall by 30 June 2018 | R 3 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos | Flooring, Block work and Supervision |  |
| KPI 45 | Tech 13 |  | Provision of Access to Sportfacilities | Construction of Mangosuthu Combi Court | Completed Mangosuthu Combi Court | Date of Completion | Completed Mangosuthu Combi Court by 30 June 2018 | R 2 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos |  |  |
| KPI 46 | Tech 14 |  |  | Upgrading of Impucuko Sportfield | Completed Impucuko Sportfield | Date of Completion | Completed Impucuko Sportfield by 30 June 2018 | R 2 964 800.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos |  |  |
| KPI 47 | Tech 15 |  |  | Construction of Ophuzane Combi Court | Completed Ophuzane Combi Court | Date of Completion | Completed Ophuzane Combi Court by 30 June 2018 | R 2 000 000.00 | Site Establishment | Commencement of work | Commencement of work | Achieved | Progress Report and Project photos |  |  |
| KPI 48 | Tech 16 |  | Ensuring Provision and Maintenance of Municipal Buildings | Maintenance of Municipal Buildings | Fully maintained municipal buildings | Date of Completion | Fully maintained municipal buildings by 30 June 2018 | R 200 000.00 | Fully maintained Municipal Buildings | Fully maintained Municipal Buildings | Fully maintained Municipal Buildings | Achieved | Progress Report |  |  |
| KPA 3: LOCAL ECONOMIC DEVELOPMENT AND SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI 49 | Tech 17 | To create conducive environment for sustainable economic growth and development | Job creation and promotion of employment opportunities | Implement EPWP Programme | 120 Work Opportunities created through EPWP Programme | Number of job opportunities created | 120 Work Opportunities created through EPWP Programme by 30 June 2018 | R 1 389 000.00 | 30 Work Opportunities | 30 Work Opportunities | 60 Work Opportunities | Not Achieved | None |  | Rephrase the Indicator to comply with the NDPW target |
| KPI 50 | Tech 18 |  |  | Create job opportunities through Capital projects | 30 Job opportunities created through each MIG Project | Number of job opportunities created | 30 Job opportunities created through each MIG Project by 30 June 2018 | R 0.00 | 8 Job Opportunities Created | 8 Job Opportunities Created | 16 Job Opportunities Created | In progress | None |  |  |
| KPI 51 | Com 1 |  |  | Coordinate the Implementation of CWP Programme | 4 Provincial CWP meetings attended | Number of CWP meetings attended | 4 Provincial CWP meetings attended by 30 June 2018 | R 0.00 | 1 Meeting Attended | 1 Meeting Attended | 2 Meetings Attended | Partially achieved | Attendance Register for Meeting attended in Q1 |  | SDBIP to be reviewed if the Municipality is unable to budget for such meetings |
| KPI 52 | Com 2 |  |  |  | 6 CWP Local Reference Committee Meetings held | Number of CWP Local Reference Committee Meetings held | 6 CWP Local Reference Committee Meetings held by 30 June 2018 | R 0.00 | 2 CWP Local Reference Meeting | X | 2 CWP Local Reference Meeting | Not Achieved | None | Meetings were put on hold until Further notice | Revise SDBIP |
| KPI 53 | PLD 1 |  |  | Create job opportunities through LED Projects | 10 Jobs created through LED Projects | Number of job opportunities created | 10 Jobs created through LED Projects by 30 June 2018 | R 0.00 | 2 Jobs created | 4 Jobs created |  |  |  |  |  |
| KPI 54 | PLD 2 |  | Development and Implementation of LED Strategy | Formulate LED Strategy | Approved LED Strategy | Date of approval | Reviewed LED Strategy by 30 June 2018 | R 0.00 | 1st Draft of the Document | 2 nd Draft of the Document | 2 nd Draft of the Document | Not Achieved | None | No capacity within the Municipality to formulate a Strategy (as per Departmental Report) | Revise SDBIP and Make Budget Provision |
| KPI 55 | PLD 3 |  | Development of Strategic Alliance and Partnership for economic growth and Development | Revive and support LED Forum | Revived LED Forum | Number of Forums | 4 LED Forum by 30 June 2018 | R 0.00 | 1 LED forum | 1 LED forum | 2 LED forums | Not Achieved | None | Due to Strategy not being formulated | Revise SDBIP and Make Budget Provision |
| KPI 56 | PLD 4 |  |  | Establish and support CTO | Established CTO | Date of Adoption | Established CTO by 30 September 2017 | R 0.00 | Established CTO by 30 September 2017 | X | X | Not Achieved | None | Due to unavailabilty of transport to visit BnB's | Revise SDBIP |
| KPI 57 | PLD 5 |  |  | Hosting of the LED summit | One summit held | Number of summits | One summit held by 30 June 2018 | R 0.00 | X | X | X | Not Achieved | None | Summit not budgeted | Revise SDBIP |
| KPI 58 | PLD 6 |  |  | Signing of agreements with development Agencies | Signed agreements with development Agencies | Date of Agreement | 1 Signed agreement with development Agencies by 30 June 2018 | R 0.00 | X | X | X | Not Achieved | None | Not planned for Q2 |  |
| KPI 59 | PLD 7 |  | Facilitation and Implementation of LED Anchor Projects | Facilitate the development of a Shopping Centre | Signed agreements with investors | Date of Agreement | 2 Signed agreements with investors by 31 December 2017 | R 0.00 | X | 2 Signed agreements with investors by 31 December 2017 | Signed agreements with investors by 31 December 2017 | Not Achieved | None | Target not achieved in Q2 but processes are on-going | Ensure the achievement of the Target, or revise SDBIP |
| KPI 60 | PLD 8 |  |  |  | Approved documents for the development of a Shopping Centre | Date of approval | Approved documents for the development of a Shopping Centre by 31 Dec 2017 | R 0.00 | X | Approved documents for the development of a Shopping Centre by 31 Dec 2017 | Approved documents for the development of a Shopping Centre by 31 Dec 2017 | Not Achieved | None | Target not achieved in Q2 but processes are on-going | Ensure the achievement of the Target, or revise SDBIP |
| KPI 61 | PLD 9 |  | Marketing and showcasing of economic and tourism development | Formulate Tourim Strategy | approved Tourism Strategy | Date of Adoption | Approved Tourism strategy by 30 June 2018 | R 0.00 | 1st Draft of the Document | 2 nd Draft of the Document | 2 nd Draft of the Document | Not Achieved | None | Unavailability of funds | Revise SDBIP |
| KPI 62 | PLD 10 |  | Formalizing the Informal Economy | Create Business incubation programme | Number of Trainings Facilitated | Number of Trainings Facilitated | 4 Facilitated Trainings on busines incubation programme by 30 June 2018 | R 0.00 | 1 Training Facilitated | 1 Training Facilitated | 2 Trainings Facilitated | Not Achieved | None | Unavailability of funds | Revise SDBIP |
| KPI 63 | PLD 11 |  |  | Informal Traders | 4 meetings held with Informal Traders Association | Number of Meetings held | 4 meetings held with Informal Traders Association by 30 June 2018 | R 0.00 | 1 Meeting | 1 Meeting | 2 Meetings | Not Achieved | None |  | Relevant Sections to ensure the functionality of this Association, otherwise Revise SDBIP it is not the core funtion |
| KPA 4: GOOD GOVERNANCE, COMMUNITY PARTICIPATION & WARD COMMITTEE SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI 64 | Com 3 | To promote effective community participation | Strengthening the functionality of Ward Committees | Conducting and attending ward committee meetings | 12 Sittings of Ward Committees | Number of sittings of Committee Meetings | 96 Sitting of Ward Committees Meetings by 30 June 2018 | R 576 000.00 | 24 Sittings of Ward Committees | 24 Sittings of Ward Committees | 48 Sittings of Ward Committees | Achieved | Attendance Registers |  |  |
| KPI 65 | Mun 13 |  | Review and Implemention of Community Participation Framework | Review and implement Community Participation Framework | Reviewed and implemented Community Participation Framework | Date of Adoption | Reviewed and implemented Community Participation Framework 30 June 2018 | R 0 00 | 1st Draft of the Document | Second Draft Of the Document | Second Draft Of the Document | Not Achieved | None | No Framework in place | Review SDBIP to place the Indicator to the relevant Department |
| KPI 66 | PLD 12 |  |  | Facilitate IDP Consultative Meeting | 16 IDP Road-shows held | Number of IDP consultatives | 16 IDP Road-shows held by 30 June 2018 | R 50 000.00 | X | 16 IDP Road-Shows | 8 IDP Road-Shows | Achieved | Attendance Registers |  |  |
| KPI 67 | PLD 13 |  |  | Facilitate IDP Representative Forums | 2 IDP Representative Forums held | Number of IDP Representative Forums held | 2 IDP Representative Forums held by 30 June 2018 | R 25 000.00 | X | 1 IDP Rep Forum | 1 IDP Rep Forum | Achieved | Q1 Attendance register |  |  |
| KPI 68 | Com 4 |  | Implemention of Operation Sukuma Sakhe | Functionality of war rooms | 12 sittings of war rooms | Number of sittings of War Rooms | 12 sittings of war rooms by 30 June 2018 | R 0.00 | 1 Sitting of war room | 1 Sitting of war room | 2 Sittings of war rooms | Achieved | Attendance Registers |  |  |
| KPI 69 | PLD 14 |  | Development and Implemention of Ward Based Plans | Facilitate Ward based plans | 8 Wards Based Plan Facilitated by 30 June 2018 | Number of Ward Based Plan | 8 Wards Based Plan Facilitated by 30 June 2018 | R 0 00 | 2 Ward Based Plans | 2 Ward Based Plans | 4 Ward Based Plans | In progress |  |  |  |
| KPI 70 | Com 5 | To promote cohesive social development | Implementation of Special Programmes | Implementation of Special Programmes | 4 Implemented Special Programmes | Number of Implemented Special Programmes | 4 Implemented Special Programmes by 30 June 2018 | R 100 000.00 | 2 Implemented Special Programmes | 2 Implemented Special Programmes | 4 Implemented Special Programmes | Not Achieved | None |  | Revise SDBIP if the Indicator is not budgeted |
| KPI 71 | Com 6 |  | Establishment of Functional Forums | Establishment of Youth Council | 1 Youth Council elected | Number of Youth Councils elected | 1 Youth Council elected by 30 September 2017 | R 0 00 | 1 Youth Council elected | X | 1 Youth Council elected | Not Achieved | None | All Forums were not established due to lack of resouces within the Municipality, i.e vehicles | Review SDBIP if Indicator is not budgeted |
| KPI 72 | Com 7 |  |  | Establishment of Sport Council | 1 Sport Council elected | Number of Sport Councils elected | 1 Sport Council elected by 30 September 2017 | R 0 00 | 1 Sport Council elected | X | 1 Sport Council elected | Not Achieved | None |  | Review SDBIP if Indicator is not budgeted |
| KPI 73 | Com 8 |  |  | Establishment of Women's Forum | 1 Women's Forum established | Number of established Forums | 1 Women's Forum established by 30 September 2017 | R 0 00 | 1 Women's Forum established | X | 1 Women's Forum established | Not Achieved | None |  | Review SDBIP if Indicator is not budgeted |
| KPI 74 | Com 9 |  |  | Establishment of Men's Forum | 1 Men's Forum established | Number of established Forums | 1 Men's Forum established by 30 September 2017 | R 0 00 | 1 Men's Forum established | X | 1 Men's Forum established | Not Achieved | None |  | Review SDBIP if Indicator is not budgeted |
| KPI 75 | Com 10 |  |  | Establishment of Eldery Forum | 1 Eldery Forum established | Number of established Forums | 1 Eldery Forum established by 30 June 2018 | R 0 00 | 1 Eldery Forum established | X | 1 Eldery Forum established | Not Achieved | None |  | Review SDBIP if Indicator is not budgeted |
| KPI 76 | Com 11 |  |  | Establishment of Disability Forum | 1 Disability Forum established | Number of established Forums | 1 Disability Forum established by 30 September 2017 | R 0 00 | 1 Disability Forum established | X | 1 Disability Forum established | Not Achieved | None |  | Review SDBIP if Indicator is not budgeted |
| KPI 77 | Com 12 |  |  | Establishment of HIV/Aids Forum | 1 HIV/Aids Forum established | Date of Adoption | 1 HIV/Aids Forum established by 30 September 2017 | R 0.00 | 1 HIV/Aids Forum established | X | 1 HIV/Aids Forum established | Not Achieved | None |  | Review SDBIP if Indicator is not budgeted |
| KPI 78 | Com 13 |  | Sports Development | Hosting of indigenous games | Hosted indigenous games | Number of Games | 3 Hosted indigenous games by 30 June 2018 | R 20 000, 00 | X | 1 Indigenous game | 1 Indigenous game | Achieved | Correspondence from SALGA and Time Sheets for official attended the games |  |  |
| KPI 79 | Com 14 |  |  | Hosting of Mayoral Games | Hosted Mayoral Games | Number of Games | 2Hosted Mayoral Games by 30 June 2018 | R 300 000, 00 | X | 1 Mayoral Game | 1 Mayoral Game | Achieved | Attendance Registers |  |  |
| KPI 80 | Com 15 |  |  | Hosting of Golden games | Hosted Golden games | Number of Games | 3 Hosted Golden games by 30 June 2018 | R 14 400, 00 | 1 Golden Game | 1 Golden Game | 2 Golden Games | Achieved | None | Department to keep attendance registers as POE |  |
| KPI 81 | Com 16 |  | HIV-Aids Intervention | Conducting HIV/AIDS Awareness Campaign | 4 Conducted HIV/AIDS Awareness Campaign | Number of HIV/AIDS Awareness Campaigns Conducted. | 4 Conducted HIV/AIDS Awareness Campaign by 30 June 2018 | R 50 000, 00 | 1 HIV/AID Awareness Campagn | 1 HIV/AID Awareness Campagn | 2 HIV/AID Awareness Campagns | Not Achieved | None | Awareness was not Conducted due to unavailability of resources | Review SDBIP if Indicator is not budgeted for |
| KPI 82 | Cor 19 |  | Facilitating the functioning of Council and Council Committees | Facilitating Sittings of Council Meeting | 04 Council Meeting Sittings facilitated | Number of Council Meetings | 04 Council Meeting Sittings facilitated by 30 June 2018 | R 0.00 | 1 Council Meeting | 1 Council Meeting | 2 Council Meetings | Achieved | Attendance Registers |  |  |
| KPI 83 | Cor 20 |  |  | Facilitating Sittings of Executive Committee | 12 Executive Committees Sittings facilitated | Number of Executive Committees Sittings facilitated | 12 Executive Committees Sittings facilitated by 30 June 2018 | R 0.00 | 3 Executive Committee Meetings | 3 Executive Committee Meetings | 6 Executive Committee Meetings | Achieved | Attendance Registers |  |  |
| KPI 84 | Cor 21 |  |  | Facilitating Sittings of Finance and Planning and Development portfolio committee meetings | 12 Finance and Planning and Development portfolio committee meetings facilitated | Number of Finance & Planning Portfolio Meetings | 12 Finance and Planning and Development portfolio committee meetings facilitated by 30 June 2018 | R 0.00 | 3 Finance & Planning Portfolio Meetings | 3 Finance & Planning Portfolio Meetings | 6 Finance & Planning Portfolio Meetings | Achieved | Attendance Registers |  |  |
| KPI 85 | Cor 22 |  |  | Facilitating Sittings of Technical Services Portfolio Committee meetings | 12 Technical Services Portfolio Committee meetings facilitated | Number of Technical Portfolio Meetings | 12 Technical Services Portfolio Committee meetings facilitated by 30 June 2018 | R 0.00 | 3 Technical Portfolio Meetings | 3 Technical Portfolio Meetings | 6 Technical Portfolio Meetings | Achieved | Attendance Registers |  |  |
| KPI 86 | Cor 23 |  |  | Facilitating Sittings of Community and Corporate Services Portfolio Committees | 12 Community and Corporate Services Portfolio Committees facilitate | Number of Community & Corporate Portfolio Committee Meetings | 12 Community and Corporate Services Portfolio Committees facilitate by 30 June 2018 | R 0.00 | 3 Community & Corporate Services Portfolio Meetings | 3 Community & Corporate Services Portfolio Meetings | 6 Community & Corporate Services Portfolio Meetings | Achieved | Attendance Registers |  |  |
| KPI 87 | Mun 14 |  |  | Facilitating Sittings of Municipal Public Accounts Committee (MPAC) | 04 Municipal Public Accounts Committee (MPAC)Meetings facilitated | Number of MPAC Facilitated Meetings | 04 Municipal Public Accounts Committee (MPAC)Meetings facilitated by 30 June 2018 | R 0.00 | 1 MPAC Meeting | 1 MPAC Meeting | 2 MPAC Meetings | Achieved | Attendance Registers |  |  |
| KPI 88 | Cor 24 |  |  | Facilitating Sittings of Audit Committee | 04 Audit Committee Meetings facilitated | Number of Audit Committee Meetings | 04 Audit Committee Meetings facilitated by 30 June 2018 | R 210 000, 00 | 1 Audit Committee Meeting | 1 Audit Committee Meeting | 2 Audit Committee Meetings | Q2 Target not Archieved | Attendance register for Q1 meeting | Only one Committee meeting was conducted | Municipality to ensure the functionality of the Audit Committee |
| KPI 89 | PLD 15 |  | Batho-Pele Principles | Batho-Pele Principles | Engangements with sector departments to do customer care survey | Conducted Costomer survey | Conducted Costomer survey by 30 June 2018 | R 0.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 1 Report by 31 December 2017 | Not Achieved | None |  | Relevant Section to facilitate this Survey or Revise SDBIP |
| KPI 90 | Com 17 |  | Promotion of arts, culture and heritage | Co-ordination of Umkhosi Womhlanga | 1 Umkhosi Womhlanga Coordinated | Number of Festivals hosted | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | R 100 000.00 | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | X | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | Achieved | Photos for Umkhoxi womhlanga |  |  |
| KPA 5: MUNICIPAL FINANCIAL VIABILITY & MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI 91 | Mun 15 | To improve municipal financial viability and sound financial management | To improve municipal audit opinion,council oversight and accountability | Establish Risk-based Internal audit plan | Approved Risk-based internal audit plan | Date of Adoption | Approved Risk-based internal audit plan by 30 September 2017 | R 1 490 470.00 | Approved Risk-based internal audit plan by 30 September 2017 | X | Approved Risk-based internal audit plan by 30 September 2017 | Not Achieved | None | IA plan not in place | Municipality to ensure the functionality of Internal Audit |
| KPI 92 | Mun 16 |  |  | Review of AC and IA Charters | Reviewed AC and IA Charters | Date of Adoption | Reviewed AC & IA Charters by 30 September 2017 | R 0.00 | Reviewed AC & IA Charters by 30 September 2017 | X | Reviewed AC & IA Charters by 30 September 2017 | Not Achieved | None | Charter not in place | Municipality to ensure the functionality of Internal Audit |
| KPI 93 | Mun 17 |  |  | Establish Internal Audit Methodology | Approved Internal Audit Methodology | Date of Adoption | Approved Internal Audit Methodology by 30 September 2017 | R 0.00 | Approved Internal Audit Methodology by 30 September 2017 | X | Approved Internal Audit Methodology by 30 September 2017 | Not Achieved | None | Methodology not in place | Municipality to ensure the functionality of Internal Audit |
| KPI 94 | Mun 18 |  |  | Conduct Audit Committee Assessments | Conducted Audit Committee Assessments | Date of Assessment | Conduct Audit Committee Assessments by 30 June 2018 | R 0.00 | X | X | X | Not Achieved | None |  | Municipality to ensure the functionality of Internal Audit |
| KPI 95 | Mun 19 |  |  | Review Risk Management Framework | Reviewed Risk Management Framework | Date of Adoption | Reviewed Risk Management Framework by 30 June 2018 | R 0.00 | X | X | X | In progress | Draft Framework document | Not planned for Q2 | Municipality to ensure the approval of this document before 30 June 2018 |
| KPI 96 | Mun 20 |  |  | Review Risk Management Policy | Reviewed Risk Management Policy | Date of Adoption | Reviewed Risk Management Policy by 30 June 2018 | R 0.00 | X | X | X | In progress | Draft Policy | Not planned for Q2 | Municipality to ensure the approval of this document before 30 June 2018 |
| KPI 97 | Mun 21 |  |  | Conducted Risk Assessment | Conducted Risk Assessment | Date of Assessment | Conducted Risk Assessment by 31 August 2017 | R 0.00 | Conducted Risk Assessment by 31 August 2017 | X | Conducted Risk Assessment by 31 August 2017 | Achieved | Attendance Register and Risk Register |  |  |
| KPI 98 | Mun 22 |  |  | Functional Risk Managment Committee | 4 Risk Management Committee Meetings | Number of Meetings | 4 Conducted Risk Committee Meetings by 30 June 2018 | R 0.00 | 1 Risk Committee Meeting | 1 Risk Committee Meeting | 2 Risk Committee Meetings | Achieved | Attendance Registers |  |  |
| KPI 99 | Mun 23 |  | Fraud and Corruption Prevention | Reviewed Fraud Prevention Plan | Reviewed Fraud Prevention Plan | Date of Adoption | Reviewed Fraud Prevention Plan by 30 June 2018 | R 0.00 | X | X | X | Not Achieved | None | Not planned for Q2 | Municipality to ensure the approval of this document before 30 June 2018 |
| KPI 100 | Mun 24 |  | Development and implemention of Audit Action Plan | Developed and 100% Implementation of Audit Action Plan | Developed Audit Action Plan | Date of Adoption | Developed Audit Action Plan by 31 January 2018 | R 0.00 | X | X | X | In progress | None | Not planned for Q2 | Municipality to ensure the availability of this document by end of Q3 |
| KPI 101 | Mun 25 |  |  | 100% Implementation of Audit Action Plan | 100% Implemented Audit Action Plan | Date of Adoption | 100% Implemented Audit Action Plan by 30 June 2018 | R 0.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 2 Reports by 31 December 2017 | Not Achieved | None | Target not achieved in Q2 but the exercise is on-going | Municipality to ensure to complete the exercise |
| KPI 102 | Mun 26 |  | Enhancement of Auditor-General engagement | Functional IDP/Budget Steering Committeee | 4 Dashboard Committee Meetings held | Number of Dashboard Committee Meetings | 4 Dashboard Committee Meetings held by 30 June 2018 | R 0.00 | 1 Dashboard Committee Meeting | 1 Dashboard Committee Meeting | 2 Dashboard Committee Meetings | Q2 Target not Archieved | Attendance Register for Q1 Dashboard meeting | Only one Dashboard meeting sat for Q1 | Municipality to ensure the functionality of this Committee |
| KPI 103 | Fin 1 |  | Payment to creditors to be made within 30 days in terms of section 65 of MFMA | 100% payment to creditors to be made within 30 days | 100% payment to creditors within 30 | Number of monthly reports | 12 Reports submitted by 30 June 2018 | R 0.00 | 3 Reports Submitted | 3 Reports Submitted | 6 Reports Submitted | Not Achieved | None | Invoices are not paid within 30 days | Revise Expenditure patterns |
| KPI 104 | Fin 2 | To improve municipal financial viability and sound financial management | Ensuring financial reporting and compliance | Submitted in-year Financial Reports in line with legislation | 17 Reports submitted by 30 June 2018 | Number of reports submitted. | 17 Reports submitted by 30 June 2018 | R 0.00 | 6 Reports Submitted | 6 Reports Submitted | 12 Reports Submitted | Achieved | Finance Sectional Reports |  |  |
| KPI 105 | Fin 3 |  | Implementing revenue enhancement strategy | Implemented Revenue Enhancement Strategy | 100% Implemented Revenue Enhancement Strategy | % of Implementation | 100% Implemented Revenue Enhancement Strategy by 30 June 2018 | R 0.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 2 Reports by 31 December 2017 | Achieved | Reports on Revenue enhancement |  |  |
| KPI 106 | Fin 4 |  | Revenue Management |  | 12 Reports submitted | Number of reports submitted. | 12 Reports submitted by 30 June 2018 | R 0.00 | 3 Reports Submitted | 3 Reports Submitted | 6 Reports Submitted | Achieved | Reports on Revenue collection outcomes |  |  |
| KPI 107 | Fin 5 |  |  | Enhance revenue collection | 90% revenue collection rate | % of revenue collection | 90% revenue collection rate by 30 June 2018 | R 186 000.00 | 3 Reports on Revenue collection | 3 Reports on Revenue collection | 6 Reports on Revenue collection | Not Achieved | Report indicating non achivement of 90% as planned | Collection rate on Refuse removal and Rates is far below than the billed amount | Municipality to finalise data cleansing and then implement revenue enhancement strategy |
| KPI 108 | Fin 6 |  | Expenditure Management | Formulated Plan for a Capital Budget | 100% Implemented the Capital Budget Plan | % of Implementation | 100% Implemented Capital Budget Plan by 30 June 2018 | R 0.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 2 Reports by 31 December 2017 | Not Achieved | Procurement Plan | Procurement paln not fully achieved | Revise Expenditure patterns |
| KPI 109 | Fin 7 |  |  | Formulated Plan for Operational Budget | 100% Implemented Operational Budget plan | % of Implementation | 100% Implemented Operational Budget plan by 30 June 2018 | R 0.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 2 Reports by 31 December 2017 | Not Achieved | Procurement Plan | Procurement paln not fully achieved | Revise Expenditure patterns |
| KPI 110 | Fin 8 |  |  | Monitored Expenditure against approved Budget | 12 Comparison reports prepared | Number of Reports | 12 Comparison reports prepared by 30 June 2018 | R 0.00 | 3 Comparison Reportrs | 3 Comparison Reportrs | 6 Comparison Reportrs | Not Achieved | None |  |  |
| KPI 111 | Fin 9 |  | Improving Budget Process and Implementation | Functional IDP/Budget Steering Committeee | 7 Steering Committee Meetings | Number of Steering Committee Meeting | 7 Steering Committee Meetings by 30 June 2018 | R 0.00 | 2 Steering Committee Meetings | 2 Steering Committee Meetings | 4 Steering Committee Meetings | Not Achieved | None | Committee is functional | Ensure the functionality of the Committee |
| KPI 112 | Fin 10 |  |  | An approved IDP/Budget Time Table (Process Plan) | An approved IDP/Budget Process Plan | Date of approval | An approved IDP/Budget Process Plan by 31 August 2017 | R 0.00 | An approved IDP/Budget Process Plan by 31 August 2017 | X | An approved IDP/Budget Process Plan by 31 August 2017 | Achieved | None |  |  |
| KPI 113 | Fin 11 |  | Enhancing Actual service charges and property rates revenue | Reviewed Tariffs | Reviewed Tariffs | Date of approval | Reviewed Tariffs by 30 June 2018 | R 0.00 | X | X | X | In progress |  | Not planned for Q2 |  |
| KPI 114 | Fin 12 |  |  | Implemented tariffs | Implemented tariffs | Level of implementation | Implemented tariffs by 30 June 2018 | R 0.00 | 1 Report by 30 September 2017 | 1 Report by 31 December 2017 | 2 Reports by 31 December 2017 | Achieved | Revenue Section monthly report |  |  |
| KPI 115 | Fin 13 |  |  | Implemented General Valuation and SV Roll | Implemented Valuation Roll | Level of implementation | Implemented Valuation Roll by 01 August 2017 | R 250 000.00 | Implemented Valuation Roll by 01 August 2017 | X | Implemented Valuation Roll by 01 August 2017 | Achieved | Ssupplementary Valuation Roll |  | Revise SDBIP to rephrase the Indicator |
| KPI 116 | Fin 14 |  |  | Preparation of the New General Valuation roll | Prepared New General Valuation Roll | Date of Adoption | Prepared New General Valuation Roll by 30 June 2018 | R 1 400 000.00 | X | X | X | Achieved | Ssupplementary Valuation Roll |  |  |
| KPI 117 | Fin 15 |  | Ensuring compliance with SCM Regulations | Reviewed SCM Policy | Reviewed SCM Policy | Date of Adoption | Reviewed SCM Policy per 30 June 2018 | R 0.00 | X | X | X | In progress | None | Not planned for Q2 |  |
| KPI 118 | Fin 16 |  |  | Appointed New Bid Committees | 3 Bid Committees appointed | Number of Bid Committees appointed | 3 Bid Committees appointed by 31 July 2017 | R 0.00 | 3 Bid Committees appointed by 31 July 2017 | X | 3 Bid Committees appointed by 31 July 2018 | Achieved | Appontment letters |  |  |
| KPI 119 | Fin 17 |  |  | Trained Bid Committees | 1 Training conducted | Number of Trainings conducted | 1 Training conducted by 30 September 2017 | R 0.00 | 1 Training Conducted | X | 1 Training Conducted | Not Achieved | None |  | Revise SDBIP |
| KPI 120 | Fin 18 |  |  | SCM Quarterly Reports | 4 SCM Reports | Number of SCM Reports | 4 SCM Reports by 30 June 2018 | R 0.00 | 1 SCM Report | 1 SCM Report | 2 SCM Reports | Achieved | Reports |  |  |
| KPI 121 | Fin 19 |  |  | Developed schedule of Bid Committee Meetings | Developed schedule of Bid Committee Meetings | Date of Adoption | Developed schedule of Bid Committee Meetings 30 September 2017 | R 0.00 | Developed schedule of Bid Committee Meetings | X | Developed schedule of Bid Committee Meetings | Not Achieved | None |  |  |
| KPI 122 | Fin 20 |  | Effective Management of Assets | Reviewed Fixed Asset Register | Reviewed Fixed Asset Register | Date of approval | Reviewed Fixed Asset Register by 30 June 2018 | R 600 000.00 | Review Asset Register | X | Review Asset Register | Achieved | Asset Register |  |  |
| KPI 123 | Fin 21 |  | Facilitating the appointment of Financial Interns | Appointed over a multi-year period | Five appointed interns | Number of Interns appointed | Five appointed interns by 30 June 2018 | R 575 000.00 | X | X | X | In progress | Advert | Target not planned for Q2 |  |
| KPI 124 | Fin 22 |  | Implementation of mSCOA | Implemented Municipal Standard Chart of Account | 4 reports on Municipal Standard Chart Account submitted | Number of reports submitted. | 4 reports on Municipal Standard Chart Account submitted by 30 June 2018 | R 1 325 000.00 | 1Report Submitted | 1Report Submitted | 2 Reports Submitted | Not Achieved |  | Programme is ongoing but no reports submitted | Revise SDBIP |
| KPI 125 | Fin 23 |  |  |  | 4 reports on Municipal Standard Chart Account submitted | Number of reports submitted. | 4 reports on Municipal Standard Chart Account submitted by 30 June 2018 | R 280 000.00 | 1Report Submitted | 1Report Submitted | 2 Reports Submitted | Not Achieved |  | Programme is ongoing but no reports submitted | Revise SDBIP |
| KPA 6 : CROSS CUTTING INTERVENTIONS (SPATIAL DEVELOMENT, ENVIRONMENT PLANNING & DISASTER MANAGEMENT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI 126 | PLD 16 | To ensure efficient and sound Strategic and Spatial municipal planning | Facilitate the formulation of the Credible IDP | Formulate IDP Process plan | 1 IDP process plan produced | Date of approval | 1 IDP process plan produced by 31 August 2017 | R 0.00 | 1 IDP process plan produced by 31 August 2017 | X | 1 IDP process plan produced by 31 August 2017 | Achieved | Council Resolution |  |  |
| KPI 127 | PLD 17 |  |  | Formulate a credible IDP | Approved IDP | Date of approval | Approved IDP by 30 June 2018 | R 0.00 | X | X | X | In progress |  | Target not planned for Q2 |  |
| KPI 128 | PLD 18 |  | Enhancing Municipal Spatial Planning | Develop Spatial Development Framework | Completed SDF | Date of approval | Completed SDF by 30 June 2018 | R 400 000.00 | X | X | X | In progress |  | Target not planned for Q2 |  |
| KPI 129 | PLD 19 |  |  | Develop Municipal Sector Plans | Completed Sector Plans | Date of Completion | x3 Completed Sector Plans by 30 June 2018 | R 1 100 000.00 | X | X | X | In progress |  | Target not planned for Q2 |  |
| KPI 130 | PLD 20 |  | Enhancing Land Use Management Systems | Establish Municipal Planning Tribunal (SPLUMA Implementation) | Established Municipal Tribunal by August 2018 | Date of Adoption | Established Municipal Tribunal by August 2018 | R 0.00 | Established Municipal Tribunal by August 2017 | X | Established Municipal Tribunal by August 2017 | Not Achieved | None | Waiting for Council Approval | Planning Department to forward item to Council |
| KPI 131 | PLD 21 |  |  | Develop Wall to Wall Land Use Scheme | CompletedPhase one of wall to wall scheme | Date of Completion | Completed Phase one of wall to wall scheme by June 2018 | R 1 000 000.00 | X | X | X | In progress |  | Target not planned for Q2 |  |
| KPI 132 | PLD 22 |  |  | Enforce Land Use Scheme | 100 % enforced Land Use Schemes | % Of enforcement | 100 % enforced Land Use Schemes by 30 June 2018 | R 0.00 | Enforce | Enforce | Enforce | In progress |  | Target not planned for Q2 |  |
| KPI 133 | Com 18 | To promote and preserve a safe and healthy environment | Enhancing Environmental Quality in Compliance with relevant legislation | Planting of greens and continous cleaning of parks and gardens | Completed Schedule of cleaning intervals | Date of Completion | Completed Schedule of cleaning intervals by 30 June 2018 | R 0.00 | X | X | X | Achieved | Waste removal schedule |  |  |
| KPI 134 | Com 19 |  |  |  | 10 Trees Planted | Date of Completion | 10 Trees Planted by 30 June 2018 | R 0.00 | X | 10 Trees Planted | 10 Trees Planted | Not Achieved | None |  | Revise SDBIP if the Indicator is not budgeted |
| KPI 135 | Com 20 |  |  | Facilitate process of legalising Waste Disposal | Legalized Waste Disposal by 30 June 2018 | Date of approval | Legalized Waste Disposal by 30 June 2018 | R 0.00 | X | Appointment of consultant | Appointment of consultant | In progress | Correspondence between the Municipality and Department of Environmental Affairs |  |  |
| KPI 136 | Cor 25 |  | Improving Municipal Response towards Disaster Occurences | Conduct public safety awareness campaign | 8 Conducted Public Safety Awareness Campaigns | Number of campaigns conducted | 8 Conducted Public Safety Awareness Campaigns by 30 June 2018 | R 0.00 | 2 Campaigns | 2 Campaigns | 4 Campaigns | Not Achieved | None |  | Revise SDBIP |

13. ANALYSIS OF MID-TERM PERFORMANCE ON EACH KEY PERFORMANCE AREA (KPA)

13.1. MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT

The performance on this KPA shows that the Municipality has achieved only 23% of the planned targets for the mid-term.  37% of targets were not achieved and 40% of targets are in progress as they were not planned for Q2.  This is still subject to auditing and verification process. The Edumbe Municipal Councillors were al trained, to ensure they understand the rules and orders of Local Government.  MPAC member as well were trained as to how to operate as a committee. This will result to the huge improvement to the functionality of the Municipality

The Challenges for non achievement of targets on this KPA is mostly  the unavailability of funds, e.g. among others things were the following

Gazetting of By-laws, implementation of Business Continuity Plan in case of disaster, purchasing of protective clothing.

Measures taken to improve performance

Corrective measure were indicated which recommends the Municipality to make budget provision next financial year or revise SDBIP.

Percentages on targets are as follows:

Achieved Targets 23%

Not Achieved 37%

Not planned for Q2 40%

13.2  BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT

The performance on this KPA shows that 61% of targets were achieved, 39% were Not achieved and 0% were not planned for Quarter 2.  Most of the Capital projects as planned and budgeted are currently on construction.  Though Enkembeni Electrification, Ward 1 Electrification and Fencing of eDumbe Cemetery currently shows a slow progress.

Among other Indicators, the patching of potholes is still a challenge due to budget constraints.

Measures taken to improve performance

The Municipality has noted this poor performance and will prioritise service delivery and make budget provision for this service. The Hounorable Mayor of eDumbe has also approached Sector Departments to bail out eDumbe Municipality in terms of Infrastructure Services, this was due to continuous deficit on the Municipal budget.  Therefore some projects have started through Small Town Rehabilitation programme.

Percentages on targets are as follows:

Achieved Targets 61%

Not Achieved 39%

Not planned for Q2  0%

13.3.  LOCAL ECONOMIC DEVELOPMENT

The performance on this Indicator shows a high level of non achievement on planned targets.  The percentages proves that systems are not in order with LED Section and Social Development.  More should be done to create more job opportunities through LED projects and porverty alleviation initiatives.  The non achievement is also  due to unavailability of funds and the lack of capacity within the Section.

Measure taken to improve performance

The Municipality has amalgamated Infrastructure and Planning Department, since the post for Directore has been vacant for some time.  The Director is now working on such issues of LED to improve the performance

Percentages on targets are as follows:

Not Achieved Targets  87%

Achieved Targets 0%

Targets in progress 13%

13.4  GOOD GOVERNANCE, COMMUNITY PARTICIPATION & WARD COMMITTEE SYSTEMS

Good governance according to the democratic principles is achieved through effective public participation. Not only does public participation allow constituents to monitor the governance record of its elected officials, but it also encourages the public to take an active interest in the performance of their municipality and region. It is only through broad public participation that citizens will recognise that their interests are taken to heart – especially the needs of the most vulnerable members of society. This allows all citizens to be heard in determining the political, social and economic priorities through the establishment of a broad societal consensus that includes civil society, government and the private sector. Active ward-based plans and consultative forums are central structures through which public participation and, ultimately, good governance can be achieved.

The Municipality has managed to fill very critical positions in Quarter 2,  i.e.  Municipal Manager and Director Corporate and Community Services.  The incumbents are resuming duties in January and February 2018

All Council Committees are functional and they meet as legislated.

Percentages on targets are as follows:

Not Achieved Targets  44%

Achieved Targets 52%

Targets in progress / Not planned for Q2 4%

13.5.  FINANCIAL VIABILITY AND FINANCE MANAGEMENT

The overall performance on this KPA shows that the Municipality is still experiencing cash flow problems.  Debtors Age analysis show a balance of about 82 000 000 owing by consumers to the Municipality.  This balance increases every month.  The Municipality has outdated Indigent register, Consumer data is not 100% correct.

The Municipality is sitting with a high volume of outstanding creditors which includes ESKOM account. The municipality is unable to pay within 30 days as legislated

Municipal investment properties/Assets are not yielding future economic benefits for the Municipality

Measure taken to improve performance

A Financial Recovery plan has been developed, with assistance by Sector Departments.  The Municipality has already statted the exercise of data cleansing in order to be able to enforce debt collection.  Advert for inviting Community to apply for indigent has been place.  This will assist the Municipality to be able to have an accurate billing

CoGTA and Provincial Treasury are assisting the Municipality in respect of Assest Management, verification, etc.

The Municipality has also engaged with Service Providers including ESKOM to come up with Payment Plans

Percentages on targets are as follows:

Not Achieved Targets  71%

Achieved Targets 23%

Targets in progress / Not planned for Q2 17%

.

13.6.  CROSS CUTTING INTERVENTION

Progress of municipal performance in this KPA had been assessed in the following  focus areas:

- Disaster management;

- Realigned municipalities;

- Urban and rural nodes; and

This is to be achieved through: capacitating municipalities to deliver quality services to communities; promoting participative, integrated and sustainable communities; ensuring municipal plans reflect national, provincial and local priorities and resources through sound intergovernmental relations; being the first port of call for municipalities for advice and support; facilitating delivery through sound administration and the engagement of all spheres of government and social partners.

Percentages on targets are as follows:

Not Achieved Targets  18%

Achieved Targets 27%

Targets in progress / Not planned for Q2 55%

14.  STATE OF READINESS ON NATIONAL DISASTER IMPLEMENTATION BY MUNICIPALITY

| 2016/17 Q2 |  |  |  |
| --- | --- | --- | --- |
| Functional disaster management centre | Disaster Management Head/ Manager appointed | Disaster management forums established | disaster management plan or framework in place |
| No | Yes | Yes | Yes |

15. CONCLUSION

The office of the Municipal Manager through PMS Unit maintains a Portfolio of Evidence to support the achievements recorded in this Mid-Term Performance Report, and Internal Audit has performed a verification of credibility of evidence of the reported achievements. Furthermore, in areas where performance was not achieved, the municipality has provided reasons and remedial actions to ensure that performance is improved in the next term of the year.

16.  RECOMMENDATIONS

As per the Council resolution taken by eDumbe Council on the 23 January 2018, It is highly recommended that

- eDumbe Municipality to review the SDBIP to ensure that targets are set on a smart principle

- eDumbe Municipality to consider an adjustment budget

17.  ACRONYMS

AFS	Annual financial statements

COGTA 	Department of Provincial and Local Government

IDP 	Integrated Development Plan

IGR	Intergovernmental Relations

IGRFA 	Intergovernmental Relations Framework Act

KPA 	Key performance area

KPI 	Key performance indicator

LED 	Local economic development

LGSETA 	Local Government Sector Education and Training Authority

MEC 	Member of executive committee

MFMA 	Municipal Finance Management Act

MIG 	Municipal infrastructure grant

MSA 	Municipal Systems Act

PMS 	Performance management system

PMU 	Project management unit

SALGA 	South African Local Government Association

SDF 	Spatial development framework