## MAIN
|  | REVISED ORGANIZATIONAL SDBIP 2018/2019 | [7 empty] | Year 2018/2019 |  |  | Q 1 |  | Q 2 |  | Mid Term |  | Q3 |  | Q4
| Strategic Objective | Strategy | Strategic Action/ Project | Key Performance Indicator (KPI) | Unit of Measure | Annual Target | Funding Source | Budget | WARD | DEMAND | BASELINE | BACKLOG | Projected Target | Budget | Projected Target | Budget | Projected Target | Budget | Projected Target | Budget | Projected Target | Budget | Responsible Department | POE
KPA 1: MUNICIPAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
KPI 1 |  |  | Develop a draft Integrated Waste Management Plan | To develop a draft Integrated Waste Management Plan by 30 June 2019 | Date | Developed draft Intergrated Waste Management Plan by 30 June 2019 | None | 0 | Institutional | None | None | None | Inception meetings with the Department of Environmental Affairs in respect of appointment of Service Provider and Funding | 0 | Appointment of Service Provider | 0 | Appointment of Service Provider | 0 | Inception Meeting and Scoping reports | 0 | Draft Intergrated Waste Management Plan | 0 | Corporate and Community Services | Draft Plan approved by Municipal Manager
KPI 2 |  | Gazzetting of by-laws | Gazzetting of Municipal By-laws | To gazzette 2 By-laws by 30 June 2019 | Number | Two By-laws gazzetted by 30 June 2019 | FMG | 55000 | Institutional | None | None | None | Developing By laws | 0 | Workshopping of BY-law, Pond By law, Electricity By law, Outdoor advertising By-law | 0 | Draft By-Laws | 0 | Draft By-Laws | 0 | Gazzette Final By-laws | 55000 | Corporate and Community Services | Proof of Gazzetting and Council Resolution
KPI 3 |  | Review of organogram | Review Municipal organogram | To review Municipal organogram by 30 June 2019 | Date | Reviewed Municipal organogram by 30 June 2019 | None | 0 | Institutional | None | None | None | Submissions from Departments | 0 | Re - engeneering of Draft Municipal Organogram and tabling to Council | 0 | Draft Municipal Organogram | 0 | Tabling of Draft Organogram | 0 | Reviewed and approved Organogram | 0 | Corporate and Community Services | Council Resolution
KPI 4 |  | Skills Development | Conduct training to staff and Councillors | To conduct MFMP training to 15 employees and 3 Councillors by 30 June 2019 | Number | Trained 15 employees and 3 Councillors by 30 June 2019 | FMG | As per the training costs | Institutional | None | None | None | Conducting skills development analysis with CoGTA | As per training costs | SCM Processes | 0 |  | 0 | Appointment of Service Provider | As per training costs | 15 trained employees and 3 Councillors | As per training costs | Corporate and Community Services | Attendance registers
KPI 5 |  | Skills Development | Provide training to 5 Women Councillors | To facilitate training by CoGTA for 5 Women Councillors by 30 June 2019 | Number | 5 Women Councillors trained by 30 June 2019 | CoGTA Grant | As per the training costs | Institutional |  |  |  | Conduct need analysis | 0 | Inception Meetings with the Funder | 0 | X | 0 | Trained 8 Women Councillors | 0 | Trained 8 Women Councillors | As per training costs | Corporate and Community Services | Attendance registers and Certificates
KPI 6 |  | Submission of compliance reports in line with legislation | Submit Workplace Skills Plan to LGSETA and Council | To submit the 2019/20 Workplace Skills Plan to LGSETA and Council by 31 May 2019 | Date | Submitted Workplace Skills Plan to LGSETA and Council by 31 May 2019 | None | 0 | Institutional | None | None | None | Implementation of the previous years WSP | 0 | Implementation of the previous years WSP | 0 | Implementation of the previous years WSP | 0 | Compilation of the skills audit | 0 | Submitted WSP by 31 May 2019 | X | Corporate and Community Services | Proof of submission
KPI 7 |  | Submitted compliance reports in line with legislation | Submit Employment Equity reports to DoL | To submit Employment Equity report to DoL by 31 January 2019 | Date | Submited Employment Equity report to DoL by 31 January 2019 | None | 0 | Institutional | None | None | None | Implementation of EEP as per vacant position | 0 | Implementation of EEP as per vacant position | 0 | Implementation of EEP as per vacant position | 0 | Submitted report to DoL | 0 | X | 0 | Corporate and Community Services | Proof of submission
KPI 8 |  | Review of ICT Governance Framework | Review ICT policies | To review ICT policies by 30 June 2019 | Date | Reviewed ICT policies by 30 June 2019 | None | 0 | Institutional | None | None | None | Reviewal of existing previous years ICT Policies | 0 | Workshopping of draft ICT Policies | 0 | X | 0 | Reviewed Policies | 0 | Reviewed Policies | 0 | Corporate and Community Services | Council Resolution
KPI 9 |  |  | Perform and submit information backups | To perform and submit monthly IT Backups and Registers to HOD by 30 June 2019 | Number | 12 Backups and Registers submitted to the HOD by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Backups and Registers performed and submitted | 0 | 3 Backups and Registers performed and submitted | 0 | 6 Backups and Registers performed and submitted | 0 | 3 Backups and Registers performed and submitted | 0 | 3 Backups and Registers performed and submitted | 0 | Corporate and Community Services | Screen shots and registers (signed by HOD)
KPI 10 |  |  | Perform information restores | To perform quarterly information Restores and Registers by 30 June 2019 | Number | 4 Restores and Register performed by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 Restore and Register performed | 0 | 1 Restore and Register performed | 0 | 2 Restores and Register performed | 0 | 1 Restore and Register performed | 0 | 1 Restore and Register performed | 0 | Corporate and Community Services | Screen shots and registers
KPI 11 |  |  | Review Access Logs | To review monthly Access logs by 30 June 2019 | Number | 12 Access logs Reviewed by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Logs Reviewed | 0 | 3 Logs Reviewed | 0 | 6 Logs Reviewed | 0 | 3 Logs Reviewed | 0 | 3 Logs Reviewed | 0 | Corporate and Community Services | Access Logs reports
KPI 12 |  | Improving the ICT Infrastructure | Review Disaster Recovery Plan and Business Continuity Plan | To review Disaster Recovery Plan and Business Continuity Plan by 30 June 2019 | Date | Reviewed DRP and BCP by 30 June 2019 | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | X | 0 | Reviewed DRP and BCP | 0 | Corporate and Community Services | DRP and BCP
KPI 13 |  |  | Monitor Antivirus software | To monitor quarterly antivirus software by 30 June 2019 | Number | 4 Monitored Antivirus software by 30 June 2019 | Internal Funding | 25000 | Institutional | None | None | None | 1 Monitored antivirus software | 0 | 1 Monitored antivirus software | 0 | Review and ensure that antivirus is updated | 0 | 1 Monitored antivirus software | X | 1 Monitored antivirus software | 25000 | Corporate and Community Services | Reports
KPI 14 |  |  | Purchase of Computers and software | To procure 16 Laptops by 30 June 2019. | Number | 16 Laptops procured by 30 June 2019 | Internal Funding | 390000 | Institutional | None | None | None | X | 0 | Commence SCM processed | 0 | X | 0 | Finalise SCM Processes | 0 | Purchased laptops | 390000 | Corporate and Community Services | Invoices
KPI 15 |  |  | Appoint Service Provider for Internet Service | To appoint Service Provider for Internet supply by 30 June 2019 | Date | Appointed Service Provider for Internet supply by 30 June 2019 | Internal Funding | 180000 | Institutional | None | None | None | X | 0 | Commence SCM processed | 180000 | Ensure sitting of Bid Committees | 0 | Ensure sitting of Bid Committees | 0 | Appointed Service Provider for Internet Supply | 0 | Corporate and Community Services | Appointment Letter
KPI 16 |  |  | Develop 2019/2020 SDBIP | To develop and approve the 2019/2020 SDBIP by 30 June 2019 | Date | Developed and approved 2019/2020 Organisational SDBIP by 30 June 2019 | Internal Funding | 5000 | Institutional | None | None | None | Review and conduct assessment on previous SDBIP (quarterly reports) | 0 | Review and conduct assessment on previous SDBIP (quarterly reports) | 0 | Review and conduct assessment on previous SDBIP (quarterly reports) | 0 | Draft 2019/2020 SDBIP | 0 | Approved 2019/2020 Final Organisational SDBIP | 5000 | All Departments | Approval letter by the Mayor
KPI 17 |  |  | Develop 2019/2020 Organizational Scorecard | To develop and approve the 2019/2020 Organisational Scorecard by 30 June 2019 | Date | Developed and approved 2019/2020 Organizational Scorecard by 30 June 2019 | Internal Funding | 5000 | Institutional | None | None | None | Review and conduct assessment on previous Scorecard (quarterly reports) | 0 | Review and conduct assessment on previous Scorecard (quarterly reports) | 0 | Review and conduct assessment on previous Scorecard (quarterly reports) | 0 | Draft 2019/2020 Organisational Scorecard | 0 | Approved 2019/2020 Final Organisational Scorecard | 5000 | All Departments | Approval letter by the Mayor
KPI 18 |  |  | Develop and sign Performance agreement | To develop and ensure signing of performance agreements for all filled S54 and 56 positions by 31 August 2018 | Date | Signed performance agreements for all filled S56 and 57 positions by 31 August 2018 | Internal Funding | 5000 | Institutional | None | None | None | Signed Performance Agreements for all filled S56/57 positions | 5000 | Collect information in preparation of assessment | 0 | X | 5000 | Ensure that provision ( of performance bonuses) on the budget is provided | 0 | Conduct final assessment and develop the following years performance agreements | 0 | Executive | Signed Performance Agreements
KPI 19 |  |  | Compile and submit to the AG the 2017/2018 Annual report | To compile and submit the 2017/2018 Annual Report to AG by 31 August 2018 | Date | Compiled and submitted Annual report to AG by 31 August 2018 | None | 0 | Institutional | None | None | None | Compiled and Submitted Annual Report to the AG | 0 | Development of an annual plan for compilation of 2018/19 annual report | 0 | Submitted Draft Annual Report | 0 | Compilation of a draft annual report for 2018/2019 | 0 | X | 0 | Executive | Proof of submission to AG
KPI 20 |  |  | Compile, approve and submit 2018/2019 Mid-term Performance report | To approve the 2018/2019 Mid-term Performance report by 26 January 2019 | Date | Approved 2018/2019 Mid term performance report by 26 January 2019 | None | 0 | Institutional | None | None | None | X | 0 | Collect quarterly reports for compilation of Final Annual Report | 0 | X | 0 | Approved and submitted Mid-term Performance report | 0 | X | 0 | Executive | Council Resolution and Confirmation letter by CoGTA
KPI 21 |  |  | compile and submit quartely B2B reports | To submit Quarterly B2B reports to Provincial Cogta by 30 June 2019 | Number | 4 submitted B2B reports to CoGTA by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 B2B Report submitted | 0 | 1 B2B Report submitted | 0 | 2 B2B Report and Support Plan submitted | 0 | 1 B2B Report submitted | 0 | 1 B2B Report submitted | 0 | Executive | Reports
KPI 22 |  |  | Compile, approve and submit the 2017/2018 Oversight Report | To develop and approve the Oversight report 60 days after the tabling of the annual report | Date | Approved and submitted Oversight Report within 60 days of the tabling of annual report | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | Adopted Oversight Report by 31 March 2019 | 0 | X | 0 | Executive | Council Resolution
KPI 23 |  |  | Review communications policy | To review Communication policy by 30 June 2019 | Date | Reviewed Communication policy by 30 June 2019 | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | X | 0 | Reviewed Communication policy by 30 June 2018 | 0 | Executive | Council Resolution
KPI 24 |  |  | Maintain the Municipal website | To ensure Municipal website is continously maintained and updated by 30 June 2019 | Date | Maintained Municipal website by 30 June 2019 | Internal Funding | 140000 | Institutional | None | None | None | Screen shots - Municipal IDP, Budget, Performance Agreements, Bids | 0 | Screen shots - Annual Report, Bids | 0 |  | 0 | Screen shots - Oversight report, Adjustment Budget, revised SDBIP, Draft Budgte, draft IDP and SDBIP, Bids | 0 | Screen shots - Approved Budget, SDBIP, Bids | 140000 | Corporate and Community Services | Screen shots
KPI 25 |  |  | Functionalise B2B | To conduct quarterly quarterly Back to Basics campaigns | Number | 4 Campaigns conducted by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 x B2B Campaing report (including photos) | 0 | 1 x B2B Campaing report (including photos) | 0 | 2 x B2B Campaing report (including photos) | 0 | 1 x B2B Campaing report (including photos) | 0 | 1 x B2B Campaing report (including photos) | 0 | All Departments | B2B reports (including photos)
KPA 2: BASIC SERVICE DELIVERY & INFRASTRUCTURE DEVELOPMENT
KPI 26 | To ensure provision of basic services in a fair, equitable and sustainable manner | Provision of Free Basic Services | Provide free basic services to all indigent households with available resources | To provide free basic electricity to 6008 Eskom indigent consumers by 30 June 2019 | Number | 6008 Eskom Indigent Consumers provided with free basic electricity by 30 June 2019 | EQS |  | All Wards | None | None | None | X | 0 | X | 0 | Ensure the receipt of consumption reports | 0 | Provide free basic electricity to qualifying Eskom Consumers | As per ESKOM invoices | Provide free basic electricity to qualifying Eskom Consumers | As per ESKOM invoices | Finance | List of ESKOM beneficiaries
KPI 27 |  |  |  | To provide free basic electricity to 174 Municipal indigent consumers by 30 June 2019 | Number | 174 Municipal Indigent Consumers provided with free basic electricity by 30 June 2019 | EQS |  | Ward 3 | None | None | None | X | 0 | Data collection | 0 | Data collection | 0 | Provide free basic electricity to qualifying Consumers | 0 | Provide free basic electricity to qualifying Consumers | 0 | Finance | List of beneficiaries
KPI 28 |  |  |  | To provide free basic waste to 174 Municipal indigent consumers by 30 June 2019 | Number | 174 Municipal Indigent Consumers provided with free basic waste removal by 30 June 2019 | EQS |  | Ward 3 | [5 empty] | Data collection | 0 | Data collection | 0 | Provide free basic waste removal to qualifying Consumers | 0 | Provide free basic waste removal to qualifying Consumers |  | Finance | List of beneficiaries
KPI 29 |  | Improvement of Access to Roads | Regravel eDumbe Cemetery Road | To re-surface 800 metres eDumbe Cemetery tarred road phase 1 by 30 June 2019 | Date | Re- surfaced eDumbe Cemetery tarred Road phase 1 by 30 June 2019 | MIG | 2200000 | Ward 3 | None | None | None | Advertisement | 50000 | Re-advertisement | 50000 | Appointment of Service Provide and 40% completed work | 1300000 | Appointment of Service Provide and 40% completed work | 1400000 | Practical Completion Certificate | 700000 | Infrastructure and Planning | Practical Completion Certificate
KPI 30 |  |  | Construct Nhlakanipho Pedestrian Crossing | To construct 40 metres long concrete surfaced Nhlakanipho Pedestrian Bribge by 30 June 2019 | Date | Constructed 40 metres Nhlakanipho Pedestrian Bridge by 30 June 2019 | MIG | 3082000 | Ward 8 | None | None | None | Tender Award | 50000 | Commencement of work | 1500000 | 50% Completed work | 1550000 | 85 % of Completed work | 800000 | Practical Completion Certificate | 732000 | Infrastructure and Planning | Practical Completion Certificate
KPI 31 |  |  | Construct Ebhishi Access Road | To construct 1.5 Km Ebhishi gravel Road by 30 June 2019 | Date | Constructed 1.5 km Ebhishi gravel Road by 30 June 2019 | MIG | 1700000 | Ward 6 | None | None | None | Tender Award | 50000 | Commencement of work | 1000000 | 50% Completed work | 1050000 | 85 % of Completed work | 550000 | Practical Completion Certificate | 600000 | Infrastructure and Planning | Practical Completion Certificate
KPI 32 |  |  | Construct Ebhishi Causeway | To construct Ebhishi Causeway by 30 June 2019 | Date | Constructed Ebhishi Causeway by 30 June 2019 | MIG | 1300000 | Ward 6 | None | None | None | X | 0 | X | 0 |  |  | Commencement of work | 250000 | Practical Completion Certificate | 250000 | Infrastructure and Planning | Practical Completion Certificate
KPI 33 |  | Improvement of access to Electricity | Provision of Infrastructure for Lenjane Electrification project | To complete Phase 2 of the Lenjane electricification project by 30 June 2019 (prior to house connection) | Date | Completed Phase 2 of the Lenjane electrification by 30 June 2019 | INEP | 2699054.37 | Ward 6 | None | None | None | Construction | 1000000 | 50% of Completed Work | 800000 | 50% of Completed Work | 1800000 | 75 % of Completed work | 600000 | Practical Completion Certificate | 299054.37 | Infrastructure and Planning | Practical Completion Certificate
KPI 34 |  |  | Connect and energize Nkonkotho project | To connect 140 Nkonkotho Households with electricity by 30 June 2019 (prior to energizing) | Number | 140 Hoseholds connected with electricity by 30 June 2019 | INEP | 4288729.54 | Ward 1 | Ward 1 | None | None | Construction | 1000000 | 50% of Completed Work | 2000000 | 50% of Completed Work | 3000000 | 90 % of Completed work | 1000000 | Practical Completion Certificate | 288729.54 | Infrastructure and Planning | Practical Completion Certificate
KPI 35 |  |  | KwaSonkela electrification | To finalise Planning stages ( Pre-marketing and Designs) for KwaSonkela Electrification by 30 June 2019 | Date | Finalised Planning stage ( Pre-marketing and Designs) for KwaSonkela Electrification by 30 June 2019 | INEP | 350000 | Ward 1 | None | None | None | Advertisement | 50000 | Pre-marketing and Tender award | 50000 | Pre-marketing and Tender award | 100000 | Completed Design Reports | 150000 | Final Designs | 100000 | Infrastructure and Planning | Design Reports
KPI 36 |  |  | Nkembeni Eletrification | To connect 50 Phase 4 Nkembeni electrified households by 30 June 2019 (prior to energizing) | Number | 50 Households connected with electricity by 30 June 2019 on Phase 4 of Nkembeni Electrification project | INEP | 2273787.68 | Ward 1 | None | None | None | Construction | 500000 | 50% of Completed Work | 500000 | 50% of Completed Work | 1000000 | 75 % of Completed work | 1200000 | Practical Completion Certificate | 73787.68 | Infrastructure and Planning | Practical Completion Certificate
KPI 37 |  |  | Zungwini Electrification (Designs) | To finalise Planning stages (designs) of Phase 1 for Zungwini Electrification by 30 June 2019 | Date | Finalised Planning stage for Phase 1 of Zungwini Electrification by 30 June 2019 | INEP | 416211.66 | Ward 7 | None | None | None | Advertisement | 50000 | Pre-marketing and Tender award | 50000 | Pre-marketing and Tender award | 100000 | Completed Design Reports | 250000 | Final Designs | 66211.66 | Infrastructure and Planning | Design Reports
KPI 38 |  |  | Ntungwini Electrification | To connect 138 of Phase 1 Ntungwini electrified households by 30 June 2019 (prior to energizing) | Number | 138 Households connected with electricity by 30 June 2019 for Phase 1 of Ntungwini project | INEP | 1904813.39 | Ward 7 | None | None | None | Construction | 700000 | 50% of Completed Work | 700000 | 50% of Completed Work | 1400000 | 75 % of Completed work | 350000 | Practical Completion Certificate | 154813.39 | Infrastructure and Planning | Practical Completion Certificate
KPI 39 |  |  | Bulk Infrastructure Upgrade | To complete infrastructure upgrade Phase 1 (install MV- and LV Network) by 30 June 2019 | Date | Installed New MV- and LV Network by 30 June 2019 | INEP | 160000 | Ward 3 | Ageing Infrastructure | Ageing Infrastructure | Ageing Infrastructure | Construction | 0 | Construction | 0 | Construction | 0 | 90 % of Completed work | 160000 | Practical Completion Certificate | 0 | Infrastructure and Planning | Practical Completion Certificate
KPI 40 |  |  | Bulk Infrastructure Upgrade (Designs) | To finalise infrastructure upgrade designs for Phase 2 of Ward 3 project by 30 June 2019 | Date | Finalised infrastructure upgrade designs for Phase 2 of Ward 3 project by 30 June 2019 | INEP | 1237166 | Ward 3 | Ageing Infrastructure | Ageing Infrastructure | Ageing Infrastructure | Design reports in progress | 0 | Design reports in progress | 0 | Design reports in progress | 0 | Completed Design Reports | 1237166 | Designs | 1237166 | Infrastructure and Planning | Design Reports
KPI 41 |  | Improvement of access to sustainable human settlement | Facilitate Housing Forums | To facilitate quarterly Housing Forum meetings by 30 June 2019 | Number | 4 Housing Forums facilitated by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 Housing Forum | 0 | 1 Housing Forums | 0 | 2 Housing Forums | 0 | 1 Housing Forums | 0 | 1 Housing Forums | 0 | Infrastructure and Planning | Attendance Register
KPI 42 |  |  | Tholakele Housing Project | To secure funding for construction of 300 units for Tholakele Housing project by 30 June 2019 | Date | Secured funding for 300 units of Tholakele Housing project by 30 June 2019 | Dept of HS | 40119552 | Ward 5 |  |  |  | Sorting of bilateral Agreements and SCM documents | 0 | Sorting out Bilateral Agreements and SCM documents | 0 | Sorting out Bilateral Agreements and SCM documents | 0 | Signing of Bilateral / Memorandum Agreements, | 0 | Signing of Bilateral / Memorandum Agreements, | 0 | Infrastructure and Planning | Attendance registers of all meetings and Construction
KPI 43 |  |  | Ophuzane Housing Project | To secure funding for construction of 300 units for Ophuzane Housing project by 30 June 2019 | Date | Secured funding for 300 units of Ophuzane Housing project by 30 June 2019 | Dept of HS | 40370046 | Ward 8 |  |  |  | Sorting of bilateral Agreements and SCM documents | 0 | Sorting out Bilateral Agreements and SCM documents | 0 | Sorting out Bilateral Agreements and SCM documents | 0 | Signing of Bilateral / Memorandum Agreements, | 0 | Signing of Bilateral / Memorandum Agreements, | 0 | Infrastructure and Planning | Attendance registers of all meetings and Construction
KPI 44 |  |  | Thubelisha Housing Project | To secure funding for construction of 300 units for Thubelisha Housing project by 30 June 2019 | Date | Secured funding for 300 units of Thubelisha Housing project by 30 June 2019 | Dept of HS | 3326590 | Ward 3 |  |  |  | Sorting of bilateral Agreements and SCM documents | 0 | Sorting out Bilateral Agreements and SCM documents | 0 | Sorting out Bilateral Agreements and SCM documents | 0 | Signing of Bilateral / Memorandum Agreements, | 0 | Signing of Bilateral / Memorandum Agreements, | 0 | Infrastructure and Planning | Feasibility study Reports
KPI 45 |  | Improvement of Access to public facilities and amenities | Construct Luneburg Community Hall | To construct 460 square metre new Luneburg Community Hall by 30 June 2019 | Date | Constructed Luneburg Community Hall by 30 June 2019 | MIG | 2850000 | Ward 1 | None | None | None | Tender Award | 100000 | Commencement of work | 750000 | 50% Completed work | 850000 | 60% of work completed | 1500000 | Practical Completion Certificate | 500000 | Infrastructure and Planning | Practical Completion Certificate
KPI 46 |  |  | Construct KwaGedlase Hall | To construct 460 square metres KwaGedlase Hall by 30 June 2019 | Date | Constructed KwaGedlase Hall by 30 June 2019 | MIG | 2850000 | Ward 6 | None | None | None | Tender Award | 100000 | Commencement of work | 750000 | 50% Completed work | 850000 | 40% of work completed | 1500000 | Practical Completion Certificate | 500000 | Infrastructure and Planning | Practical Completion Certificate
KPI 47 |  | Provision of Access to Sportfacilities | Construct KwaNgwanya Sportfield | To upgrade existing KwaNgwanya Sportfield by 30 June 2019 | Date | Constructed KwaNgwanya Sportfield by 30 June 2019 | MIG | 2250000 | Ward 7 | None | None | None | Tender Award | 70000 | Commencement of work | 450000 | 50% Completed work | 520000 | 80% of work completed | 1500000 | Practical Completion Certificate | 230000 | Infrastructure and Planning | Practical Completion Certificate
KPI 48 |  |  |  | To rehabilitate Phase 1 eBilanyoni Sportsfield by 30 June 2019 | Date | Rehabilitated eBilanyoni Sportfield by 30 June 2019 Phase 1 | MIG | 9000000 | Ward 4 | None | None | None | X |  | Commencement of work |  | 50% Completed work |  | 70% of work completed |  | Practical Completion Certificate |  | Infrastructure and Planning | Practical Completion Certificate
KPI 49 |  |  |  | To rehabilitate phase 2 eBilanyoni Sportsfield by 30 June 2019 | Date | Rehabilitated eBilanyoni Sportfield by 30 June 2019 Phase 2 | SPORT AND RECREATION | 4500000 | Ward 4 | None | None | None |  |  | Commencement of work |  | 50% Completed work |  | 90% of work completed |  | Practical Completion Certificate |  | Infrastructure and Planning | Practical Completion Certificate
KPI 50 |  |  | Construct Abaqulusi Sportfield | To construct new Abaqulusi sportfield by 30 June 2019 | Date | Constructed Abaqulusi Sportfield by 30 June 2019 | MIG | 2250000 | Ward 7 | None | None | None | Tender Award | 70000 | Commencement of work | 450000 | 60% Completed work | 520000 | 95% of work completed | 1500000 | Project Completion | 230000 | Infrastructure and Planning | Practical Completion Certificate
KPA 3: LOCAL ECONOMIC DEVELOPMENT
KPI 51 | To create conducive environment for sustainable economic growth and development | Job creation and promotion of employment opportunities | Impelement EPWP Programme | To create 228 Work Opportunities through EPWP and Capital Projects by 30 June 2019 | Number | 228 Work Opportunities created through EPWP and Capital Projects by 30 June 2019 | EPWP and Capital Grants Funding | 1103000 | Institutional | None | None | None | Quarterly Report on Work Opportunities created | As per the number created | Quarterly Report on Work Opportunities created | As per the number created | Quarterly Report on Work Opportunities created and maintained | As per the number created and maintained | Quarterly Report on Work Opportunities created | As per the number created | Quarterly Report on Work Opportunities created | 1103000 | Infrastructure Planning | EPWP system report
KPI 52 |  |  | Construct and install Market Stalls for Informal Traders | To construct and install Market stalls for Informal Traders by 30 June 2019 | Date | Constructed and installed Market Stalls by 30 June 2019 | CoGTA | 2000000 | Institutional | None | None | None | SCM Processes and identification of land | As per Business Plan | SCM Processes and identification of land | 0 | SCM Processes and identification of land | 0 | Appointment of Service Provider | 0 | Completed and installed Market stalls | 2000000 | Infrastructure & Planning | Market Stalls
KPI 53 |  | Formalizing the Informal Economy through Informal Traders | Formalise the Informal Traders | To conduct at least 2 meetings with Informal Traders Committee by 30 June 2019 | Number | 2 meetings conducted with Informal Traders Committee by 30 June 2019 | None | 0 | Institutional | None | None | None | X | 0 | 1 Meeting | 0 | 1 Meeting | 0 | X | 0 | 1 Meeting | 0 | Infrastructure & Planning | Attendance Register and Minutes of the meetings
KPA 4: GOOD GOVERNANCE, COMMUNITY PARTICIPATION & WARD COMMITTEE SYSTEM
KPI 54 |  |  | Facilitate IDP Consultative Meeting | To facilitate IDP Road-shows by 30 June 2019 | Date | Facilitated IDP Road-shows by 30 June 2019 | EQS | 0 | Institutional | None | None | None | X | 0 | 8 IDP Road-Shows | 0 | 8 IDP Road-Shows | 0 | X | 0 | 8 IDP Road-Shows | 0 | Infrastructure Planning | Attendance Register
KPI 55 |  |  | Facilitate IDP Representative Forums | To facilitate 2 IDP Representative Forums by 30 June 2019 | Number | 2 IDP Representative Forums facilitated by 30 June 2019 | EQS | 0 | Institutional | None | None | None | X | 0 | 1 IDP Rep Forum | 0 | 1 IDP Rep Forum | 0 | X | 0 | 1 IDP Rep Forum | 0 | Infrastructure Planning | Attendance Register
KPI 56 |  | Implemention of Operation Sukuma Sakhe | Ensure functionality of war rooms | To conduct monthly war rooms meetings by 30 June 2019 | Number | 12 war rooms meetings conducted by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Sitting of war room | 0 | 3 Sitting of war room | 0 | 6 Sittings of war rooms | 0 | 3 Sitting of war room | 0 | 3 Sitting of war room | 0 | Corporate and Community Services | Attendance Register
KPI 58 |  | Sports Development | Hosting of the indigenous games | To participate in indigenous games by 30 Sep 2018 | Date | Participated in indigenous games by 30 Sep 2018 | EQS | R 20 000, 00 | Institutional | None | None | None | 1 Indigenous game | 0 |  | 6666.7 | 1 Indigenous game | 6666.7 |  | 6666.7 |  | 6666.7 | Corporate and Community Services | Attendance Register
KPI 59 |  |  | Hosting the Mayoral Games | To participate in Mayoral Games by 31 March 2019 | Date | Participated in Mayoral Games by 31 March 2019 | EQS | R 300 000, 00 | Institutional | None | None | None | X | 0 | 1 Mayoral Game | 150000 | 1 Mayoral Game | 150000 |  | 150000 | X | X | Corporate and Community Services | Attendance Register
KPI 60 |  |  | Hosting the Golden games | To participate in Golden games by 30 Sep 2018 | Date | Participated in Golden games by 30 Sep 2018 | EQS | R 14 400, 00 | Institutional | None | None | None | 1 Golden Game | 4800 |  | 4800 | 2 Golden Games | 9600 |  | 4800 | X | X | Corporate and Community Services | Attendance Register
KPI 61 |  | Facilitating the functioning of Council and Council Committees | Facilitate sitting of Council meetings | To convene quarterly Council meetings by 30 June 2019 | Number | 04 Council meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 Council Meeting | 0 | 1 Council Meeting | 0 | 2 Council Meetings | 0 | 1 Council Meeting | 0 | 1 Council Meeting | 0 | Corporate and Community Services | Notice of the meetings
KPI 62 |  |  | Facilitate sitting of Executive Committee meetings | To convene monthly Executive Committee meetings by 30 June 2019 | Number | 12 Executive Committees meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Executive Committee Meetings | 0 | 3 Executive Committee Meetings | 0 | 6 Executive Committee Meetings | 0 | 3 Executive Committee Meetings | 0 | 3 Executive Committee Meetings | 0 | Corporate and Community Services | Notice of the meetings
KPI 63 |  |  | Facilitate sitting of Finance and Planning and Development portfolio committee meetings | To convene monthly Finance Portfolio committee meetings by 30 June 2019 | Number | 12 Finance and Planning Development portfolio committee meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Finance & Planning Portfolio Meetings | 0 | 3 Finance & Planning Portfolio Meetings | 0 | 6 Finance & Planning Portfolio Meetings | 0 | 3 Finance & Planning Portfolio Meetings | 0 | 3 Finance & Planning Portfolio Meetings | 0 | Corporate and Community Services | Notice of the meetings
KPI 64 |  |  | Faciliatate sitting of Technical Services Portfolio Committee meetings | To convene monthly Technical Services and Planning Portfolio Committee meetings by 30 June 2019 | Number | 12 Technical Services Portfolio Committee meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Technical Portfolio Meetings | 0 | 3 Technical Portfolio Meetings | 0 | 6 Technical Portfolio Meetings | 0 | 3 Technical Portfolio Meetings | 0 | 3 Technical Portfolio Meetings | 0 | Corporate and Community Services | Notice of the meetings
KPI 65 |  |  | Facilitate sittings of Community and Corporate Services Portfolio Committee meeting | To convene monthly Community and Corporate Services Portfolio Committee meetings by 30 June 2019 | Number | 12 Community and Corporate Services Portfolio Committee meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 3 Community & Corporate Services Portfolio Meetings | 0 | 3 Community & Corporate Services Portfolio Meetings | 0 | 6 Community & Corporate Services Portfolio Meetings | 0 | 3 Community & Corporate Services Portfolio Meetings | 0 | 3 Community & Corporate Services Portfolio Meetings | 0 | Corporate and Community Services | Notice of the meetings
KPI 66 |  |  | Facilitate sittings of Municipal Public Accounts Committee (MPAC) meeting | To convened quarterly Municipal Public Accounts Committee (MPAC) meetings by 30 June 2019 | Number | 04 Municipal Public Accounts Committee (MPAC) meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 MPAC Meeting | 0 | 1 MPAC Meeting | 0 | 2 MPAC Meetings | 0 | 1 MPAC Meeting | 0 | 1 MPAC Meeting | 0 | Corporate and Community Services | Notice of the meetings
KPI 67 |  |  | Facilitate sittings of Audit Committee | To convene quarterly Audit Committee Meetings by 30 June 2019 | Number | 04 Audit Committee Meetings held by 30 June 2019 | EQS | R 210 000, 00 | Institutional | None | None | None | 1 Audit Committee Meeting | 52500 | 1 Audit Committee Meetings | 52500 | 2 Audit Committee Meetings | R 1 05 000 .00 | 1 Audit Committee Meeting | 52500 | 1 Audit Committee Meeting | 52500 | Corporate and Community Services | Notice of the meetings
KPI 68 |  | Promotion of arts, culture and heritage | Co-ordinate Umkhosi Womhlanga | To host 1 Umkhosi Womhlanga event by 30 Sep 2018 | Number | 1 Umkhosi Womhlanga hosted by 30 September 2018 | EQS | 100000 | Institutional | None | None | None | 1 Umkhosi Womhlanga Coordinated by 30 September 2018 | 160000 | X | 0 | 1 Umkhosi Womhlanga Coordinated by 30 September 2017 | 160000 | X | 0 | X | 0 | Corporate and Community Services | Attendance
KPI 69 | To improve municipal financial viability and sound financial management | To improve municipal audit opinion,council oversight and accountability | Approve Risk-based Internal audit plan | To compile and approve the 2018/2019 Risk-based internal audit plan by 30 September 2018 | Date | Approved 2018/2019 Risk-based internal audit plan by 30 September 2018 | None | 0 | Institutional | None | None | None | Approved Internal Audit plan | 0 | X | 0 | X | 0 | X | 0 | X | 0 | Executive | Risk Based Audit Plan & Council Resolution
KPI 70 |  |  | Implement a Risk-based Internal Audit Plan | To compile quarterly reports in implementation of a Risk-based internal audit plan by 30 June 2019 | Number | 4 (Quarterly) reports on Risk-based internal audit plan developed by 30 June 2019 | None | 0 | Institutional | None | None | None | Quarterly Internal Audit report | 0 | Quarterly Internal Audit report | 0 | Quarterly Internal Audit report | 0 | Quarterly Internal Audit report | 0 | Quarterly Internal Audit report | 0 | Executive | Quarterly Internal Audit reports
KPI 71 |  |  | Review AC and IA Charters | To review the AC and IA Charters by 3o Sep 2018 | Date | Reviewed AC & IA Charters by 30 Sep 2018 | None | 0 | Institutional | None | None | None | Reviewed AC & IA Charters | 0 | X | 0 | X | 0 | X | 0 | X | 0 | Executive | Council Resolution
KPI 72 |  |  | Review Internal Audit Methodology | To establish and review the Internal Audit Methodology by 30 Sep 2018 | Date | Reviewed Internal Audit Methodology by 30 Sep 2018 | None | 0 | Institutional | None | None | None | Reviewed Internal Audit Methodology | 0 | X | 0 | X | 0 | X | 0 | X | 0 | Executive | Council Resolution
KPI 73 |  |  | Develop and approve AG audit action Plan | To develop and approve AG Audit Action Plan by 31 January 2019 | Date | Approved Audit Action Plan by 31 January 2019 | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | Approved AG audit action plan | 0 | X | 0 | Executive | Council Resolution
KPI 74 |  |  | Implement Auditor General Action Plan | To resolve 100% AG queries raised in 2016/2017, 2017/2018 financial year by 30 June 2019 | Percentage | 100% Resolved Findings on Tracking Register by 30 June 2019 | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | 40% findings resolved | 0 | 60% findings resolved | 0 | Executive | Annual Report and Council Resolution on AG queries
KPI 75 |  |  | Functionality of Audit Committee | To ensure the submission of quarterly Audit Committee reports submitted to Council by 30 June 2019 | Number | 4 Audit Committee reports submitted to Council by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 Audit Committee Report | 0 | 1 Audit Committee Report | 0 | 2 Audit Committee Report | 0 | 1 Audit Committee Report | 0 | 1 Audit Committee Report | 0 | Executive | Council Resolution
KPI 76 |  |  | Conduct the Organisational Risk Assessment | To conduct 1 (one) 2018/2019 Organisational Risk Assessment by 30 Sep 2018 | Number | 1 conducted 2018/2019 Organisational Risk Assessment by 30 Sep 2018 | None | 0 | Institutional | None | None | None | Risk Assessment conducted | 0 | X | 0 | Risk Assessment conducted | 0 | X | 0 | X | 0 | Executive | Risk Register
KPI 77 |  |  | Conduct the Organisational Risk Assessment | To conduct 1 2019/2020 Organisational Risk Assessment by 30 June 2019 | Number | 1 Conducted 2019/2020 Risk Assessment by 30 June 2019 | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | X | 0 | Risk Assessment conducted | 0 | Executive | Risk Register
KPI 78 |  |  | Functionalise Risk Managment Committee | To convene quarterly Technical Risk Management Committee Meetings by 30 June 2019 | Number | 4 Technical Risk Committee Meetings convened by 30 June 2019 | None | 0 | Institutional | None | None | None | 1 Technical Risk Committee Meeting | 0 | 1 Risk Committee Meeting | 0 | 2 Risk Committee Meetings | 0 | 1 Risk Committee Meeting | 0 | 1 Risk Committee Meeting | 0 | Executive | Attendance Registers
KPA 5: MUNICIPAL FINANCIAL VIABILITY & MANAGEMENT
KPI 79 |  | Payment to creditors to be made within 30 days in terms of section 65 of MFMA | Ensure payment of creditors within 30 days | To pay monthly Creditors within 30 days on monthly basis till 30 June 2019 | Percentage | Creditors paid within 30 days on monthly basis till 30 June 2019 | EQS | 0 | Institutional | None | None | None | Pay 50% of Creditors / Monthly Creditors Reconciliations | 0 | Pay 50% of Creditors / Monthly Creditors Reconciliations | 0 | Pay 50% of Creditors / Monthly Creditors Reconciliations | 0 | Pay 50% of Creditors / Monthly Creditors Reconciliations | 0 | Pay 50% of Creditors / Monthly Creditors Reconciliations | 0 | Finance | Creditors Age Analysis and Creditors Reconciliations
KPI 80 |  |  | Reducing accruals | To reduce accruals up to 10% by 30 June 2019 (as compared to previous years) | Percentage | 10% accruals reduced by 30 June 2019 | EQS | 0 | Institutional | None | None | None | Reports on Implemented Cost Cutting Measures | 0 | Reports on Implemented Cost Cutting Measures | 0 | Reports on Implemented Cost Cutting Measures | 0 | Reports on Implemented Cost Cutting Measures | 0 | Reports on Implemented Cost Cutting Measures | R 0 00 | Finance | Creditors Age Analysis
KPI 81 | To improve municipal financial viability and sound financial management | Ensuring financial reporting and compliance | Submit in-year Financial Reports in line with legislation | To compile and submit monthly Section 71 reports to Treasury within 10 working days by 30 June 2019 | Number | 12 monthly reports submitted to Treasury by 30 June 2019 | None | 0 | Institutional | None | None | None | Confirmation of submission by Treasury (July - Sep 2018) | 0 | Confirmation of submission by Treasury (Oct - Dec 2018) | 0 | Confirmation of submission by Treasury (July - Dec 2018) | 0 | Confirmation of submission by Treasury (Jan - March 2019) | 0 | Confirmation of submission by Treasury (April - June 2019) | 0 | Finance | 12 months confirmation of submission reports
KPI 82 |  | Revenue Management | Enhance revenue collection | To decrease debt book by 10% quarterly till 30 June 2019 | Percentage | 10% decreased debt book by 30 June 2019 | Property Rates | 186000 | Institutional | None | None | None | Debtors Age Analysis and Debtors Reconciliation reports (for July - Sep 2018) | 0 | Debtors Age Analysis and Debtors Reconciliation reports (for Oct - Dec 2018) | 0 | Debtors Age Analysis and Debtors Reconciliation reports (for July - Dec 2018) | 0 | Debtors Age Analysis and Debtors Reconciliation reports (for Jan - March 2019) | 0 | Debtors Age Analysis and Debtors Reconciliation reports (for April - June 2019) | 0 | Finance | 12 months Debtors Age Analysis and Debtors Reconciliations
KPI 83 |  |  | Ensure disconnection on outstanding electricity accounts | To implement monthly disconnections on outstanding electicity accounts by 30 June 2019 | Number | 12 monthly disconnections implemented on outstanding electricity accounts by 30 June 2019 | None | 0 | Institutional | Long outstanding Debts | None | Long outstanding Debts | July - Sep 2018 Disconnection list implemented | 0 | Oct - Dec 2018 Disconnection list implemented | 0 | July - Dec 2018 (Mid year) Disconnection list implemented | 0 | Jan - March 2019 Disconnection list implemented | 0 | April - June 2019 Disconnection list implemented | 0 | Finance and Electricity | Monthly disconnection lists (for 12 months)
KPI 84 |  |  |  | To reduce occurance / percentage of deviations to 10% by 30 June 2019 | Percentage | Reduced deviations by 30 June 2019 |  |  | Institutional |  |  |  | UIFW register for July 2018 - Sep 2018 | 0 | UIFW register for Oct 2018 - Dec 2018 | 0 | UIFW register for Mid term | 0 | UIFW register for Jan 2019 - March 2019 | 0 | UIFW register for April 2019 - June 2019 | 0 | Finance | 12 months UIFW Register
KPI 85 |  |  | Compile a draft five year plan General Valuation Roll | To compile a draft five year plan General Valuation Roll by 30 June 2019 | Date | compiled draft General Valuation Roll by 31 Dec 2018 | Rates | 200000 | Institutional | None | None | None | Appoint Service Provider | 0 | Inception meeting discussing the scope of works and project plan | 0 | X | 0 | Collection of information by Service Provider and update on progress | 0 | Draft Valuation Roll | 0 | Finance | Draft Valuation Roll signed by Accounting Officer
KPI 86 |  | Expenditure Management | Formulate a plan for Capital Budget expenditure | To spend 100% Capital Budget by 30 June 2019 | Percentage | 100% Implemented Capital Budget expenditure by 30 June 2019 | Grants | 0 | Institutional | None | None | None | Grant register report for all implemented Capital projects (July - Sep 2018) | 0 | Grant register report for all implemented Capital projects (Oct - Dec 2018) | 0 | Grant register report for all implemented Capital projects (Mid Term) | 0 | Grant register report for all implemented Capital projects (Jan - March 2019) | 0 | 100% expenditure on Capital Budget | 0 | Finance | Grant Register
KPI 87 |  |  | To ensure the proper allocation of Capital projects on a separate line as per MSCOA | To ensure Capital projects are allocated on a separate line item on the financial system to keep proper track record of expenditure per project by 31 June 2019 | Items | Capital Projects allocated on a separate line item by 31 July 2018 | None | 0 | Institutional | None | None | None | Balance Sheet (extracted from the Financial System) July - Sep | 0 | Balance Sheet (extracted from the Financial System) Oct - Dec | 0 | Balance Sheet (extracted from the Financial System) Mid term | 0 | Balance Sheet (extracted from the Financial System) Jan - March | 0 | Balance Sheet (extracted from the Financial System) April - June | 0 | Finance | 12 months Balance Sheet (extracted from the Financial System)
KPI 88 |  |  | Ensure training of Bid Committees | To conduct 1 training for all Bid Committee Members by 31 Dec 2018 | Number | 1 Training for Bid Committee Members conducted by 31 Dec 2018 | None | 0 | Institutional | None | None | None | X | 0 | 1 Training Conducted | R 0 00 | X | 0 | 1 Training Conducted | R 0 00 | X | R 0 00 | Finance | Proof of Trained Bid Committees / Attendance Register
KPI 89 |  |  | Develop and approve the Procurement Plan | To develop and approve and implement procurement plan by 30 Sep 2018 | Date | Developed, approved and implemented procurement plan by 30 September 2018 | None | 0 | Institutional | None | None | None | Developed and approved pocurement plan | 0 | Implement the Plan | 0 | Implement the Plan | 0 | Implement the Plan | 0 | Implement the Plan | 0 | Finance | Approved procurement plan
KPI 90 |  |  | Verification on movable Assets | To perform quarterly verifications on movable assets by 30 June 2019 | Number | 12 monthly verified movable assets by 30 June 2019 | None | 0 | Institutional | None | None | None | report on Asset verification on movable assets | X | report on Asset verification on movable assets | X | report on Asset verification on movable assets | X | report on Asset verification on movable assets | X | report on Asset verification on movable assets | 0 | Finance | Reports
KPA 6 : CROSS CUTTING INTERVENTIONS (SPATIAL DEVELOMENT, ENVIRONMENT PLANNING & DISASTER MANAGEMENT)
KPI 91 | To ensure efficient and sound Strategic and Spatial municipal planning | Facilitate the formulation of the Credible IDP | Formulate IDP process plan | To formulate and approve IDP process plan by 31 August 2018 | Date | Approved IDP process plan by 31 August 2018 | None | 0 | Institutional | None | None | None | 1 IDP process plan formulated and approved | 0 | X | 0 | 1 IDP process plan formulated | 0 | X | 0 | X | 0 | Infrastructure Planning | Council Resolution
KPI 92 |  |  | Formulate a credible IDP | To formulate and approved a credible IDP by 30 June 2019 | Date | Approved IDP by 30 June 2019 | None | 0 | Institutional | None | None | None | Table in Council IDP time schedule and deadlines | 0 | Situational analysis and submission of process plan | 0 | Roadshows and Rep Forums | 0 | Strategic Planning sessions, Draft ward based plans and Draft Plan | 0 | IDP and Budget roadshows, rep forum and Final IDP | 0 | Infrastructure Planning | Council Resolution
KPI 93 |  | Enhancing Municipal Spatial Planning | Develop Spatial Development Framework | To formulate and approve the SPLUMA compliant Spatial Development Framework by 30 June 2019 | Date | Approved SDF by 30 June 2019 | CoGTA | 1000000 | Institutional | None | None | None | Appointment of Service Provider, | As per Business Plan | PSC meetings, inception report | 0 | PSC meetings, inception report | 0 | Draft SDF Document | 0 | Final SDF Document | 1000000 | Infrastructure Planning | Council Resolution and Final SDF Document
KPI 94 |  | Enhancing Land Use Management Systems | To Establish Municipal Planning Tribunal (SPLUMA Implementation) by 30 June 2019 | To establish and approve the Municipal Tribunal by 30 June 2019 | Date | Approved Municipal Tribunal by 30 June 2019 | None | 0 | Institutional | None | None | None | Engage with District and CoGTA for establishment of Tribunal | 0 | X | 0 | X | 0 | Signed JMPT Agreement | 0 | Approved Terms of Reference for JMPT | 0 | Infrastructure Planning | Signed JMPT Agreement, TOR's and Council Resolution
KPI 95 |  |  | Develop Wall to Wall Land Use Scheme | To complete Phase two of wall to wall scheme by 30 June 2019 | Date | Completed Phase one of wall to wall scheme by June 2019 | COGTA | 1000000 | Institutional | None | None | None | Land use surveys in 8 wards | 0 | Finalising land use surveys, creating maps for land uses inspection | 0 | Finalising land use surveys, creating maps for land uses inspection | 0 | Draft Land use Management Framework, Draft Wall to Wall Scheme | 0 | Final Wall to Wall Scheme Document | 1000000 | Infrastructure Planning | Final Wall to Wall Scheme Document Council Resolution
KPI 96 |  |  | Enforce Land Use Scheme | To enforce 50 Land Use Scheme by 30 June 2019 | Number | 50 enforced Land Use Schemes by 30 June 2019 | None | 0 | Institutional | None | None | None | X | 0 | X | 0 | X | 0 | Door to door inspections | 0 | Door to door inspections | 0 | Infrastructure Planning | 50 Enforcement Letters
|  |  | _______________________________ |  | ______________________________
|  |  | SIGNED BY HONOURABLE MAYOR: CLLR SJ KUNENE |  | DATE

## Sheet1
2018/2019 ANNUAL PERFORMANCE REPORT - EDUMBE LOCAL MUNICIPALITY
SDBIP Ref | NATIONAL KEY PERFORMANCE AREAS | STRATEGIC OBJECTIVE | STRATEGIES | KEY PERFORMANCE INDICATOR | UNIT OF MEASURE | COMPARISON WITH 2017/2018 FINANCIAL YEAR |  | BUDGET 2018/2019 |  | CURRENT YEARS ACHIEVEMENT - 2018/2019 |  | STATUS (ACHIEVED/NOT ACHIEVED) | REASONS FOR VARIANCES | MEASURES TAKEN TO IMPROVE PERFORMANCE | RESPONSIBLE DEPARTMENT | WARD INFORMATION | PORTFOLIO OF EVIDENCE
[6 empty] | ANNUAL TARGET | ANNUAL ACTUAL | TARGET BUDGET | ACTUAL BUDGET | ANNUAL TARGET | ANNUAL ACTUAL
KPI 1 | MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | To improve Institutional capacity through Policy development and enforcement | Developing IWMP | To develop a draft Integrated Waste Management Plan by 30 June 2019 | Date | N/A | N/A | N/A | N/A | Developed draft Integrated Waste Management Plan by 30 June 2019 | Final Intergrated Waste Management Plan was developed by 30 June 2019 | Achieved | N/A | N/A | Community Services | Institutional | Final Intergrated Waste Management Plan report
KPI 2 |  |  | Gazzetting of Municipal By-laws | To gazzette 2 By-laws by 30 June 2019 | Number | N/A | N/A | 55000 | 0 | Two By-Laws gazetted by 30 June 2019 | By-laws were not gazzetted by 30 June 2019 | Not Achieved | N/A | By-laws will be gazzetted in August 2019 (2019/2020 financial year) | Corporate Services | Institutional | Draft By-laws
KPI 3 |  |  | Reviewing of Municipal organogram | To review Municipal organogram by 30 June 2019 | Date | Reviewed Municipal Organogram by 30 June 2018 | Organogram was not reviewed by 30 June 2018 | 0 | 0 | Reviewed Municipal Organogram by 30 June 2019 | Organogram was not reviewed by 30 June 2019 | Not Achieved | Organogram was tabled to Council with no success of approval | The Accounting Officer will table the organogram to Council again in 2019/2020 financial year | Corporate Services | Institutional | Council Resolution
KPI 4 |  |  | Skills development | To conduct MFMP training to 13 employees and 10 Councillors by 30 June 2019 | Number | N/A | N/A | 500000 | 500000 | MFMP training conducted and on-going to 13 employees and 10 Councillors by 30 June 2019 | MFMP training is conducted and on-going to 13 Employees and 10 Councillors by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Attendance registers
KPI 5 |  |  | Facilitate training to 5 Women Councillors | To facilitate training to 5 Women Councillors by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 5 Women Councillors trained by 30 June 2019 | 5 Women Councillors were trained by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | LGSETA Certificates
KPI 6 |  |  | Submit WSP to LGSETA | To submit the 2019/20 Workplace Skills Plan to LGSETA by 31 May 2019 | Date | Submitted Workplace skills Plan to LGSETA by 31 May 2018 | Workplace skills Plan was submitted to LGSETA by 31 May 2018 | N/A | N/A | Submitted Workplace Skills Plan to LGSETA by 31 May 2019 | Workplace skills Plan was submitted to LGSETA on by 31 May 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Proof of submission
KPI 7 |  |  | Submit Employment Equity to DoL | To submit Employment Equity report to DoL by 31 January 2019 | Date | Submitted Employment Equity report to DoL by 31 January 2018 | Employment Equity Plan was submitted to DoL by 31 January 2018 | N/A | N/A | Submited Employment Equity report to DoL by 31 January 2019 | Employment Equity Plan was submitted to DoL by 31 January 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Proof of submission
KPI 8 |  |  | Review ICT policies | To review ICT policies by 30 June 2019 | Date | Reviewed ICT policies by 30 June 2018 | ICT Policies were not reviewed by 30 June 2018 | N/A | N/A | Reviewed ICT policies by 30 June 2019 | ICT Policies were reviewed on 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Council Resolution
KPI 9 |  |  | Perform information backups and registers | To perform monthly IT Backups and Registers by 30 June 2019 | Number | 12 performed Backups and Registers by 30 June 2018 | 12 Backups and registers were performed by 30 June 2018 | N/A | N/A | 12 monthly Backups and Registers performed by 30 June 2019 | 12 monthly Backups and registers were performed by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Screen shots and registers
KPI 10 |  |  | Perform information restores | To perform quarterly information Restores and Registers by 30 June 2019 | Number | 4 performed information restores and registers by 30 Jun 2018 | 4 information restores and registers were performed by 30 Jun 2018 | N/A | N/A | 4 quarterly information Restores and Register performed by 30 June 2019 | 4 information restores and registers were performed by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Screen shots and registers
KPI 11 |  |  | review access logs | To review monthly Access logs by 30 June 2019 | Number | 12 reviewed access logs by 30 June 2018 | 12 access logs were reviewed by 30 June 2018 | N/A | N/A | 12 Access logs Reviewed by 30 June 2019 | 12 access logs were reviewed by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Access logs reports
KPI 12 |  |  | implement DRP and PCP | To implement Disaster Recovery Plan and Business Continuity Plan by 30 June 2019 | Date | Implemented DRP and BCP by 30 June 2018 | DRP and BCP was not implemented by 30 June 2018 | N/A | N/A | Implemented DRP and BCP by 30 June 2019 | DRP and BCP was not implemented by 30 June 2019 | Not Achieved | This was due to financial constraints | Corporate Services to source funds to purchase equipments for the implentation of the plans | Corporate Services | Institutional | Implemented DRP and BCP
KPI 13 |  |  | Purchase of computers and software | To procure 16 Laptops by 30 June 2019. | Number | N/A | N/A | 240000 | 199000 | Procured 16 Laptops by 30 June 2019 | 30 Laptops were procured by 30 June 2019 | Achieved | Due to shortage of computers for employees, 30 laptops were then purchased instead of 16 | N/A | Corporate Services | Institutional | Invoices
KPI 14 |  |  | Appoint service provider for PBX system and internet service | To appoint Service Provider for Internet supply by 30 June 2019 | Date | N/A | N/A | 180000 | 288011.99 | Appointed Service Provider for PBX System and Internet supply by 30 June 2019 | Service Provider for PBX System and internet supply was appointed by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Appointment letter
KPI 15 |  |  | Develop 2019/2020 SDBIP | To develop and approve the 2019/2020 SDBIP by 30 June 2019 | Date | Developed and approved 2018/2019 SDBIP by 30 June 2018 | 2018/2019 SDBIP was approved by 30 June 2018 | N/A | N/A | Developed and approved 2019/2020 Organisational SDBIP by 30 June 2019 | 2019/2020 SDBIP was developed and approved by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | Signed SDBIP
KPI 16 |  |  | Develop and sign Perf. Agreements | To develop and ensure signing of 2018/2019 performance agreements for all filled S54 and 56 positions by 31 August 2018 | Date | Developed and signed Performance Agreements for all filled S54/56 by 31 August 2017 | Performance Agreements for filled Section 54/56 positions were signed by 31 August 2017 | N/A | N/A | Developed and signed 2018/2019 performance agreements for all filled S54 and 56 positions by 31 August 2018 | Performance agreements for all filled S54/56 positions were developed and sigend by 31 August 2018 | Achieved | N/A | N/A | Executive | Institutional | Signed Performance agreements
KPI 17 |  |  | Compile and approve the 2017/2018 annual report | To compile and approve the 2017/2018 Annual Report within 7 months after the end of the financial year (MFMA 127 (2) | Date | Compiled and approved 2016/2017 Annual report within 7 months after the end of the financial year (MFMA 127 (2) | 2016/2017 Annual report was compiled and approved within 7 months after the end of the financial year (MFMA 127 (2) | N/A | N/A | Compiled and approved 2017/2018 Annual report within 7 months after the end of the financial year (MFMA 127 (2) | 2017/2018 Annual report was compiled and approved within 7 months after the end of the financial year (MFMA 127 (2) | Achieved | N/A | N/A | Executive | Institutional | Council Resolution
KPI 18 |  |  | compile and approve 2018/2019 mid-term performance report | To approve the 2018/2019 Mid-term Performance report by 26 January 2019 (MFMA 72) | Date | Approved 2017/2018 Mid-Term Performance report by 26 January 2018 | 2017/2018 Mid-Term performance report was approved by 26 January 2018 | N/A | N/A | Approved 2018/2019 Mid term performance report by 26 January 2019 | 2018/2019 Mid-Term performance report was approved on 26 January 2019 | Achieved | N/A | N/A | Executive | Institutional | Council Resolution
KPI 19 |  |  | compile and submit quarterly B2B reports | To submit Quarterly B2B reports to Provincial Cogta by 30 June 2019 | Number | 4 submitted B2B quarterly reports to CoGTA by 30 June 2018 | 4 quartely B2B reports were submitted to CoGTA by 30 June 2018 | N/A | N/A | 4 submitted B2B quarterly reports to CoGTA by 30 June 2019 | 4 quartely B2B reports were submitted to CoGTA by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | B2B Report
KPI 20 |  |  | compile and approve the 2017/2018 Oversight report | To develop and approve the Oversight report 60 days after the tabling of the annual report (MFMA 129 (1) | Date | Approved Oversight report by 31 March 2018 | Oversight report was approved by 31 March 2018 | N/A | N/A | Developed and approved Oversight Report within 60 days after the tabling of annual report (MFMA 129 (1) | Oversight report was developed and approved within 60 days after the tabling of annual report (MFMA 129 (1) | Achieved | N/A | N/A | Executive | Institutional | Council Resolution
KPI 21 |  |  | Maintain Municipal website | To ensure Municipal website is continously maintained and updated by 30 June 2019 | Date | Maintained Municipal website by 30 June 2018 | Website was continously maintained by 30 June 2018 | N/A | N/A | Maintained Municipal website by 30 June 2019 | Website was continously maintained by 30 June 2019 | Achieved | N/A | N/A | Corporate Services | Institutional | Screen shots
KPI 22 |  |  | functionalise B2B | To conduct quarterly quarterly Back to Basics campaigns | Number | N/A | N/A | N/A | N/A | Conducted 4 quarterly Back to Basics campaigns by 30 June 2019 | 4 quarterly Back to Basics Campaings were conducted by 30 June 2019 | Achieved | N/A | N/A | Community Services | Institutional | B2B campaign reports
KPI 23 | BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | To ensure provision of basic services in a fair, equitable and sustainable manner | Provide free basic services | To provide free basic electricity to 174 Municipal indigent consumers (after verification process) by 30 June 2019 | Number | N/A | N/A | 1400000 | 0 | 174 Municipal Indigent Consumers provided with free basic electricity (after verification process) by 30 June 2019 | 174 Municipal Indigent Consumers were provided with free basic electricity (after verification process) by 30 June 2019 | Achieved | N/A | N/A | Finance | Ward 3 | List of Municipal indigent beneficiaries
KPI 24 |  |  |  | To provide free basic waste to 174 Municipal indigent consumers (after verification process) by 30 June 2019 | Number | N/A | N/A | 1400000 | 0 | 174 Municipal Indigent Consumers provided with free basic waste removal (after verification process) by 30 June 2019 | 174 Municipal Indigent Consumers were provided with free basic waste (after verification process) by 30 June 2019 | Achieved | N/A | N/A | Finance | Ward 3 | List of Municipal indigent beneficiaries
KPI 25 |  |  | Re-surface eDumbe Cemetery road | To re-surface eDumbe Cemetery road phase 1 by 30 June 2019 | Date | N/A | N/A | 2200000 | 2715478.84 | Re- surfaced eDumbe Cemetery Road phase 1 by 30 June 2019 | eDumbe Cemetery road was re-sufaced by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 3 | Practical completion Certificate
KPI 26 |  |  | Construct Nhlakanipho Pedestrian crossing | To construct Nhlakanipho Pedestrian Bribge by 30 June 2019 | Date | N/A | N/A | 3082000 | 3261478.98 | Constructed Nhlakanipho Pedestrian Bridge by 30 June 2019 | Nhlakanipho Pedestrian bridge was constructed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 8 | Practical completion Certificate
KPI 27 |  |  | Construct Ebhishi access road | To construct Ebhishi gravel Road by 30 June 2019 | Date | N/A | N/A | 2200000 | 875357.1 | Constructed Ebhishi gravel Road by 30 June 2019 | Ebhishi road was constructed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 6 | Practical completion Certificate
KPI 28 |  |  | Construct Ebhishi causeway | To construct Ebhishi Causeway by 30 June 2019 | Date | N/A | N/A | 800000 | 781425 | Constructed Ebhishi Causeway by 30 June 2019 | Ebhishi causeway was constructed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 6 | Practical completion Certificate
KPI 29 |  |  | Provision of Infrastructure for Lenjane electrification project | To complete Phase 2 of the Lenjane electricification project by 30 June 2019 (prior to energizing) | Date | Completed feasibility study, pre-marketing, survey, detailed design approval and MV electrical infrastructure by 30 June 2018 | Feasibility study, pre-marketing, survey, detailed design approval and MV electrical infrastructure were completed by 30 June 2018 | 2699054.37 | 2699054.37 | Completed Phase 2 of the Lenjane electrification by 30 June 2019 | Phase 2 of Lenjane electrification was completed by 30 June 2019 (prior to energizing) | Achieved | N/A | N/A | Infrastructure | Ward 6 | Practical completion Certificate
KPI 30 |  |  | Connect and energize Nkonkotho project | To connect 140 Nkonkotho Households with electricity by 30 June 2019 (prior to energizing) | Number | Completed feasibility study, pre-marketing, survey, detailed design approval and MV electrical infrastructure by 30 June 2018 | Feasibility study, pre-marketing, survey, detailed design approval and MV electrical infrastructure were completed by 30 June 2018 | 4288729.54 | 4288729.54 | 140 Hoseholds connected with electricity by 30 June 2019 | 140 Nkonkotho Households were connected with Electrification by 30 June (prior/ awaiting oenergizing | Achieved | N/A | N/A | Infrastructure | Ward 1 | Practical completion Certificate
KPI 31 |  |  | KwaSonkela electrification | To finalise Planning stages (feasibility study) for KwaSonkela Electrification by 30 June 2019 | Date | N/A | N/A | 350000 | 350000 | Finalised Planning stage ( feasibility study) for KwaSonkela Electrification by 30 June 2019 | Planning stage (feasibility study) was finalised for kwaSonkela Electrification by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 1 | Feasibility study report
KPI 32 |  |  | Nkembeni Eletrification | To connect 50 Phase 4 Nkembeni electrified households by 30 June 2019 (prior to energizing) | Number | Completed pre-marketing, survey, and construction of MV electrical infrastructure by 30 June 2018 | Pre-marketing, survey, and construction of MV electrical infrastructure were completed by 30 June 2018 | 2273787.68 | 2273787.68 | 50 Households connected with electricity on Phase 4 of Nkembeni Electrification project by 30 June 2019 | 50 Households on phase 4 of Nkembeni were connected with electricity (prior to energizing) by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 1 | Practical completion Certificate
KPI 33 |  |  | Zungwini Electrification (Designs) | To finalise Planning stages (designs) of Phase 1 for Zungwini Electrification by 30 June 2019 | Date | N/A | N/A | 416211.66 | 416211.66 | Finalised Planning stage (designs) for Phase 1 of Zungwini Electrification by 30 June 2019 | Planning stage (Designs) were finalised for Phase 1 of Zungwini electrification by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 7 | Designs report
KPI 34 |  |  | Ntungwini Electrification | To connect 138 of Phase 1 Ntungwini electrified households by 30 June 2019 (prior to energizing) | Number | N/A | N/A | 1904813.39 | 1904813.39 | 138 Households connected with electricity for Phase 1 of Ntungwini project by 30 June 2019 | 138 Households were connected with electricity for phase 1 of Ntungwini project by 30 June 2019 (prior to energizing) | Achieved | N/A | N/A | Infrastructure | Ward 7 | Practical completion Certificate
KPI 35 |  |  | Bulk Infrastructure Upgrade | To complete infrastructure upgrade Phase 1 (install MV- and LV Network) by 30 June 2019 | Date | N/A | N/A | 160000 | 160000 | Installed New MV- and LV Network by 30 June 2019 | New MV and LV network were installed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 3 | Practical completion Certificate
KPI 36 |  |  | Bulk Infrastructure Upgrade (Designs) | To finalise infrastructure upgrade designs for Phase 2 of Ward 3 project by 30 June 2019 | Date | N/A | N/A | 1237166 | 1237166 | Finalised infrastructure upgrade designs for Phase 2 of Ward 3 project by 30 June 2019 | Infrastructure upgrade designs were finanlised for phase 2 of Ward 3 project by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 3 | Designs report
KPI 37 |  |  | Facilitate Housing Forums | To facilitate quarterly Housing Forum meetings by 30 June 2019 | Number | 4 facilitated housing forum meetings by 30 June 2018 | 4 housing forums were facilitated by 30 June 2018 | N/A | N/A | 4 Housing Forums facilitated by 30 June 2019 | 4 Housing Forum were Facilitated by 30 June 2019 | Achieved | N/A | N/A | Planning | Institutional | Minutes of Housing Forums meetings
KPI 38 |  |  | Tholakele Housing Project | To secure funding for construction of 300 units for Tholakele Housing project by 30 June 2019 | Date | N/A | N/A | N/A | N/A | Secured funding for 300 units of Tholakele Housing project by 30 June 2019 | Funding for 300 units of Tholakele Housing projects was secured by 30 June 2019 | Achieved | N/A | N/A | Planning | Ward 5 | Signed Memorundum of Agreements
KPI 39 |  |  | Ophuzane Housing Project | To secure funding for construction of 300 units for Ophuzane Housing project by 30 June 2019 | Date | N/A | N/A | N/A | N/A | Secured funding for 300 units of Ophuzane Housing project by 30 June 2019 | Funding for 300 units of Ophuzane Housing projects was secured by 30 June 2019 | Achieved | N/A | N/A | Planning | Ward 8 | Signed Memorundum of Agreements
KPI 40 |  |  | Thubelisha Housing Project | To secure funding for construction of 300 units for Thubelisha Housing project by 30 June 2019 | Date | N/A | N/A | N/A | N/A | Secured funding for 300 units of Thubelisha Housing project by 30 June 2019 | Funding for 300 units of Thubelisha Housing projects was secured by 30 June 2019 | Achieved | N/A | N/A | Planning | Ward 3 | Signed Memorundum of Agreements
KPI 41 |  |  | Construct Luneburg Community Hall | To construct Luneburg Community Hall by 30 June 2019 | Date | N/A | N/A | 2850000 | 2420788.93 | Constructed Luneburg Community Hall by 30 June 2019 | Luneburg Community Hall was constructed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 1 | Practical completion Certificate
KPI 42 |  |  | Construct KwaGedlase Hall | To construct 460 square metres KwaGedlase Hall by 30 June 2019 | Date | N/A | N/A | 2850000 | 2513341.94 | Constructed KwaGedlase Hall by 30 June 2019 | kwaGedlase Hall was not completely constructed by 30 June 2019 | Not Achieved | This was due to the slow construction progress by the appointed contractor | The Municipality terminated the contract due to slow progress and another Service Provider was appointed to fast track the progress | Infrastructure | Ward 6 | Project photos
KPI 43 |  |  | Construct KwaNgwanya Sportfield | To upgrade existing KwaNgwanya Sportfield by 30 June 2019 | Date | N/A | N/A | 2250000 | 2254087.89 | Constructed KwaNgwanya Sportfield by 30 June 2019 | kwaNgwanya sportfield was constructed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 2 | Practical completion Certificate
KPI 44 |  |  |  | To rehabilitate Phase 1 of eBilanyoni Sportsfield by 30 June 2019 | Date | N/A | N/A | 9000000 | 9000000 | Rehabilitated phase 1 of eBilanyoni Sportfield by 30 June 2019 | eBilanyoni sportfield phase 1 was rehabilitated by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 4 | Practical completion Certificate
KPI 45 |  |  |  | To rehabilitate phase 2 of eBilanyoni Sportsfield by 30 June 2019 | Date | N/A | N/A | 4500000 | 4075000 | Rehabilitated phase 2 of eBilanyoni Sportfield by 30 June 2019 | eBilanyoni sportfield phase 2 was rehabilitated by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 4 | Practical completion Certificate
KPI 46 |  |  | Construct Abaqulusi Sportfield | To construct new Abaqulusi sportfield by 30 June 2019 | Date | N/A | N/A | 2250000 | 2257487.48 | Constructed Abaqulusi Sportfield by 30 June 2019 | Abaqulusi sportfield was constructed by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Ward 7 | Practical completion Certificate
KPI 47 | LOCAL ECONOMIC DEVELOPMENT | To create conducive environment for sustainable economic growth and development | Impelement EPWP Programme | To create 228 Work Opportunities through EPWP and Capital Projects by 30 June 2019 | Number | N/A | N/A | 1103000 | 1103000 | 228 Work Opportunities created through EPWP and Capital Projects by 30 June 2019 | 246 Work opportunities were created through EPWP and Capital projects by 30 June 2019 | Achieved | N/A | N/A | Infrastructure | Institutional | District Quarterly report
KPI 48 |  |  | Construct and install Market Stalls for Informal Traders | To construct and install Market stalls for Informal Traders by 30 June 2019 | Date | N/A | N/A | 2000000 | 2000000 | Constructed and installed Market Stalls by 30 June 2019 | Market stalls for Informal Traders were constructed and installed by 30 June 2019 | Achieved | N/A | N/A | Planning | Ward 3 | Market stalls
KPI 49 |  |  | Formalise the Informal Traders | To conduct at least 2 meetings with Informal Traders Committee by 30 June 2019 | Number | 2 meetings conducted with Informal Traders Committee by 30 June 2018 | 2 meetings were conducted with Informal Traders Committee by 30 June 2018 | N/A | N/A | 2 meetings conducted with Informal Traders Committee by 30 June 2019 | 2 meetings were conducted with Informal Traders Committee by 30 June 2019 | Achieved | N/A | N/A | Planning | Institutional | Attendance register
KPI 50 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | To promote effective community participation | Facilitate IDP Consultative Meeting | To facilitate IDP Road-shows by 30 June 2019 | Date | Facilitated IDP Road-shows by 30 June 2018 | IDP road shows were facilitated by 30 June 2018 | N/A | N/A | Facilitated IDP Road-shows by 30 June 2019 | IDP road shows were facilitated by 30 June 2019 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Attendance registers
KPI 51 |  |  | Facilitate IDP Representative Forums | To facilitate 2 IDP Representative Forums by 30 June 2019 | Number | 2 IDP Representative Forums facilitated by 30 June 2018 | 2 IDP representative forums were facilitated by 30 June 2018 | N/A | N/A | 2 IDP Representative Forums facilitated by 30 June 2019 | 2 IDP representative forums were facilitated by 30 June 2019 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Attendance registers
KPI 52 |  |  | Ensure functionality of war rooms | To conduct 4 quarterly war rooms meetings by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 4 quarterly war rooms meetings conducted by 30 June 2019 | 4 quarterly war rooms meetings were conducted by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Attendance registers
KPI 53 |  |  | Indigenous games | To participate in indigenous games by 30 Sep 2018 | Date | Participated in indigenous games by 30 June 2018 | Partcipated in indigenous games by 30 June 2018 | 20000 | 20000 | Participated in indigenous games by 30 Sep 2018 | Partcipated in indigenous games by 30 Sep 2018 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Attendance registers
KPI 54 |  |  | Mayoral Games | To participate in Mayoral Games by 31 March 2019 | Date | Participated in Mayoral Games by 30 June 2018 | Participated in Mayoral games by 30 June 2018 | 410000 | 510000 | Participated in Mayoral Games by 31 March 2019 | Participated in Mayoral games by 31 March 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Attendance registers
KPI 55 |  |  | Golden games | To participate in Golden games by 30 Sep 2018 | Date | Participated in Golden games by 30 June 2018 | Participated in Golden games by 30 June 2018 | 14400 | 14400 | Participated in Golden games by 30 Sep 2018 | Participated in Golden games by 30 Sep 2018 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Attendance registers
KPI 56 |  |  | Facilitate sitting of Council meetings | To convene 4 quarterly Council meetings by 30 June 2019 | Number | 04 quarterly Council meetings convened by 30 June 2018 | 4 quarterly Council meeting were convened by 30 June 2018 | N/A | N/A | 04 quarterly Council meetings convened by 30 June 2019 | 4 quarterly Council meeting were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | 4 Notice of the meeting and Agendas
KPI 57 |  |  | Facilitate sitting of Executive Committee meetings | To convene 4 quarterly Executive Committee meetings by 30 June 2019 | Number | 4 quarterly Executive Committees meetings convened by 30 June 2018 | 4 quarterly Executive Committee meetings were convened by 30 June 2018 | N/A | N/A | 4 quarterly Executive Committees meetings convened by 30 June 2019 | 4 quarterly Executive Committee meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | 4 Notice of the meeting and Agendas
KPI 58 |  |  | Facilitate sitting of Finance portfolio committee meetings | To convene 4 quarterly Finance Portfolio committee meetings by 30 June 2019 | Number | 4 quarterly Finance portfolio committee meetings convened by 30 June 2018 | 4 quarterly Finance portfolio meetings were convened by 30 June 2018 | N/A | N/A | 4 quarterly Finance portfolio committee meetings convened by 30 June 2019 | 4 quarterly Finance portfolio meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Notice and agenda of the meetings
KPI 59 |  |  | Faciliatate sitting of Infrastructure and Planning Portfolio Committee meetings | To convene 4 quarterly Infrastructure Planning Portfolio Committee meetings by 30 June 2019 | Number | 4 quarterly Infrastructure and Planning Portfolio Committee meetings convened by 30 June 2018 | 4 quarterly Infrastructure and Planning Portfolio Committee meetings were convened by 30 June 2018 | N/A | N/A | 4 quarterly Infrastructure and Planning Portfolio Committee meetings convened by 30 June 2019 | 4 quarterly Infrastructure and Planning Portfolio Committee meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Notice and agenda of the meetings
KPI 60 |  |  | Facilitate sittings of Community and Corporate Services Portfolio Committee meeting | To convene 4 quarterly Community and Corporate Services Portfolio Committee meetings by 30 June 2019 | Number | 4 quarterly Community and Corporate Services Portfolio Committee meetings convened by 30 June 2018 | 4 quarterly Community and Corporate Services Portfolio Committee meetings were convened by 30 June 2018 | N/A | N/A | 4 quarterly Community and Corporate Services Portfolio Committee meetings convened by 30 June 2019 | 4 quarterly Community and Corporate Services Portfolio Committee meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Notice and agenda of the meetings
KPI 61 |  |  | Facilitate sittings of Municipal Public Accounts Committee (MPAC) meeting | To convened 4 quarterly Municipal Public Accounts Committee (MPAC) meetings by 30 June 2019 | Number | 04 quarterly Municipal Public Accounts Committee (MPAC) meetings convened by 30 June 2018 | 04 quarterly Municipal Public Accounts Committee (MPAC) meetings were convened by 30 June 2018 | N/A | N/A | 04 quarterly Municipal Public Accounts Committee (MPAC) meetings convened by 30 June 2019 | 04 quarterly Municipal Public Accounts Committee (MPAC) meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Notice and agenda of the meetings
KPI 62 |  |  | Facilitate sittings of Audit Committee | To convene 4 quarterly Audit Committee Meetings by 30 June 2019 | Number | 04 quarterly Audit Committee Meetings convened by 30 June 2018 | 04 quarterly Audit Committee Meetings were convened by 30 June 2018 | 210000 | 210000 | 04 quarterly Audit Committee Meetings convened by 30 June 2019 | 04 quarterly Audit Committee Meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Notice and agenda of the meetings
KPI 63 |  |  | Participate in Umkhosi Womhlanga | To participate in Umkhosi Womhlanga event by 30 Sep 2018 | Date | Participated in Umkhosi Womhlanga event by 30 September 2017 | Participated in Umkhosi Womhlanga event by 30 September 2017 | 120000 | 120000 | Participated in Umkhosi Womhlanga event by 30 September 2018 | Participated in Umkhosi Womhlanga event by 30 September 2018 | Achieved | N/A | N/A | Corporate and Community Services | Institutional | Umkhosi womhlanga report
KPI 64 |  |  | Approve Risk-based Internal audit plan | To compile and approve the 2018/2019 Risk-based internal audit plan by 30 September 2018 | Date | Approved risk based 2017/2018 risk based audit plan by 30 June 2018 | A risk based internal audit plan was approved by 30 June 2018 | N/A | N/A | Compiled and approved 2018/2019 Risk-based internal audit plan by 30 September 2018 | A risk based internal audit plan was copiled and approved by 30 September 2018 | Achieved | N/A | N/A | Executive | Institutional | Approved risk based audit plan
KPI 65 |  |  | Implement a Risk-based Internal Audit Plan | To compile 4 quarterly internal audit reports by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 4 (Quarterly) reports compiled by 30 June 2019 | 4 quarterly Internal audit reports were compiled by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | 4 quarterly internal audit reports
KPI 66 |  |  | Review AC and IA Charters | To review the AC and IA Charters by 30 June 2019 | Date | Reviewed AC & IA Charters by 30 June 2018 | AC and IA Charters were reviewed by 30 June 2018 | N/A | N/A | Reviewed AC & IA Charters by 30 June 2019 | AC and IA Charters were reviewed by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | Council Resolution
KPI 67 |  |  | Review Internal Audit Methodology | To review the Internal Audit Methodology by 30 June 2019 | Date | Reviewed Internal Audit Methodology by 30 June 2018 | Internal Audit Methodology was reviewed by 30 June 2018 | N/A | N/A | Reviewed Internal Audit Methodology by 30 June 2019 | Internal Audit Methodology was reviewed by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | Council Resolution
KPI 68 |  |  | Develop and approve AG audit action Plan | To develop and approve AG Audit Action Plan by 31 January 2019 | Date | Developed and approved AG action plan by 31 January 2018 | AG Audit action plan was developed and approved by 31 January 2018 | N/A | N/A | Developed and approved AG Audit Action Plan by 31 January 2019 | AG Audit action plan was developed and approved by 31 January 2019 | Achieved | N/A | N/A | Executive | Institutional | Council Resolution
KPI 69 |  |  | Implement Auditor General Action Plan | To resolve 100% AG queries raised in 2017/2018 financial year by 30 June 2019 | Percentage | N/A | N/A | N/A | N/A | 100% Resolved AG queries raised in 2017/2018 financial year by 30 June 2019 | 100% AG queries raised in 2017/2018 were resolved by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | Progress report
KPI 70 |  |  | Functionality of Audit Committee | To submit 4 quarterly Audit Committee reports to Council by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 4 quarterly Audit Committee reports submitted to Council by 30 June 2019 | 4 quarterly Audit Committee reports were submitted to Council by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | Audit Committee reports
KPI 71 |  |  | Conduct the Organisational Risk Assessment | To conduct 1 2018/2019 Organisational Risk Assessment by 30 Sep 2018 | Number | 1 conducted 2017/2018 Organisational Risk Assessment by 30 Sep 2017 | 1 2017/2018 Organisational Risk Assessment was conducted by 30 Sep 2017 | N/A | N/A | 1 conducted 2018/2019 Organisational Risk Assessment by 30 Sep 2018 | 1 2018/2019 Organisational Risk Assessment was conducted by 30 Sep 2018 | Achieved | N/A | N/A | Executive | Institutional | Risk Register
KPI 72 |  |  | Functionalise Risk Managment Committee | To convene 4 quarterly Technical Risk Management Committee Meetings by 30 June 2019 | Number | 4 quarterly Technical Risk Committee Meetings convened by 30 June 2018 | 4 quarterly Technical Risk Committee meetings were convened by 30 June 2018 | N/A | N/A | 4 quarterly Technical Risk Committee Meetings convened by 30 June 2019 | 4 quarterly Technical Risk Committee meetings were convened by 30 June 2019 | Achieved | N/A | N/A | Executive | Institutional | 4 quarterly risk reports
KPI 73 | MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | To improve municipal financial viability and sound financial management | Ensure payment of creditors within 30 days | To pay monthly Creditors within 30 days on monthly basis till 30 June 2019 | Date | Creditors paid within 30 days on monthly basis till 30 June 2018 | Creditors were not paid within 30 days on monthly basis till 30 June 2018 | Refer to Income statement and B/S | Refer to Income statement and B/S | Creditors paid within 30 days on monthly basis till 30 June 2019 | Creditors were not paid within 30 days on monthly basis till 30 June 2019 | Not Achieved | Financial Constraints | The Municipality has in-sourced some of the out-sourced services as part of cost cutting measures | Finance | Institutional | 12 months Creditors age analysis
KPI 74 |  |  | Submit in-year Financial Reports in line with legislation | To compile and submit 12 monthly Section 71 reports to Treasury within 10 working days by 30 June 2019 | Number | 12 monthly section 71 reports compiled and submitted to Treasury within 10 working days by 30 June 2018 | 12 monthly section 71 reports were compiled and submitted to treasurt within 10 working days by 30 June 2018 | N/A | N/A | 12 monthly section 71reports compiled and submitted to Treasury within 10 working days by 30 June 2019 | 12 monthly section 71 reports were compiled and submitted to treasurt within 10 working days by 30 June 2019 | Achieved | N/A | N/A | Finance | Institutional | 12 months confirmation of submission of reports
KPI 75 |  |  | Perform Debtors Recons | To perform monthly Debtors Reconciliations by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 12 monthly Debtors Recons performed by 30 June 2019 | 12 monthly Debtors Recons were performed by 30 June 2019 | Achieved | N/A | N/A | Finance | Institutional | Debtors Reconcilations
KPI 76 |  |  | Ensure disconnection on outstanding electricity accounts | To implement monthly disconnections on outstanding electicity accounts by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 12 monthly disconnections implemented on outstanding electricity accounts by 30 June 2019 | 12 monthly disconnections were implemented on outstanding electricity accounts by 30 June 2019 | Achieved | N/A | N/A | Finance | Institutional | Disconnection lists
KPI 77 |  |  | Compile a draft General Valuation Roll | To compile a draft General Valuation Roll by 30 June 2019 | Date | N/A | N/A | 1500000 | 999000 | Compiled draft General Valuation Roll by 30 June 2019 | Draft valuation roll was not completely compiled by 30 June 2019 | Not Achieved | Slow progress by Service Provider | Service provider has submitted the progress report and draft will be completed by end of August 2019. Extension of time for implementation was then granted by MEC to the Municipality | Finance | Institutional | Progress Report
KPI 78 |  |  | To ensure the proper allocation of Capital projects on a separate line as per MSCOA | To ensure Capital projects are allocated on a separate line item on the financial system to keep proper track record of expenditure per project by 30 June 2019 | Items | N/A | N/A | N/A | N/A | Allocated Capital Projects on a separate line item in the system to track record of expenditure per project by 30 June 2019 | Capital Projects were allocated on a separate line item in the system to track record of expenditure per project by 30 June 2019 | Achieved | N/A | N/A | Finance | Institutional | 12 months Balance Sheet
KPI 79 |  |  | Ensure training of Bid Committees | To conduct 1 training for all Bid Committee Members by 30 June 2019 | Number | 1 Training for Bid Committee Members conducted by 30 June 2018 | 1 Training for Bid Committee Members was conducted by 30 June 2018 | N/A | N/A | 1 Training for Bid Committee Members conducted by 30 June 2019 | 1 Training for Bid Committee Members was conducted by 30 June 2019 | Achieved | N/A | N/A | Finance | Institutional | Attendance register (Q2 POE file)
KPI 80 |  |  | Develop and approve the Procurement Plan | To develop and approve procurement plan by 30 Sep 2018 | Date | Developed and approved procurement plan by 30 September 2017 | Procurement plan was developed and approved by 30 Sep 2017 | N/A | N/A | Developed and approved procurement plan by 30 September 2018 | Procurement plan was developed and approved by 30 Sep 2018 | Achieved | N/A | N/A | Finance | Institutional | Approved Procurement Plan
KPI 81 |  |  | Verification on movable Assets | To perform 4 quarterly verifications on movable assets by 30 June 2019 | Number | N/A | N/A | N/A | N/A | 4 quarterly verified movable assets by 30 June 2019 | Movable assets were not verified on quarterly basis by 30 June 2019 | Not Achieved | Capacity constraints | The Municipality has out-sourced the Assets service to ensure the quartely assets verification and skills transfer | Finance | Institutional | Report on assets verification
KPI 82 | CROSS CUTTING INTERVENTIONS | To ensure effecient and sound stratedic and spatial municipal planning | Approve IDP process plan | To approve IDP process plan by 31 August 2018 | Date | Approved IDP process plan by 31 August 2017 | IDP process plan was approved by 31 Audust 2017 | N/A | N/A | Formulated and Approved IDP process plan by 31 August 2018 | IDP process plan was formulated and approved by 31 August 2018 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Council Resolution
KPI 83 |  |  | Formulate a credible IDP | To formulate and approved a credible IDP by 30 June 2019 | Date | Approved IDP by 30 June 2018 | IDP was approved by 30 June 2018 | N/A | N/A | Formulated and Approved IDP by 30 June 2019 | IDP was formulated and approved by 30 June 2019 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Council Resolution
KPI 84 |  |  | Develop Spatial Development Framework | To develop and approve the SPLUMA compliant Spatial Development Framework by 30 June 2019 | Date | Developed and approved SDF by 30 June 2019 | SDF was not developed and approved by 30 June 2019 | N/A | N/A | Developed and approved SDF by 30 June 2019 | SDF was developed and approved by 30 June 2019 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Draft SDF
KPI 85 |  |  | To Establish Municipal Planning Tribunal (SPLUMA Implementation) by 30 June 2019 | To establish and approve the Municipal Tribunal by 30 June 2019 | Date | Established and approved Municipal Tribunal by 30 June 2018 | Municipal Tribunal was not established and approved by 30 June 2018 | N/A | N/A | Established and approved Municipal Tribunal by 30 June 2019 | Municipal Tribunal was not established and approved by 30 June 2019 | Not Achieved | The establishment and funtionality of the Tribunal is in the District's control | The Municipality regularly engage with the District for the establishment of the Tribunal | Infrastructure and Planning | Institutional | Emails between the District Municipality and eDumbe Municipality
KPI 86 |  |  | Complete Wall to Wall Land Use Scheme | To complete Phase two of wall to wall scheme by 30 June 2019 | Date | N/A | N/A | 1000000 | 1000000 | Completed Phase two of wall to wall scheme by June 2019 | Phase two of wall to wall scheme was completed by by June 2019 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Council Resolution
KPI 87 |  |  | Enforce Land Use Scheme | To enforce 50 Land Use Scheme by 30 June 2019 | Number | 50 enforced Land Use Schemes by 30 June 2018 | 50 Land Use Schemes were not enforced by 30 June 2018 | N/A | N/A | 50 enforced Land Use Schemes by 30 June 2019 | 50 Land Use Schemes were enforced by 30 June 2019 | Achieved | N/A | N/A | Infrastructure and Planning | Institutional | Enforcement letters